AI-governed QMS evidence workflow · pharma / biotech · design-partner phase

Marketing Plan v1.1

Operational Companion to the Locked GTM Launch Flow

v1.1 update: Role clarification (Sense7ai DP team named) + Identified-Gap resolution

ArkOS CRM · LinkedIn Sales Navigator · Founder Outbox — Execution Handbook

Subordinate to:

Verixa Pilot Execution Plan v3 MASTER · 2026-05-31

Verixa GTM Launch Flow v2 · 2026-06-16

Verixa Design Partner Strategy LOCKED · 2026-05-22

W4 Founder Outreach Cards · 2026-06-10

Version 1.1  ·  18 June 2026  ·  W3 Thursday  ·  Role-Clarification Update

DRAFT — FOR EXTENDED POD REVIEW (10 reviewers per §18 sign-off)

Author: Vimal Veereshwarayya, PhD., RAC · Founder & CEO · vimalv@verixa.ai

Reviewers: Droupathy · Kavin · Manoj · Janani · Raja · Prakash · Manisha · Viji · Contractor

Classification: Internal · Verixa / Navira Quality Systems Pvt Ltd

# Read Before You Execute

This plan does NOT change anything that is already locked. If anything written here contradicts the GTM Launch Flow (Jun 16) or the W4 Outreach Cards (Jun 10) or the LOCKED DP Strategy (May 22), the locked source wins. Flag the contradiction to Vimal + Droupathy within 24h. The marketing pod commits the locked plan to execution; this companion gives you the operating detail.

### What this document gives you

- The day-to-day operational specs for ArkOS CRM, Apollo, Clay, LinkedIn Sales Navigator.

- The execution detail for the 9 workstreams already defined in the GTM Launch Flow swimlane.

- The compliance review workflow integration with the Public Claim Register (XLSX Sheet 14).

- The ABM operating mechanics for the 4 LIVE + 1 BLOCKED DP targets currently in the field.

- The handover and approval gates for every external claim (founder bandwidth protection).

### What this document does NOT give you

- A new ICP, new DP target list, new timeline, new gate calendar, new budget, or new KPI structure — those are all locked in the source documents named above.

- A justification for skipping any compliance check — the Public Claim Register is the auditable claim-control operating system. No exception.

- Permission to use any banned phrase from the W4 Outreach Cards. The phrasing rules are absolute (§5 below).

# Document Control

| Field | Value |
| --- | --- |
| Document Title | Verixa Marketing Plan v1.1 — Operational Companion |
| Status | Draft for Extended Pod Review (Marketing + Sense7ai DP Team named) |
| Issue Date | 18 June 2026 (W3 Thursday) |
| Supersedes | v1.0 (12 June 2026) |
| Effective Date | Mon 22 Jun 2026 (W4 start), upon 9-reviewer sign-off per §18 |
| Author | Vimal Veereshwarayya, PhD., RAC · Founder & CEO · Verixa |
| Lead Reviewer (A) | Droupathy (Marketing Lead) |
| Responsible Reviewers (R) | Kavin (Digital Marketing) · Manoj (Web/SEO) |
| Consulted — Verixa | Janani Rangesh (PM · Product Ownership) · Contractor (Compliance) |
| Consulted — Sense7ai DP Team | Raja (Technical ownership) · Prakash (PM coordination) · Manisha (UAT readiness) · Viji Janakiraman (Operating + leadership support · escalation) |
| Locked Source 1 | Verixa Pilot Execution Plan v3 MASTER (2026-05-31) |
| Locked Source 2 | Verixa GTM Launch Flow v2 (2026-06-16) · authoritative on what/when/who |
| Locked Source 3 | Verixa Design Partner Strategy LOCKED (2026-05-22) |
| Locked Source 4 | W4 Founder Outreach Cards (2026-06-10) · current DP target list |
| Locked Source 5 | Role Clarification Memo from Viji (2026-06-18) — folded into §2 of this plan |
| Compliance Anchor | Public Claim Register · Verixa GTM Launch Plan 2026 xlsx · Sheet 14 |
| External Positioning Rule | Sense7ai = Development Partner only · not embedded · not white-labeled · not a re-seller. Marketing-facing attribution: Verixa product owned by Verixa / Navira Quality Systems Pvt Ltd. |
| Brand | NOIR + MARIGOLD palette · Recoleta + Adobe Clean · Calibri for review-grade DOCX |
| Confidentiality | Internal · No external sharing without Founder approval |

## Change Log

Single working draft — we version only at the final stage. The substantive edits since first issue are noted below for the reviewers' reference. The currently open review pass is the founder-review edit pass (18 Jun 2026 PM).

| Pass | When | Substance |
| --- | --- | --- |
| First issue | 12 Jun 2026 · End of W2 | Initial operational companion to the locked GTM Launch Flow |
| Role-clarification pass | 18 Jun 2026 AM | Sense7ai DP team named (Raja · Prakash · Manisha · Viji) · Identified Gap resolved (Option C) · §17 inserted · approvals expanded to 10 |
| Founder-review pass | 18 Jun 2026 PM | COMMERCIAL PRIORITY OVERRIDE inserted (early) · W6 KILL-CHECK redefined to a single gate (paid sprint signed or LOI/MSA in legal) · Sep-01 renamed internally to "Evidence Maturity / Verified Go-Live Decision" · cover language softened · EU AI Act and FDA CSA glossary entries rewritten · Close-Call Readiness Checklist added (NEW §6.4) · Vimal daily calendar trimmed to true final-approval-only · PR posture reduced to "design-partner cohort open" · Webinar #1 date reconciled to W7 (Wed 15 Jul) live · reviewer count made consistent |
| Brand + patent-filing pass | 18 Jun 2026 PM | Official Verixa brand kit integrated: primary combination logo (Navy) on cover · Brand Mark in header · MARIGOLD #FFE388 · STONE #D5D5C9 · NOIR #13132B · VERMILION #E74E2E · FROST #C2E4F3 · Adobe Clean Bold (heading) + Adobe Clean Regular (body) · Recoleta in logo image only. Patent-filing date realignment: patent filing target Fri 26 Jun is the blocker for public marketing. W3-W4 = internal setup + founder 1-to-1 outbound only. W5 (Mon 29 Jun) = public marketing unlocks (newsletter · pillar pages · founder LinkedIn cadence · PR note · webinar invites). |
| Contractor interim + Stack simplification pass | 18 Jun 2026 PM | Contractor (CSV/CSA + RA) hire slipped past W2 target — Vimal holds interim first-pass + final-approval until hire closes (NOT Janani). MR-16 added. Hire-close target: before W6 KILL-CHECK Mon 06 Jul. Stack simplified: Apollo DEFERRED (re-evaluate W6 KILL-CHECK only if cold email becomes primary channel) · Clay DROPPED (revisit W14+ when volume justifies). Sales Navigator + ArkOS + Vimal's outbox carry the load for 4 LIVE DP targets + 14 broader ICPs. §3 + §7 + §13.4 + §16 W3 row + Appendix B + Appendix C all updated. Annual budget savings ~US$13K-17K. |
| Founder review pass #3 — 10 cleanup edits | 18 Jun 2026 evening | Cover subtitle changed to "ArkOS CRM · LinkedIn Sales Navigator · Founder Outbox — Execution Handbook." NEW "Contractor Hard Deadline + Interim-Vimal Continuation Rule" near front — founder decision: if contractor not hired by 30 Jun, Vimal continues as interim with MANDATORY mitigations (external counsel retainer + 60% cadence + conservative phrasing + weekly audit + written risk acceptance). W6 KILL-CHECK redefined to single gate everywhere (Green = 1 paid sprint signed OR 1 priced LOI/MSA in legal with scope agreed) · MQL/SQL removed from W6 gate. NEW dual gate for W5 public marketing unlock (patent counsel clearance + compliance gate). "audit-ready"/"inspection-ready" replaced with structured-evidence vocabulary in customer-facing copy. OOS 38% example deleted. Phase 1 distinction added (Product module set vs Commercial sprint scope). Data residency claim flagged for architecture proof + security review. FDA CSA glossary qualified (medical-device-led). NEW Appendix I "Active vs Deferred Work" anti-drift reference. NEW Appendix J "W6 KILL-CHECK Gate Sheet" single-source reference. Reviewer count locked at 10 = 9 internal + 1 Contractor (or interim). |

# Commercial Priority Override

Until the first paid design-partner sprint is signed, all marketing work is subordinate to paid sprint conversion. PR, podcasts, broad MQL targets, general content, and non-essential paid campaigns may be deferred if they compete with founder close bandwidth, buyer due diligence, legal readiness, or demo preparation.

This override sits above every section that follows. Where a workstream commitment in this plan would compete with paid-sprint close, the workstream defers — automatically, no debate. The pod aligns on the close target weekly at the Friday GTM sync.

### What This Means In Practice

- PR splash language on Fri 26 Jun reduced to "design-partner cohort open." Save the heavier launch posture for verified-go-live decision.

- Broad MQL / SQL volume targets are not the W6 gate. The gate is paid-sprint close (see §1.2 W6 row).

- General content + SEO/AEO/GEO continue at minimum viable cadence until first paid sprint signed. Manoj pauses non-essential SEO/GEO work.

- Webinars + podcast appearances remain in the calendar but Vimal personally defers any scheduled engagement that competes with a live close window.

- Founder close bandwidth, buyer due diligence response, legal readiness on the LOI / MSA / SoW, and demo preparation always come first.

Discipline check: the Friday GTM sync opens by asking — "What did we do this week that moved the first paid sprint forward?" — before anything else.

# Contractor Hard Deadline + Interim-Vimal Continuation Rule

Hard contractor-hire deadline: Tue 30 Jun 2026. Founder decision (18 Jun 2026): if the External CSV/CSA + RA Contractor is not hired and onboarded by Tue 30 Jun 2026 17:00 IST, public marketing CONTINUES under the Interim-Vimal model — Vimal holds both first-pass and final claim review until contractor is onboarded. This is Vimal's explicit risk acceptance and supersedes the freeze default. NOT Janani. The mitigations below become MANDATORY, not optional, the moment the 30 Jun deadline passes.

### Interim-Vimal Mandatory Mitigations (Effective 01 Jul 2026 if contractor not onboarded)

- Public cadence reduced to 60% of planned volume (newsletter bi-weekly only · LinkedIn 3×/wk max · webinar #1 invites continue · paid ABM held at minimum spend).

- External counsel review (paid retainer) on every asset making any regulatory, validation, audit-readiness, AI-governance, EU AI Act, FDA CSA, data residency, or compliance-positioning claim. Vimal cannot self-clear these.

- Public Claim Register row required for every external claim — Vimal as Contractor-equivalent reviewer + external counsel as second reviewer. Two-person check restored via counsel.

- Conservative phrasing default: when in doubt, drop the claim. Banned-phrase list (§5.1) applies absolutely. Approved-phrasing list (§5.2) is the only safe vocabulary.

- Weekly Vimal-only compliance audit (every Friday before GTM sync) — log live external claims + evidence binding + counsel-clearance status.

- Contractor hire continues as P0 priority — re-evaluate weekly at Friday sync until close.

- Vimal logs written risk acceptance in ArkOS Compliance-Review-Log every time the 30-Jun-not-met state extends another week.

### Why these mitigations matter

Vimal alone holding first-pass + final review collapses the two-person check designed by the Pilot Execution Plan v3 MASTER (§3). The mitigations above re-establish a two-person check by inserting external counsel as the second reviewer for the highest-risk claim categories, and by reducing claim volume + cadence so the founder bandwidth load stays survivable. Without these, the claim-risk window before the contractor is hired creates a regulator-visible exposure that the seed-raise narrative cannot afford.

# Contents

1.   Locked Position — Recap of the Source Documents

2.   GTM Pod — Roles, Bandwidth Protection, RACI

3.   Stack Architecture — ArkOS CRM + Apollo + Clay + Sales Navigator

4.   ArkOS CRM Operating Spec (Pipelines · Reports · Integrations)

5.   Compliance Discipline — Banned Phrases, Approved Phrasing, Public Claim Register

6.   The Four Live DP Targets — Operational ABM

7.   Apollo · Clay · Sales Navigator Operating Spec

8.   Founder Outbound Mechanics (Vimal — Final-Approval-Only Mode)

9.   Workstream Operating Detail (9 Workstreams from the Swimlane)

10.  Editorial + Content Engine Detail (Pillars · Cadence · SEO · AEO · GEO)

11.  Webinar Series Detail (#1 Annex 22 · #2 CSA SaaS · #3 Founding Partner)

12.  Founder PR + Voice Operating Detail

13.  Digital + Paid Operating Detail (LinkedIn ABM · Email · Retargeting)

14.  Measurement, Attribution, Weekly Friday Review

15.  Risk Register — Operational Layer (under the master risk list)

16.  90-Day Execution Calendar — Week-by-Week from W3 to W14

17.  Identified Gap Resolution — Inbound Leads + Product Coordination (NEW v1.1)

18.  Approvals & Sign-Off

A.   Appendix A — Workstream Owner-Action Reference (linked to GTM xlsx)

B.   Appendix B — Apollo Saved-Search Setup Spec

C.   Appendix C — Clay Enrichment Waterfall + Trigger-Score Spec

D.   Appendix D — Sales Navigator Saved-Search + Daily Ritual Spec

E.   Appendix E — ArkOS Sequence Templates (Cold · Warm · Inbound · DP)

F.   Appendix F — Content Brief + Compliance Review Form

G.   Appendix G — Pre-Publish Compliance Checklist (Reproduced from W4 Cards)

H.   Appendix H — Glossary

# 1. Locked Position — Recap of the Source Documents

This section restates what is already locked. Nothing here is open for the marketing team to renegotiate. Read it; do not re-debate it.

## 1.1 The Three GTM Phases (Locked · Mirrors Engineering Phases 1 / 2 / 3)

| Phase | Window | Posture | Marketing Objective (Locked) |
| --- | --- | --- | --- |
| Phase 1 · DEMO-READY | W1–W4 · 01 Jun → 26 Jun · 🔒 Demo lock 26 Jun | Brand · ICP activation · founder voice launch | verixa.ai live · ArkOS+Apollo+GA4+LinkedIn Tag wired · 14 ICPs loaded · founder outreach begins · Pillars #1–3 published · Vimal LinkedIn rhythm live · Webinar #1 scheduled W5 · Demo-ready PR splash 26 Jun |
| Phase 2 · BUILD-WHILE-SELL | W5–W13 · 29 Jun → 28 Aug | LOI sprint · founder media tour · webinars | W6 KILL-CHECK: 2-3 LOIs signed, 8 demos delivered · 5 podcasts · 3 op-eds · 4 analyst briefings · 3 webinars · W9 RC freeze: G-8 SIGNED partner #1 · India roundtable W13 · trade press · W10 CC freeze: marketing freezes new product claims |
| Phase 3 · VERIFIED → VALIDATE | W14+ · 01 Sep onwards · CONDITIONAL on W12/W14 engineering | Go-live splash · case study · investor process | 01 Sep GO-LIVE PR splash IFF (a) W12 engineering confirm + (b) W14 per-workflow verified. If incomplete: 'controlled-wave / founding partner verification program' messaging — NEVER 'delayed launch.' Partner-consent gate enforced. |

## 1.2 Hard Gates (Locked · Marketing Subordinate to Engineering)

| Date (2026) | Gate | Marketing Implication (Locked) |
| --- | --- | --- |
| 🔒 Fri 26 Jun | Demo-ready lock + GTM Phase 1 close | PR posture reduced to: "design-partner cohort open." (See Commercial Priority Override.) Compliance audit #1 passed. ZERO 'validated/compliant' claims. |
| Tue 30 Jun | G-JUN exit · June recap | Investor + DP pipeline note. Webinar #1 invitations sent (300+ reg target). |
| Mon 06 Jul | W6 KILL-CHECK (SINGLE GATE · binding) | 🟢 GREEN: 1 paid design-partner sprint SIGNED · OR 1 priced LOI/MSA in legal with scope agreed. 🟡 YELLOW: 2 qualified buyer meetings completed · named sponsor identified · written next step received. 🔴 RED: no named sponsor · no paid scope acceptance · OR buyer requires validated production claim. IF RED → narrow to 6 high-conviction accounts · pause broad PR / content expansion. MQL/SQL volume is NOT a W6 target — see §16 calendar note. |
| Fri 31 Jul | RC freeze + G-8 SIGNED | Founding-partner G-8 quality agreement signed. Reduced PR posture continues (consent contingent). Founding-partner application closes by W10. |
| Mon 03 Aug | Change-control freeze | No new product-claim creation. Only evidence-backed messaging from G-7 going forward. Compliance audit #3 passed. |
| Fri 28 Aug | G-7 + Enablement Kit | Partner-ready evidence pack distributed · case study #1 begins · India QA roundtable · Pillar #6 published. |
| Mon 31 Aug | Final compliance sign-off (T-1) | Vimal + Contractor + Manisha (UAT-readiness signal) audit all comms. ZERO self-claims. All partner refs explicit written approval. |
| 🎯 Tue 01 Sep | SEP-01 EVIDENCE MATURITY / VERIFIED GO-LIVE DECISION (internal name) | Buffered external narrative gate · NOT first commercial launch. External comms IFF W12 confirm + W14 per-workflow verified + Manisha UAT green. Otherwise: "controlled-wave / founding-partner verification program" messaging. Partner-consent gate per ArkOS. |
| 🛑 Mon 15 Sep | Hard backstop | Beyond this date, any unverified workflow flips to "controlled wave." Never "delayed launch." |

## 1.3 Primary KPI Targets (Locked · Hard Business)

| KPI | W6 Target | W9 Target | W14 Target | Owner |
| --- | --- | --- | --- | --- |
| Signed LOIs (paid design-partner intents) | ≥ 2 | 3–4 | 4–5 | Vimal |
| G-8 quality agreements SIGNED | 0 (draft) | 1 (founding) | 1–2 | Vimal + Legal |
| Partners ready for validation | 0 | 1 (Phase 1 active) | 1 LIVE | Vimal + Janani |
| Partner validation scoping calls completed | 0 | 1 | 3 | Vimal + Janani |
| Signed evidence-pack receipt acknowledgements | 0 | 0 | 1 | Janani |
| Partner-approved go-live statement on file (ArkOS) | 0 | 0 | 1 | Vimal + Legal |

## 1.4 Secondary (Vanity) KPI Targets (Locked · Amplification Only)

| KPI | W6 | W9 | W14 | Owner |
| --- | --- | --- | --- | --- |
| MQLs | 100 | 250 | 500 | Kavin |
| SQLs | 20 | 50 | 100 | Kavin |
| LinkedIn impressions (cumulative) | 75K | 150K | 300K | Droupathy |
| AI-search citations (AEO/GEO) | 1 | 2 | 5 | Manoj |
| Op-eds published | 1 | 2 | 4 | Droupathy |
| PR pickups at go-live | — | — | 10+ | Droupathy |

Vanity KPIs do not substitute for primary KPIs. Weekly Friday review prioritizes primary; secondary is amplification color.

## 1.5 Budget Envelope (Locked)

Total approved marketing-side spend through W14: approximately ₹36.7 lakh / US$37.8K. Allocation between line items is the Marketing Lead's call subject to Founder approval on items > ₹2 lakh. No new vendor contract is opened without Founder + Lead sign-off.

# 2. GTM Pod — Roles, Bandwidth Protection, RACI

Bandwidth protection rule: Vimal is FINAL APPROVAL ONLY. Vimal does NOT first-pass demos, first drafts of LinkedIn/op-eds, first-pass claim review, or low-stakes follow-ups. Droupathy first-drafts founder content. Janani runs first-pass demos. Contractor first-pass-reviews every external claim before Vimal sees it. Without this discipline the plan collapses.

## 2.1 Pod Roster

v1.1 update: The roster now includes 4 Sense7ai Development Partner team members named for operating clarity (Raja, Prakash, Manisha, Viji). External marketing positioning of Sense7ai remains unchanged: Development Partner only · not embedded · not white-labeled · not a re-seller. The Verixa product is attributed solely to Verixa / Navira Quality Systems Pvt Ltd in customer-facing materials.

| Person | Role · Mode | Owns | Does Not Own |
| --- | --- | --- | --- |
| Vimal Veereshwarayya, PhD., RAC | Founder / CEO (Verixa) — Final approval only (reduced-load) | Final founder voice (review, not draft) · high-stakes calls only · G-8 negotiation · final compliance sign-off · final A on every workstream · product direction + market positioning + scope decisions | First-pass demos · first drafts of LinkedIn / op-eds · first-pass claim review · low-stakes follow-ups |
| Janani Rangesh | Product Manager (Product Ownership) | Requirements + workflow clarity · acceptance-criteria coordination · product-level decisions · first-pass demos (Vimal joins from demo 4+ or P0/strategic only) · product proof points · enablement kit · DP feedback loop · pipeline ops · resolves ambiguity on requirements, workflow behavior, acceptance criteria, product priorities within agreed direction · aligns with Vimal where decision affects overall direction / positioning / scope | Marketing first-draft writing · website/SEO/digital ops · architecture / infrastructure / delivery |
| Droupathy | Marketing — first drafts of founder content + inbound-lead interim owner | First drafts of all Vimal LinkedIn posts, long-form, op-eds, PR statements (Vimal reviews + approves voice — does not write) · editorial · PR · webinars · founder media bookings · case studies · brand-voice enforcement · INTERIM owner of inbound leads + product coordination (Janani co-pilot · see §17) | Demo delivery · technical product claims · paid media operations |
| Kavin | Digital Marketing | ArkOS CRM ops · Apollo sequences · paid · email nurture · attribution · LinkedIn ABM · marketing automation · works with Prakash on ArkOS automation for Verixa | Editorial copy · technical SEO / schema · founder voice content |
| Manoj | Website · Front-end · SEO/AEO/GEO | verixa.ai launch · schema · E-E-A-T · AI search visibility · LP infra · technical SEO · resources hub | CRM / paid / outbound / content writing |
| Raja (Sense7ai DP team) | Technical Ownership | Architecture · infrastructure readiness · engineering execution · delivery · dependencies · timelines · aligns with Vimal on major architectural decisions · final decision on implementation approach, engineering sequencing, infra readiness, technical dependencies, release feasibility within agreed architecture · escalates unresolved trade-offs through Janani or Viji | Day-to-day marketing operations · brand voice |
| Prakash (Sense7ai DP team) | PM Coordination — Product↔Engineering liaison | URS/workflow alignment + readiness through defined processes · supports ArkOS automation for Verixa with Kavin + Droupathy · works with Janani on product clarity and with Raja on processes · resolves process / coordination / sequencing / documentation / readiness gaps within agreed product + technical direction · escalates unresolved Product–Engineering misalignment to Viji | Engineering deliverables or timelines (Raja's call) · product decisions (Janani's call) |
| Manisha (Sense7ai DP team) | UAT Readiness + Code Quality | Tracks deliverable readiness for UAT · code quality + readiness for testing/QA · gates Phase-2/Phase-3 marketing claims (no go-live messaging without UAT green) · works with Janani on UAT readiness and with Raja on quality of build going into test | Marketing copy · direct buyer engagement |
| Viji Janakiraman (Sense7ai DP team) | Operating + Leadership Support | Cross-functional alignment · delivery-risk review · conflict resolution · escalation support · resolves unresolved cross-functional ownership, operating-model, process, accountability conflicts | Product-direction decisions (Vimal + Janani) · technical decisions (Raja) |
| External CSV/CSA + RA Contractor (TBD) | Compliance — first-pass claim review · INTERIM owner: Vimal (until contractor identified) | First-pass claim review on every external claim · language audit · evidence-binding review · MIRA/AI claim review · G-7 + G-8 framing · trade-press claim review. NOTE: Until contractor is hired, Vimal holds BOTH first-pass + final-approval — this collapses the two-person check designed by the Pilot Execution Plan v3 MASTER (§3). Hire is URGENT and slipped past W2 target. Not Janani. | Drafting marketing copy · running ABM |

## 2.2 RACI on the 9 Workstreams (Locked from GTM Launch Flow · v1.1 updated)

v1.1 updates: rows for Digital/Paid · DP Pipeline · Sales Enablement · Website now include Sense7ai DP team consult roles where their decisions gate marketing execution.

| Workstream | R (Responsible) | A (Accountable) | C (Consulted) | I (Informed) |
| --- | --- | --- | --- | --- |
| Positioning | Droupathy | Vimal | Contractor · Janani | All |
| Founder voice / PR | Droupathy (drafts) | Vimal (approves) | Contractor | All |
| Content / Editorial | Droupathy | Droupathy | Janani · Manoj · Contractor | Vimal · Kavin |
| Website / SEO / AEO / GEO | Manoj | Droupathy | Janani · Contractor · Raja (architecture/perf decisions on verixa.ai infra) | Vimal · Kavin · Prakash |
| Digital / Paid (ArkOS) | Kavin | Droupathy | Vimal · Contractor · Prakash (ArkOS automation liaison) · Raja (architecture) | Manoj · Janani |
| DP Pipeline / ABM | Kavin (ops) · Vimal (founder) | Vimal | Janani · Prakash (process) · Contractor · Legal | Droupathy · Manoj · Raja |
| Events / Webinars | Droupathy | Droupathy | Vimal · Janani · Contractor | Kavin · Manoj · Prakash |
| Sales Enablement | Janani | Vimal | Droupathy · Contractor · Manisha (UAT readiness for demo lab) | Kavin · Raja |
| Compliance Review | Vimal (interim — until Contractor hired) | Vimal | Janani · Legal | All |

Escalation path: Product-Engineering misalignment or gaps that Prakash cannot resolve at the coordination layer go to Viji for resolution. Product-direction decisions remain with Vimal + Janani. Technical decisions remain with Raja.

Compliance interim assignment: until the External CSV/CSA + RA Contractor is identified and onboarded, Vimal holds BOTH first-pass claim review and final approval. This collapses the two-person check designed by the Pilot Execution Plan v3 MASTER (§3). It is a temporary bridge only. NOT Janani. The Contractor hire was due at W2 (Jun 8-12) and has slipped — it is now URGENT and should close before W6 KILL-CHECK. See §15 MR-16.

## 2.3 Working Cadence (Locked)

| Cadence | When (IST) | Attendees | Output |
| --- | --- | --- | --- |
| Daily founder pulse (15 min) | Mon–Fri 09:15 | Vimal + Droupathy | 1 priority for the day · approval queue |
| Marketing pod stand-up (20 min) | Mon · Wed · Fri 10:00 | Droupathy + Kavin + Manoj (Janani Wed) | Sprint progress · blockers · approval queue clearance |
| Weekly GTM pod sync (45 min) | Fri 11:00 | All pod + Vimal + Janani + Contractor | Primary KPI dashboard · Public Claim Register status · next-week plan |
| Bi-weekly Founder × Lead (60 min) | Tue 16:00 (alt weeks) | Vimal + Droupathy | Strategic adjustments · approvals batch · DP-target health |
| Monthly Marketing Review (90 min) | First Mon of month 16:00 | Pod + Vimal + Janani + Contractor | Monthly report · pivots |
| Quarterly Plan + Budget Review | Last Fri of quarter | Pod + Vimal | Updated plan · revised budget |
| Cross-functional escalation (NEW v1.1) | On-demand · 24h SLA | Prakash → Raja (technical) · Janani (product) · Viji (final) | Resolution captured in ArkOS Cross-Functional-Escalation-Log |
| Product-Eng-Marketing sync (NEW v1.1) | Weekly Tue 15:00 IST | Janani + Prakash + Raja + Kavin | ArkOS automation status · marketing-blocking eng items · UAT readiness signal from Manisha |

# 3. Stack Architecture — ArkOS CRM + Sales Navigator (Simplified)

Stack simplified after founder review (18 Jun 2026). Apollo deferred conditional (revisit W5+ only if cold email becomes a real channel). Clay dropped (scale tool · revisit W14+ when manual enrichment fatigue is real). ArkOS CRM is the single source of truth. Sales Navigator is the primary outbound + intent surface. No partner reference is used externally without written approval stored in ArkOS.

## 3.1 Logical Flow

Sales Navigator (intent + relationship + saved searches) → ArkOS CRM (single source of truth + sequences + activities + e-signature + reporting) → Calendly (meetings booked) → ArkOS opportunity progression → Loom/Vidyard (asynchronous proof clips) → verixa.ai (conversion + AEO/GEO surface) → GA4 / Search Console (organic feedback loop). For the 4 LIVE DP targets, founder 1-to-1 outbound is hand-crafted in Vimal's outbox; no bulk sequencer required.

Deferred / dropped: Apollo (deferred to W5+ conditional · activate only if Sales Nav InMail volume is insufficient and cold email becomes the actual channel). Clay (dropped from W3-W14 · revisit W14+ when prospect volume exceeds 25/week).

## 3.2 Tool Roles at a Glance

| Tool | Role | Owner | Source-of-Truth? |
| --- | --- | --- | --- |
| ArkOS CRM (in-house) | Pipeline · sequences · activities · e-signature · attribution · reporting | Kavin (ops) · Droupathy (A) | YES — single source of truth |
| LinkedIn Sales Navigator | Intent + relationship intelligence · saved searches with alerts · InMail outreach | Vimal + Droupathy | No — feeds ArkOS |
| Calendly | Meeting booking · auto-linked to ArkOS opportunity | Vimal · Droupathy · Janani | No — feeds ArkOS |
| Loom · Vidyard | Asynchronous proof clips (≤ 90s) | Vimal · Janani | No — links stored in ArkOS |
| verixa.ai | Conversion surface · AEO/GEO surface | Manoj | No — leads pushed to ArkOS via form-fill webhook |
| GA4 + Google Search Console | Organic + paid analytics · search visibility | Manoj | No — reporting only |
| Ahrefs · Similarweb | SEO + AEO + GEO competitive intelligence | Manoj | No — reporting only |
| LinkedIn (Vimal · Verixa Page) | Founder voice + brand surface | Vimal (approves) · Droupathy (drafts) · Kavin (Verixa Page) | No — engagement logged to ArkOS |
| n8n (preferred) or Zapier | Integration glue · lower data exposure (n8n self-hosted) | Kavin (ops) · Manoj (technical) | No — integration plane |
| Vimal's email outbox (verixa.ai domain) | Direct founder email to 4 LIVE DP targets · hand-crafted | Vimal | No — sent items logged to ArkOS by Kavin |
| DEFERRED — Apollo | B2B contact universe · cold-email warming · sequenced cadence | Conditional W5+ | Not in W3-W14 plan |
| DROPPED — Clay | Waterfall enrichment · trigger scoring · signal compilation | Revisit W14+ | Not in W3-W14 plan |

# 4. ArkOS CRM Operating Spec

## 4.1 Required Objects (Must Exist by Mon 22 Jun 2026 · W4 Start)

| Object | Required Fields (minimum) | Notes |
| --- | --- | --- |
| Account | Legal name · trading name · domain · HQ city · HQ country · ICP tier · sub-segment (CDMO / Mfr / Spinoff / Biotech / etc.) · regulatory-authority footprint · public-signal flags | One row per organization. Apollo + Clay sourced; deduped by domain. |
| Contact | Full name · title (current) · function · seniority · email (verified) · LinkedIn URL · phone (optional) · DPDP / GDPR opt-in status · last-touch date | One per person. Deduped by email. |
| Opportunity | Account · primary contact · stage · expected ARR band (DP-A/B/C tier) · expected close date · LOI status · G-8 status · MSA clauses negotiated · validation scope · pilot start date | Per-pilot opportunity. Linked to one account, one or more contacts. |
| Sequence | Sequence name · channel · cadence steps · audience filter · status · sent count · open count · reply count · meeting count · ICP tier | Cold · Warm · Inbound · DP — see Appendix E. |
| Activity | Activity type (email / LinkedIn / call / meeting / loom-clip / event-handshake) · subject · contact · account · opportunity · channel UTM · outcome · timestamp · user | Every touch logged. Source of truth for attribution. |
| Note | Free text · linked to contact / account / opportunity · author · timestamp | Discovery-call notes captured here. |
| Attachment | File · link · linked record · classification (Public · Internal · Restricted · Partner-Approved) | Loom links · decks · briefs · LOI drafts. |
| Public-Claim-Register Entry | Claim text · claim type · evidence binding · Contractor approval status · Vimal approval status · live in asset (URL) · live-from date | Mirrors Sheet 14 of the Verixa GTM Launch Plan xlsx. Auditable. |
| Signal | Signal type · source · score weight · linked contact / account · date | Trigger-score composite per Clay waterfall (Appendix C). |
| DP-Agreement | DP-A/B/C tier · LOI status · G-8 status · 7 MSA clauses status · pricing band · sprint scope · e-signature record | Quality-agreement compliance. |

## 4.2 Required Pipelines

- Outbound — Founder-led cold (Vimal motion · Caplin / Synthix / Cohance / SMS · 4 LIVE).

- Inbound — verixa.ai form fills + LinkedIn DM replies.

- Design Partner — qualified opportunities heading to LOI / MSA / G-8.

- Customer Expansion — post-LOI conversion to ARR + scope expansion.

- Reference Loop — post-go-live · case study + testimonial + partner-approved external use.

- Cold Archive — non-engaged > 24 months · DPDP / GDPR right-to-erasure cohort.

## 4.3 Required Reports (Visible by W3 · Friday 19 Jun)

| Report | Cadence | Owner | Pass Criteria |
| --- | --- | --- | --- |
| Primary KPI dashboard | Weekly Friday | Vimal | Mirrors the 6 primary KPIs in §1.3 |
| Outbound activity report (per founder hour) | Daily | Vimal · Droupathy | Volume guardrails respected (§8.4) |
| Pipeline by stage | Weekly | Droupathy | Stage hygiene · stuck-deal flagging |
| Reply-rate by sequence | Weekly | Kavin | Trend lines · sequence pause triggers |
| Public Claim Register status | Weekly | Contractor (R) · Vimal (A) | Every live external claim has Contractor sign-off + Vimal sign-off + evidence binding |
| Source-attribution cohort (first-touch + multi-touch) | Monthly | Kavin | Channel diagnostics · attribution disagreement > 30% flagged |
| Webinar funnel | Per-event + cumulative | Droupathy | Reg → attend → demo-book conversion |
| DP target health | Weekly | Vimal · Janani | Status of Caplin / Synthix / Cohance / SMS · last touch · next step |
| Partner-consent register | Continuous | Vimal · Legal | Every partner reference (logo / name / quote / screenshot) has signed consent on file before any external use |

## 4.4 Required Integrations (Build Order)

- Apollo → ArkOS contact + account sync (webhook · 24h batch).

- Clay → ArkOS enrichment payload sync + trigger-score field update (webhook · 24h).

- Sales Navigator → Clay (manual export + paste into Clay tables · weekly until automated).

- Calendly → ArkOS opportunity activity sync (native or n8n).

- verixa.ai forms → ArkOS inbound lead (webhook · live).

- LinkedIn (Vimal personal account) → ArkOS engagement log (manual log + LinkedIn export for Verixa Page).

- GA4 + Search Console → ArkOS session linkage (UTM mapping per §13.4 standard).

- LinkedIn Insight Tag → website (paid ABM attribution).

Open dependency (v1.1 escalation path updated): If any required object / pipeline / report in §4.1 → §4.3 is missing on Mon 22 Jun 2026 (W4 start), Prakash + Janani jointly escalate to Raja. Raja decides on implementation approach + sequencing within the agreed architecture. If unresolved within 48 hours, Viji is final escalation. Marketing external outbound does not begin until the escalation is resolved or a documented contingency (§15 MR-01) is approved by Vimal. ArkOS automation thread (Prakash–Kavin–Droupathy) operates inside this escalation path.

# 5. Compliance Discipline — Banned, Approved, Public Claim Register

Verifies-not-validates. This rule is absolute. "Verixa is in design-partner phase and is not represented as a validated 21 CFR Part 11 / EU Annex 11 system." — locked clause 1 of the 7 MSA clauses. Every Marketing Pod member learns these phrases verbatim.

## 5.1 Banned Phrases (Locked · From W4 Outreach Cards Jun 10)

| Banned Phrase | Why |
| --- | --- |
| validated | Verixa does not claim validation. Customer validates intended use. |
| compliant | No GxP-compliance claim before partner validation evidence + regulator-visible audit. |
| audit-ready | Reads as a compliance claim. |
| inspection-ready | Reads as a compliance claim. |
| regulator-safe | Implies regulator review of Verixa as a product. |
| architecturally impossible | Verixa cannot make absolute claims about the limits of AI behavior. |
| defensible under inspection | Outside Verixa's scope to claim on a customer's behalf. |
| GxP-compliant out of the box | No GxP claim before validation by the customer. |
| "we saw your 483 / your deficiencies / your citation" | Never lead with the prospect's enforcement history. |

## 5.2 Approved Phrasing (Locked · From W4 Outreach Cards Jun 10 + Founder Review 18 Jun)

- "designed to support…"

- "internally verified under our SDLC"

- "the customer validates intended use"

- "co-design evidence sprint"

- "designed to support emerging expectations such as draft EU GMP Annex 22 — not a compliance claim"

- "structured evidence package" (replacement for "audit-ready")

- "inspection-supporting evidence" (replacement for "inspection-ready")

- "reviewable evidence trail" (replacement for either)

- "CSA-aligned risk-based assurance principles where applicable" (replacement for any direct FDA CSA claim)

## 5.3 Standard Disclosure (Locked · Must Appear on Every Outreach Card and Pilot Asset)

"Co-design evidence sprint. Phase 1 produces design-partner evidence artifacts, not a validated GxP production deployment. Customer validation of intended use is not included."

## 5.4 Public Claim Register — Operating Workflow

- Drafter (Droupathy for content · Vimal for founder-voice originals · Manoj for technical web) drafts the asset.

- Drafter opens a Public Claim Register row (Sheet 14 of the GTM Launch Plan xlsx) for every distinct external claim made in the asset.

- Contractor first-pass reviews each claim: ban-word check · evidence-binding check · MIRA/AI claim check · Annex 22 / EU AI Act framing check · G-7 evidence linkage check.

- Contractor sets each row's status to ✔ APPROVED FOR ASSET / ✖ REJECTED / ⌛ CONDITIONAL (with conditions written in the row).

- Vimal sees only Contractor-approved assets. Vimal applies founder-voice review and final A.

- Approved asset ships. Live URL + live-from date logged into the same Register row.

- Marketing Lead runs weekly Register status review (Friday GTM pod sync). Live external claims with stale evidence binding are pulled within 48 hours.

If you cannot produce a Public Claim Register row with Contractor sign-off, the asset does not ship. Founder approval cannot substitute for first-pass claim review by the Contractor.

## 5.5 Phase 1 Scope Distinction — Product Module Set vs Commercial Sprint Scope

Two different things share the "Phase 1" label. They are NOT the same. Marketing copy must use the precise term every time. Founder review 18 Jun made this distinction binding.

- Product Phase 1 module set (broader product scope). Q&A · Deviation Assessment · Risk Assessment · RCA · CAPA · Audit Readiness module · Document Control · others per Verixa product manual. This is the PRODUCT scope shipping into the demo-lock + verified build.

- Commercial design-partner sprint scope (narrow commercial offering). Deviation → RCA → CAPA → effectiveness check → closure → evidence trail. This is what we SELL into the paid sprint right now. The buyer signs SoW against this scope.

Marketing copy uses "Commercial design-partner sprint scope" when describing what the buyer gets. "Product Phase 1 module set" is internal-only language about product breadth. Mixing the two confuses the buyer and overclaims commercial scope. **OOS is OUT of Commercial Sprint Scope** (belongs to Product module set only, future extension). If a buyer asks about OOS: "Out of Commercial Sprint Scope — a future scoped extension at the product-module level." Never offer an "OOS sprint."

## 5.6 Compliance Audit Schedule (Locked · From GTM Launch Flow)

| Audit | Window | Trigger | Owner |
| --- | --- | --- | --- |
| #1 | W2 → W3 | Pre-Phase-1 launch | Contractor + Vimal |
| #2 | W5 → W6 | Pre-KILL-CHECK | Contractor + Vimal |
| #3 | W8 → W9 | Pre-RC freeze | Contractor + Vimal |
| #4 | W12 → W13 | Pre-GO-LIVE | Contractor + Vimal |
| Final | W14 | T-1 day to go-live (Mon 31 Aug) | Contractor + Vimal |

# 6. The Four Live DP Targets — Operational ABM

This is the W4 list of the moment (Jun 10). 4 READY + 1 BLOCKED. If the list changes during W3, the Marketing Lead updates this section within 24h and re-notifies the pod. The DP target list is owned by Vimal, not by marketing.

## 6.1 Live Target Card Summary

| # | Account | Status | Owner Target | Access | Cycle | Hook |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Caplin Steriles Ltd (Gummidipoondi TN) | READY · Priority #1 · confirmed additive fit | MD / Head of Quality | Chennai · founder-direct | short | Public AI-governance commentary + filed patent · injectable-line expansion |
| 2 | Solara Active Pharma / Synthix (Hyderabad) | READY · greenfield hypothesis | Head of Quality / MD (new entity) | Hyderabad | short | Post-demerger clean-slate moment · CRAMS sponsor audits |
| 3 | Cohance Lifesciences (Hyderabad) | READY · phase-to-commercial hypothesis | VP Quality / CEO | Hyderabad | medium | Phase-3 → commercial scale-up · CDMO QA cycle compression |
| 4 | SMS Pharmaceuticals (Hyderabad / Vizag) | READY · reachable · additive hook | QA Head / ED | Hyderabad · Vizag | short–medium | Multi-authority, multi-site cadence load · evidence workflow |
| 5 | Windlas Biotech (Dehradun) | 🚫 BLOCKED until 3 gates clear | — | — | — | Predecessor entity (Windlas Healthcare) carries 2020 FDA warning letter + Import Alert 66-40 — do not contact |

## 6.2 Windlas Unblock Gate (All Three Must Pass · Vimal Sign-Off)

- Verify current FDA import-alert status (66-40) for the listed entity — confirmed cleared.

- Confirm the warning letter is formally closed and not attached to the current entity.

- Confirm no open enforcement on any of the 5 WHO-GMP sites.

Owner of unblock work: Vimal + Contractor + Legal. Marketing pod does NOT initiate Windlas outreach until written unblock recorded in ArkOS DP-Agreement object.

## 6.3 Per-Target ABM Mechanics (What Marketing Does for Each Live Target)

| # | Account | Marketing Pod's Job |
| --- | --- | --- |
| 1 | Caplin Steriles | Kavin: ABM audience in LinkedIn (Caplin Steriles + Caplin Point + MD Srinivasa Sridhar) · ArkOS DP-Agreement object created · Drop pages on verixa.ai/founding-partner with anchor copy · Manoj: tag + retarget pixels live. Droupathy: prepare Vimal's outbound first-touch DRAFT for Vimal review (founder voice rule). Janani: prep first-pass demo if call books. Contractor: scrub every claim in the outbound for ban-words + evidence binding. |
| 2 | Solara / Synthix | Kavin: ABM audience for Solara / Synthix (new entity). ArkOS DP-Agreement. Droupathy: Vimal outbound DRAFT for greenfield hypothesis hook. Janani: first-pass demo if call books. Manoj: pixel + retarget. Contractor: scrub claims. Discovery posture only — Janani prepares to confirm operationality of Synthix on first call. |
| 3 | Cohance Lifesciences | Kavin: ABM audience for Cohance. ArkOS DP-Agreement. Droupathy: Vimal outbound DRAFT for phase-3-to-commercial hook. Janani: prep first-pass demo. Manoj: pixel. Contractor: scrub. Discovery posture only — verify pain hypothesis on first call. |
| 4 | SMS Pharmaceuticals | Kavin: ABM audience for SMS. ArkOS DP-Agreement. Droupathy: Vimal outbound DRAFT for multi-authority/multi-site cadence hook — NO mention of 483s. Janani: demo prep. Manoj: pixel. Contractor: scrub — special attention to the no-citation-led-opener rule. |
| 5 | Windlas (BLOCKED) | Marketing pod takes ZERO outbound, ZERO ABM, ZERO website personalization, ZERO retargeting on Windlas until the 3-gate unblock is recorded in ArkOS. If the unblock comes, marketing receives a written brief from Vimal + Contractor and only then activates. |

## 6.4 Close-Call Readiness Checklist (Mandatory Before Any Founder Close Call)

Founder review pass addition. Before any founder close call (DP target conversation aimed at moving the opportunity toward LOI / MSA / paid sprint signature), all 11 items below must be GREEN in ArkOS. Kavin owns the ArkOS "Close-Readiness" field set. Droupathy + Janani co-sign before Vimal is scheduled. No green = no close call.

| # | Check | Owner | Pass Criteria |
| --- | --- | --- | --- |
| 1 | Target account approved | Vimal | Account in 4 LIVE list (Caplin / Solara-Synthix / Cohance / SMS) or written Vimal exception |
| 2 | Sponsor named | Janani | Named buyer with title + LinkedIn URL + relationship-to-decision documented in ArkOS |
| 3 | Pain confirmed | Janani + Droupathy | First-call discovery (per §8.3) captured pain in own words · logged in ArkOS |
| 4 | Decision path known | Vimal + Janani | Decision-maker · approver · influencer · blocker map drawn in ArkOS |
| 5 | Paid sprint price approved | Vimal | DP-A / DP-B / DP-C tier locked + written Vimal approval on pricing exception (if any) |
| 6 | SoW ready | Janani + Legal | Statement of Work draft attached to ArkOS DP-Agreement object |
| 7 | Validation boundary clause included | Contractor + Legal | "Verixa verifies · customer validates intended use" clause present + verifies-not-validates audit pass |
| 8 | Data handling note ready | Manisha + Contractor + Raja (architecture proof) + Security/Privacy reviewer | Data residency claim ('India → AWS Mumbai · US → AWS US-East') requires written architecture proof from Raja AND security/data-handling review before being placed in any buyer document. Until proven: do not state the residency claim in writing — use "data residency model in design; specifics shared under NDA pending architecture confirmation." DPDP / GDPR posture confirmed by Contractor or external counsel. |
| 9 | No partner-publicity promise | Vimal + Legal | No commitments to name / quote / feature partner externally without separate written consent |
| 10 | Demo workflow ready | Janani | Phase 1 demo workflow (deviation → RCA → CAPA · evidence trail) tested in segregated eval env in last 5 days |
| 11 | Janani delivery owner confirmed | Janani | Janani has bandwidth to deliver the sprint if signed; if not, Vimal escalates to Viji for ops-resourcing decision before the call |

## 6.5 Disqualification Criteria (Locked — Drop on First Call)

From the LOCKED DP Strategy. If any criterion is observed, the account drops out of pipeline on first call. Marketing pod marks the ArkOS Opportunity "Disqualified — Locked Criterion" and adds the criterion code to the note.

- Active Veeva Vault / MasterControl / TrackWise / SAP QM contract for target site.

- Active FDA Warning Letter, Import Alert, or Consent Decree on target site.

- Cannot name a QA Head or sponsor reachable within 2 LinkedIn degrees.

- Requires Verixa to claim "21 CFR Part 11 validated" today.

- Demands procurement to run; cannot complete in < 60 days at US$25–75K.

- Pure domestic with no WHO-GMP / USFDA / EU-GMP export ambition.

- Hostile data environment (destroyed records, criminal referral).

# 7. LinkedIn Sales Navigator + ArkOS Operating Spec (Simplified)

Founder-review pass simplification. The 4 LIVE DP targets are named accounts — they don't need an Apollo database lookup. The broader 14 ICPs over 14 weeks are a hand-managed list, not a Clay-scale problem. Sales Navigator + ArkOS + Vimal's outbox carry the load. Apollo / Clay revisited only if the simpler stack hits a real bottleneck.

## 7.1 LinkedIn Sales Navigator — Primary Outbound Surface

- Seats. Sales Navigator Core for Vimal + Droupathy. Reassess at W14.

- Use cases. Saved-search alerts on India pharma QA leaders + CDMO leadership + recent job changes · relationship-mapping for warm intros · InMail to the 4 LIVE DP target sponsors when warm tie not yet established · daily intent-signal scan.

- Saved searches. 8 saved searches with daily alerts — full spec in Appendix D.

- Daily ritual (Droupathy operates · Vimal acts on approved list). 09:00–09:30 IST: news + signal scan; surface up to 10 high-signal contacts. Droupathy promotes to ArkOS "Hot Today" list. Vimal acts in slot 2 of his calendar (§8.1) on the curated short-list. Per W4 Outreach Cards opener rule: forward-looking signals only, never enforcement history.

- Engagement rule. Three meaningful interactions (comment / share / signal-engage) before a connection request to any new prospect.

- Volume guardrails. Vimal ≤ 30 connection requests / day across both LinkedIn accounts · ≤ 40 InMail per week. Below LinkedIn's published soft limits.

## 7.2 Vimal's Outbox (Email) — Founder Direct to 4 LIVE DP Targets

- Channel. vimalv@verixa.ai. Hand-crafted founder emails to the 4 LIVE DP target sponsors only (Caplin · Solara-Synthix · Cohance · SMS). No bulk sequencer required at this volume.

- Logging. Kavin daily logs sent items + replies into ArkOS Activity object. Manual until W14+ if needed.

- Compliance. DPDP 2023 + GDPR + CAN-SPAM. Universal unsubscribe in every email. Registered physical address (Navira Quality Systems Pvt Ltd India · Navira Quality Systems Inc US) in mail footer.

- Volume cap. ≤ 5 founder-direct first-touches per day. Quality over volume.

## 7.3 Apollo — DEFERRED (Conditional Revisit at W5+)

Apollo is NOT in the W3-W14 stack. Revisit only if BOTH of these are true at the W6 KILL-CHECK: (a) Sales Nav InMail volume is exhausted for the broader 14 ICPs, AND (b) cold email is identified as the actual primary channel for the unreached portion. Until then, Apollo is dropped — no seats, no spend.

## 7.4 Clay — DROPPED (Revisit at W14+ Scale)

Clay is NOT in the W3-W14 stack. The 4 LIVE DP targets are hand-enriched by Janani (USFDA EIR pull · MCA filings · LinkedIn signal review) in an afternoon. The broader 14 ICPs are a similar manual exercise. Clay becomes relevant only at >25 prospects/week when manual enrichment fatigue is real — revisit at W14+ alongside the SDR/BDR hire decision (§17 Option C).

## 7.5 Email Infrastructure — Simplified (No Decision Pending)

With Apollo dropped, the original "Apollo native vs Smartlead vs Instantly" decision is moot. Vimal's outbox (verixa.ai) is the only email send surface. Domain warming is via normal founder-led human send patterns. No bulk warm-up vendor needed.

# 8. Founder Outbound Mechanics (Vimal — Final-Approval-Only Mode)

Vimal does NOT first-draft. Droupathy first-drafts every founder LinkedIn post, op-ed, PR statement, and outbound email. Contractor first-pass-claim-reviews. Vimal applies founder-voice review + final A. This is the non-negotiable bandwidth protection rule.

## 8.1 Daily Cadence (Vimal — Mon–Fri · True Final-Approval-Only Mode)

Founder review pass discipline: Vimal's daily window is ≤ 3 hours total of marketing-pod-facing time. Everything else (Sales Nav scanning, LinkedIn engagement, drafts, Loom production, pipeline hygiene) is owned by Droupathy + Kavin + Janani. If a slot below feels like execution rather than approval, Droupathy moves it off Vimal's calendar by end of week.

| Slot | Window IST | Activity | Output to ArkOS |
| --- | --- | --- | --- |
| 1 | 08:45–09:00 | Approval queue clearance only (Contractor-cleared assets · Droupathy drafts · Janani demo brief) | Batch approval timestamps |
| 2 | 11:00–12:00 | High-stakes founder calls only (DP target sponsor calls · investor warm intros) | Call notes + next steps |
| 3 | 14:30–15:30 | High-stakes discovery / DP demo participation (joins from demo 4+ or P0/strategic only) | Call notes + Janani follow-up brief |
| 4 | 16:30–16:45 | End-of-day approval batch for tomorrow's send (signs off marked drafts) | Approved + flagged drafts |

Owned by others — NOT on Vimal's calendar:

- Sales Navigator daily scan + "Hot Today" promotion → Droupathy operates · Kavin syncs to ArkOS.

- LinkedIn engagement on ICP posts → Droupathy drafts comments for Vimal review (batched at slot 4); Vimal posts only after approval.

- Outbound writing → Droupathy first-drafts → Contractor scrubs → Vimal slot-4 approval → Kavin sends.

- Loom clips → Droupathy or Janani records and edits; Vimal records only the founder-voice intro on flagged-for-founder clips.

- Inbound replies (excluding DP-target high-trust signals) → Droupathy as interim owner (§17 Option C).

- Pipeline hygiene + ArkOS field updates → Kavin daily.

## 8.2 First-Touch Hook Templates (Locked — W4 Outreach Cards)

- Patent-pattern hook (Caplin): Reference Caplin's Q3 FY26 earnings commentary on AI governance architecture for pharma SOPs + patent filing.

- Greenfield hook (Solara / Synthix): Reference the post-demerger clean-slate quality system architecture opportunity.

- Phase-3-to-commercial hook (Cohance): Reference Phase-3 → commercial QMS step-up + multi-customer audit evidence.

- Multi-authority load hook (SMS): Reference the multi-authority, multi-site documentation cadence load. No mention of 483 history.

- AI governance hook (any persona A or E target): Reference the April 2026 first AI-quality FDA Warning Letter + Annex 22 emerging expectations — never claim Verixa is compliant.

- Refusal-as-product hook (AI-sophisticated buyers only): "The novel thing about our platform is that the AI refuses to act when governance evidence is missing."

## 8.3 Per-Target First-Call Discovery (Verbatim · From W4 Outreach Cards)

Each card carries 5 discovery questions that Vimal asks on the first call. These are tools to qualify the opportunity, NOT to pitch. The W4 Outreach Cards file is the source of truth — Droupathy does not edit them without Vimal sign-off.

- Caplin discovery. AI-governance approach filed on (current system) · injectable-line scale + deviation/CAPA evidence (pain) · 2026 priority for AI governance (urgency) · pilot decision owner (owner) · what makes a 90-day co-design sprint worth it (pilot path).

- Solara / Synthix discovery. Building fresh QMS or adapting legacy (premise check) · CRAMS client quality-agreement documentation (pain) · FY26-27 digital QMS budget (urgency + owner) · decision owner in new entity (owner) · clean-slate co-design sprint exploration (pilot path).

- Cohance discovery. Phase-3 → commercial documentation step-up (pain) · current quality-event tracking system (current system) · QA evidence compile time per client audit (pain) · decision owner (owner) · 2026 priority (urgency + pilot path).

- SMS discovery. Unified system or authority-specific processes (current system) · biggest manual burden (pain) · 2026 QMS digitisation evaluation (urgency) · evaluation owner (owner) · deviation-to-CAPA co-design sprint (pilot path).

## 8.4 Volume Guardrails (Locked)

- Vimal sends ≤ 60 cold first-touch emails per day. ArkOS rejects volume above.

- Vimal sends ≤ 30 LinkedIn connection requests per day across both accounts.

- Domain warming respects ≥ 21-day warm-up window before any cold push.

- No purchase of cold-email lists. No scraped lists outside Apollo / Clay / Sales Navigator.

- Universal unsubscribe link present in all marketing-class emails.

- Sales Navigator daily messaging stays below LinkedIn's published soft limits.

- Demo not offered until account confirms pain + named owner + urgency + pilot path.

# 9. Workstream Operating Detail (9 Workstreams from the Swimlane)

These follow the lanes defined in the GTM Launch Flow swimlane. The bars and weeks below are taken from that source (the canonical view is the assignee calendar HTML). This section adds operational hygiene for each lane.

## 9.1 Positioning (Vimal · Droupathy)

- W1–W2 · Lock V1 messaging — verifies-not-validates framework, six-element AI evidence trail, anchor differentiators. Source-bind every claim into the Public Claim Register.

- W2–W3 · Compliance guardrail publication — Contractor + Vimal sign-off on the Phase-1 boundary statement that appears on every external surface.

- W3–W5 · Investor + DP narrative — same anchor messages, two audience cuts.

- W6–W9 · Founding-partner messaging — once 1+ LOI signed, the "founding partner" narrative becomes available (only with partner-consent gate).

- W10–W13 · Verified-not-validated rollout — pre-launch posture · Phase-3 wording locked.

- W14 · GO-LIVE narrative — conditional on W12 confirm + W14 per-workflow verified.

## 9.2 Founder Voice / PR (Vimal · Droupathy)

- W1–W4 · Vimal LinkedIn 3×/wk (Droupathy first-draft · Vimal review).

- W3–W7 · Podcast tour booking · 3–5 confirmed appearances (Droupathy books · Vimal records).

- W5–W9 · Op-ed: "Verify vs Validate" (Droupathy first-draft · Contractor scrub · Vimal review).

- W7–W12 · Analyst briefings — 4 confirmed (Droupathy books · Vimal delivers · Janani co-presents on product specifics).

- W9–W13 · Trade press placements (Droupathy · partnership with Indian Pharma Industry, Pharmabiz, BioSpectrum India).

- W14 · GO-LIVE press splash (Droupathy curates · Contractor compliance scrub · Vimal final A).

## 9.3 Content / Editorial (Droupathy · Janani)

Six pillar articles, each anchored to one of the locked editorial pillars. Cadence in §10 below.

- Pillar #1 (W1–W4) — Annex 22 readiness for India SME pharma.

- Pillar #2 (W3–W6) — FDA CSA for SaaS-delivered QMS.

- Pillar #3 (W5–W9) — EU AI Act and what high-risk classification means for pharma QMS AI.

- Pillar #4 (W7–W12) — Human-in-the-loop architecture for AI-assisted quality decisions.

- Pillar #5 (W10–W13) — The founding-partner program model (post-G-8 signing only).

- Pillar #6 (W12–W14) — Customer evidence pack contents — what ships with subscription.

## 9.4 Website / SEO / AEO / GEO (Manoj · Droupathy)

- W1–W2 · verixa.ai launch (Manoj). Brand + bio kit shipped to site.

- W2–W4 · Schema + E-E-A-T (Manoj). Organization + SoftwareApplication + FAQPage schema on every pillar page.

- W3–W6 · Pillar pages + clusters (Manoj + Droupathy).

- W5–W9 · LP infrastructure (Manoj).

- W7–W11 · AEO/GEO engineering — featured-snippet targeting, AI Overview readiness, GEO entity reinforcement.

- W10–W13 · Resources hub launch (Manoj + Droupathy).

- W13–W14 · GO-LIVE landing page (Manoj). Conditional copy ready for both go-live and controlled-wave scenarios.

## 9.5 Digital / Paid (ArkOS) (Kavin)

Patent-filing-aware sequencing: pre-26-Jun = internal setup + founder 1-to-1 outbound only (no public ABM / paid). Post-26-Jun (W5+) = public sequences and paid ABM activate. ArkOS automation runs as a Prakash–Kavin–Droupathy thread. Raja approves any architecture change crossing tenant boundaries or affecting deliverability / data flow.

- W1–W2 · ArkOS + Apollo + GA4 + LinkedIn Insight Tag wired (Kavin operates · Prakash coordinates · Raja signs off on architecture). Internal-only · no public sends yet.

- W3–W4 · Founder 1-to-1 outbound to the 4 LIVE DP targets continues under NDA / private framing (Vimal sends · Kavin logs to ArkOS). NO bulk Apollo sequences yet.

- W5 (post patent filing 26 Jun) · Apollo sequences live for the 14 broader ICPs (Kavin builds · Vimal approves messaging · Prakash confirms ArkOS-to-Apollo automation contract).

- W5–W6 · LinkedIn ABM ads — small budget test, 4 LIVE DP accounts + 14 ICPs (Kavin · creative pre-cleared by Contractor).

- W5–W9 · Email nurture sequences live (Kavin · ArkOS automation thread).

- W7–W12 · Webinar funnels (Kavin builds · Droupathy owns content · Prakash confirms registration → ArkOS → demo-book flow).

- W10–W13 · Retargeting (Kavin · pixel + LinkedIn audience match).

- W13–W14 · Sep-01 Evidence Maturity / Verified Go-Live Decision campaign (Kavin · paid push — gated on Manisha UAT readiness green + W12 confirm + Vimal final A).

## 9.6 DP Pipeline / ABM (Vimal · Janani · Kavin)

- W1 · 14 ICPs locked (Vimal). Per W4 Outreach Cards: 4 LIVE + 1 BLOCKED actively engaged.

- W1–W4 · Founder outreach (Vimal).

- W3–W6 · Demos 8/14 (Janani delivers first-pass · Vimal joins from demo 4+ or P0/strategic only).

- W5–W9 · LOI sprint 3–4 signed (Vimal + Legal). G-8 SIGNED partner #1 by W9.

- W7–W11 · Pilot scoping (Vimal + Janani).

- W10–W13 · Partner onboarding (Janani).

- W14 · Partner GO-LIVE — conditional on engineering and partner-consent gate.

## 9.7 Events / Webinars (Droupathy · Janani)

Three webinars on the locked roadmap + an India roundtable at W12. Detail in §11.

## 9.8 Sales Enablement (Janani · Vimal)

- W1–W4 · Demo script + objection handling v1 (Janani drafts · Vimal reviews).

- W3–W6 · Demo script v2 (Janani · post first 8 demos).

- W5–W9 · Pricing + ROI live (Janani · in line with locked DP-A / DP-B / DP-C tiers).

- W7–W12 · Enablement kit (Janani).

- W10–W13 · G-7 leverage guide (Janani).

- W13–W14 · Production sales kit (Janani).

## 9.9 Compliance Review (Vimal · Contractor)

4 compliance audits + 1 final sign-off — schedule and owners in §5.6.

# 10. Editorial + Content Engine Detail

## 10.1 Editorial Mix

- Long-form pillar articles. 6 over W1–W14 (one per pillar). 1,400–2,200 words. Schema-marked (Article + FAQPage + HowTo where applicable). Each carries the standard disclosure (§5.3).

- Cluster articles per pillar. 2–3 supporting cluster articles per pillar. Each targets a specific long-tail buyer question.

- Newsletter. Bi-weekly from W3 onwards. Plain-text-first. Compliance-anchored. 5 sections: inspection radar · regulatory updates · Verixa shipped (carefully bounded to demo-only scope) · pharma case (anonymized) · open Q to readers.

- LinkedIn — Vimal Page. 3×/wk in Phase 1 (Droupathy first-drafts · Vimal reviews + posts). 5×/wk in Phase 2.

- LinkedIn — Verixa Page. Daily light cadence (Kavin owns Page · Droupathy supplies content).

- Op-eds. "Verify vs Validate" (W5–W9) + 1 op-ed per pillar window. Drop into trade press (Pharmabiz, Indian Pharma Industry, BioSpectrum India). Hindi-language adaptation if available.

- Podcasts. 3–5 founder appearances W3–W7. Droupathy books · Vimal records.

- Webinars. See §11.

## 10.2 SEO Discipline (Manoj)

- Each pillar page targets one head keyword (≤ 5 word phrase).

- Each cluster article targets 1 primary + 3–5 secondary long-tails.

- Internal linking: every cluster article links up to pillar + sideways to 2 sibling cluster articles.

- Manoj runs monthly cannibalization scan (Ahrefs) + quarterly content audit.

## 10.3 AEO Discipline (Featured Snippets · PAA · AI Overviews)

- Every long-form article begins with a 40–60 word direct answer to its primary question, schema-marked.

- Each article ships with ≥ 4 FAQ schema entries.

- "How to" content gets HowTo schema where applicable.

- Voice-search variants for top 20 buyer-intent questions tracked in Ahrefs.

## 10.4 GEO Discipline (ChatGPT · Perplexity · Gemini · Claude)

- Entity reinforcement: Verixa is described consistently across verixa.ai · LinkedIn · CrunchBase · positioning sentence is identical everywhere.

- Schema.org Organization + SoftwareApplication + FAQPage markup on every pillar page.

- Authored content cites primary sources (FDA, EMA, ICH, ISPE, PDA) so LLMs treat Verixa as a derivative authority worth citing.

- Quarterly GEO audit by Manoj: prompt ChatGPT + Perplexity + Gemini with the 20 highest-intent buyer prompts; track citation share. KPI target: 1 by W6 · 2 by W9 · 5 by W14.

# 11. Webinar Series Detail

## 11.1 Locked Webinar Schedule

| # | Window | Topic | Host | Co-host | Outcome |
| --- | --- | --- | --- | --- | --- |
| W1 (Webinar #1) | W5 invites · W7 LIVE (Wed 15 Jul) | "What EU GMP Annex 22 (Draft 2025) actually expects from AI in pharma quality" | Vimal | Janani · invited regulatory expert | Invites W5 (post patent filing 26 Jun) · 300+ reg target by W6 · LIVE W7 |
| W2 (Webinar #2) | W6 → W9 · Live W9 (Wed 30 Jul · subject to RC freeze pacing) | "FDA CSA in SaaS-delivered QMS — what the September 2025 final guidance actually changes" | Vimal | Janani · invited CSV/CSA practitioner | DP narrative reinforcement |
| W3 (Webinar #3) | W10 → W13 · Live W12 (Wed 19 Aug) | "Founding-partner program — the verify-not-validate model" | Vimal | Janani · invited founding partner (if consented) | Partner-consent-gated. Anchored to active DP narrative. |
| W4 (Launch event) | W14 · Tue 01 Sep | "Verixa verified go-live — what ships, what we verify, what the partner validates" | Vimal | Janani · founding partner (if consented) | Conditional on W12 confirm. Launch posture or controlled-wave posture. |

## 11.2 Production Spec

- Riverside or similar high-fidelity remote production.

- Recording → newsletter + LinkedIn clip set + on-page replay (verixa.ai/webinars/{slug}).

- Each webinar deck reviewed by Contractor pre-live for ban-word + claim-binding compliance.

- Q&A capture in ArkOS: questions get reply ownership assigned to Droupathy + Janani within 24h.

- Per W4 outreach card discipline: no "validated" or "compliant" framing anywhere in webinar marketing or in the webinar itself.

# 12. Founder PR + Voice Operating Detail

## 12.1 Founder Voice Doctrine

- Voice. Confident · evidence-anchored · technically literate · understated · never hyperbolic.

- Cadence. 3×/wk Phase 1 → 5×/wk Phase 2. Droupathy first-drafts · Vimal reviews + posts.

- Topic mix. Educational (40%) · Founder POV (25%) · Peer / customer signal (15%) · Question-back to audience (10%) · Verixa product proof (10% · Phase 2+ only, post-LOI signing).

- Pre-posting check. Droupathy runs every draft through the ban-phrase list (§5.1) before sending to Vimal.

## 12.2 PR Calendar (Locked)

| Window | Trigger | PR Action | Owner |
| --- | --- | --- | --- |
| 🔒 Fri 26 Jun | Demo-ready lock | PR splash: "Verixa demo-ready · design-partner cohort open" | Droupathy |
| W6 → W9 | RC freeze + G-8 signed (partner #1) | PR #2 (consent contingent — only if signed partner consents) | Droupathy · Vimal |
| W10 → W13 | Pre-launch warming | Trade press placements (Pharmabiz · Indian Pharma Industry · BioSpectrum India · CDSCO-adjacent publications) | Droupathy |
| W13 | G-7 + Kit | India QA roundtable post-event PR | Droupathy |
| 🎯 Tue 01 Sep | Verified go-live (CONDITIONAL) | Launch press release IFF W12 confirm + W14 per-workflow verified · otherwise controlled-wave posture | Droupathy · Vimal · Contractor |

## 12.3 PR Risk Discipline

- Every press release is Contractor-cleared first, Vimal-approved second.

- If a journalist asks about validation status: Vimal personally takes that question. Marketing pod does not improvise.

- Partner consent for naming / quoting requires written approval stored in ArkOS Partner-Consent-Register.

- "Controlled wave" / "founding-partner verification program" is the fallback posture if go-live conditions are unmet — NEVER "delayed launch".

# 13. Digital + Paid Operating Detail

## 13.1 LinkedIn ABM (Kavin)

Small-budget test through W6 against the 14 ICPs + 4 LIVE DP accounts. Then scale based on KILL-CHECK result.

- Audience model. Company match list (14 ICPs) · job-title targeting (VP Quality, Head of Quality, MD, CIO, Head of Regulatory) · seniority Director+. Excludes Windlas + any disqualified accounts.

- Creative. Three concept families: (a) Annex 22 readiness · (b) AI evidence trail · (c) Founding-partner program. Each creative pair (image + 30-second video). Refresh quarterly.

- Compliance scrub. Every creative passes Contractor first-pass-claim review before launch.

- Spend gates. Pre-W6: low-budget test only. Post-KILL-CHECK: scale only if primary KPIs at green. Post-W14: production push.

## 13.2 Email Nurture (Kavin · Droupathy supplies content)

- Cadence. Bi-weekly newsletter + event-triggered drops (webinar invites · post-event replay).

- Sequence templates. See Appendix E. Cold / Warm / Inbound / DP — locked language only.

- Compliance. DPDP 2023 + GDPR + CAN-SPAM. Universal unsubscribe + registered physical address in every email.

## 13.3 Retargeting (Kavin)

- Pixels. LinkedIn Insight Tag + Meta Pixel (Verixa Page only — not Vimal personal LinkedIn) wired on verixa.ai.

- Audiences. ICP-matched visitors who consumed pillar content. Excludes any prospect on the disqualification list.

- Spend cap. Pre-W14: light-touch (warming only). Post-W14: production cadence if go-live confirmed.

## 13.4 UTM Standard + n8n Glue (Locked · v1.1 ownership clarified)

Five-parameter UTM standard. All marketing URLs use this discipline. n8n validates the tag combination; any tag not in the controlled vocabulary routes to Kavin. v1.1 ownership: Kavin operates the n8n integration plane. Prakash coordinates any change that touches the ArkOS automation thread (Verixa). Raja approves any architecture change affecting tenant boundaries, data residency, or deliverability.

- utm_source. linkedin-vimal · linkedin-verixa · sales-nav · newsletter · webinar · event-{slug} · referral-{partner} · organic · paid-linkedin · vimal-outbox

- utm_medium. outbound · social · email · content · paid · event · referral

- utm_campaign. phase1-launch · phase2-loi-sprint · phase3-go-live · pillar-{slug} · webinar-{n} · arkos-test

- utm_content. Asset slug · creative variant

- utm_term. Optional · keyword or ICP segment

# 14. Measurement, Attribution & Friday Pod Sync

## 14.1 Reporting Layers

| Layer | Audience | Cadence | Tool |
| --- | --- | --- | --- |
| Layer 1 — Primary KPI dashboard | Vimal · Droupathy · Janani | Weekly Friday 11:00 IST | ArkOS dashboard |
| Layer 2 — Workstream dashboards | Marketing pod | Daily ArkOS view | ArkOS dashboard |
| Layer 3 — Monthly strategic report | Vimal · Janani · Contractor | First Monday of month | 5-page slide deck + ArkOS export |
| Layer 4 — Quarterly board-ready | Board + investors (post-close) | Quarterly | Aligned to investor update format |

## 14.2 Attribution Model

- First-touch. Earliest contactable interaction (form fill · LinkedIn message reply · event handshake) credited fully to the channel that delivered it.

- Multi-touch. Even-weight across all logged touches in ArkOS during the deal cycle. Pipeline value attributed proportionally.

- Last-touch. Final interaction before opportunity creation — tiebreaker only.

- Conflict resolution. Channels with disagreement > 30% between first-touch and multi-touch get reviewed at Monthly Strategic.

## 14.3 Friday Pod Sync (Locked Cadence · 11:00 IST)

- Open with the 6 primary KPIs (LOIs · G-8s · Partners ready · Scoping calls · Evidence-pack receipts · Partner-approved go-live statements).

- Public Claim Register status — any flagged or stale entries?

- DP target health — Caplin / Solara-Synthix / Cohance / SMS / Windlas-unblock-gates.

- Workstream-by-workstream stand-up (5 min each, 9 workstreams).

- Approval queue clearance for the founder voice batch.

- Next-week plan + ownership. Wins, misses, asks.

## 14.4 Anti-Vanity Discipline

- Reach / impressions / follower counts reported as context only, never as a goal.

- Open rates are reported with explicit caveat (Apple Mail Privacy Protection).

- AI-search citations checked manually by Manoj quarterly.

- Every marketing claim used externally has an evidence note in the Public Claim Register.

# 15. Risk Register — Operational Layer

These are operational-layer risks that sit under the master risk list in Verixa Pilot Execution Plan v3 MASTER §10. They are tracked in ArkOS and reviewed weekly.

| Ref | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| MR-01 | ArkOS objects / pipelines / reports not ready by Mon 22 Jun | Medium | High | v1.1 escalation: Prakash + Janani jointly escalate to Raja by Wed 17 Jun. Raja decides on implementation + sequencing within agreed architecture. If unresolved 48h, Viji is final escalation. Contingency (Vimal-approved only): Apollo + Clay run as temp source-of-truth ≤ 14 days · documented in Public Claim Register. |
| MR-02 | Email infrastructure decision (Apollo native / Smartlead / Instantly) slips past W3 | Medium | Medium | Default to Apollo native warm-up at W3 Thu morning if no decision. Re-evaluate at W6. |
| MR-03 | Mailbox warming fails or domain reputation drops | Medium | Medium | Pre-warmed secondary domains via Apollo. Weekly reputation check (GlockApps or equivalent). Founder primary mailbox preserved for high-trust only. |
| MR-04 | LinkedIn account restriction on Vimal | Low | High | Conservative volume below soft limits. Two-LinkedIn playbook (Vimal personal + Verixa Page). Daily ritual logged in ArkOS. |
| MR-05 | Banned phrase appears in an external asset | Medium | High — credibility hit | Contractor first-pass-claim review is non-negotiable. Pre-publish checklist enforced. If observed live: pull within 4 working hours. |
| MR-06 | DP target list shifts mid-week (e.g., Caplin slips, new target added) | Medium | Medium | Marketing Lead refreshes this plan + ArkOS DP-Agreement objects within 24h. Pod re-notified. |
| MR-07 | Marketing pod capacity stretched (3 FTE + 1 fractional · 187 work items in 14 weeks) | High | Medium | Drop or defer non-critical assets (e.g., 2nd webinar slipped to W11 · 5th pillar to W12). Weekly Friday capacity check. v1.1: Prakash acts as process-coordination valve — surfaces what to defer + drives readiness through defined processes. Viji is final escalation if capacity conflict cannot be resolved. |
| MR-08 | Webinar #1 reg < 200 by 30 Jun | Medium | Medium | Activate B-list: founder podcast guests · ISPE chapter newsletters · partner-network amplification. |
| MR-09 | ABM ad set rejected by LinkedIn (regulated-industry policy) | Low | Medium | Pre-clear creative concepts with LinkedIn account rep. Submit early. |
| MR-10 | PR splash 26 Jun lands flat | Low | Medium | Trade-press pre-briefings W3 + W4 to set expectations. Founding-partner consented quote in pocket as Plan B. |
| MR-11 | Founder bandwidth — fundraising + product + outbound overlap | High | High | Daily cadence §8.1 is the discipline. Droupathy preps every batch. Janani fronts product-side demos. |
| MR-12 | Partner-consent gate breached (logo / quote used without written approval) | Low | High | Partner-Consent-Register in ArkOS. Vimal + Legal sign-off before any external partner reference. |
| MR-13 | Negative engineering signal at W6 KILL-CHECK | Medium | High | Marketing immediately switches to authority-only content. Demo offer pulled within 24h. Holding template T-RECON pre-approved. |
| MR-14 | 01 Sep go-live unmet | Medium | High | Transition to "controlled wave / founding partner verification program" copy. Public launch deferred to verified date. NEVER "delayed launch." v1.1: Manisha is the UAT-readiness signal owner — marketing's go-live messaging depends on her green status by Mon 31 Aug T-1 audit. If Manisha flags UAT not ready, marketing automatically routes to controlled-wave posture; no founder override required. |
| MR-15 | Operating tool downtime during launch week | Low | High | ArkOS Friday snapshot backed up to Notion. Launch-week incident playbook (Kavin). |
| MR-16 | Contractor (CSV/CSA + RA) hire not closed → Vimal holds both first-pass + final claim review | High | High | Until Contractor onboarded, Vimal holds BOTH first-pass + final approval — two-person check collapses + founder bandwidth load increases. URGENT close before W6 KILL-CHECK (Mon 06 Jul). Sources: founder-network referrals + counsel referrals + India RA consultancy outreach. NOT Janani. Vimal owns the hire decision. |

# 16. 90-Day Execution Calendar — Week-by-Week from W3 to W14

This calendar is the operational layer under the GTM Launch Flow swimlane. It surfaces the marketing-pod-owned actions only. The full 187-item catalog lives in the Assignee Calendar HTML; do not duplicate, link to that.

| Week | Marketing Pod Actions | Owner | Verification Checkpoint |
| --- | --- | --- | --- |
| W3 (Mon 15 Jun) — INTERNAL ONLY (patent disclosure window) | ArkOS objects + pipelines + reports confirmed live · Sales Navigator seats live (Vimal + Droupathy) · Apollo DEFERRED · Clay DROPPED (per simplified stack §7) · INTERNAL drafting only: Newsletter #1 ready-but-unsent · Pillar #1 + #4 drafted-but-unpublished · Webinar #1 reg page drafted-but-unpublished · founder 1-to-1 OUTBOUND continues to known DP targets via Vimal's outbox (verixa.ai) + LinkedIn DM under NDA / private framing (no public claims) | Janani + Kavin + Droupathy + Manoj | ArkOS report list screenshot · 9 reports running · drafts in ArkOS staging · 1-to-1 outbound log |
| W4 (Mon 22 → Fri 26 Jun) — PATENT FILING WINDOW | Patent filing target Fri 26 Jun (Vimal + IP team) — public-disclosure-gated marketing remains held · Founder 1-to-1 outbound to 4 LIVE DP targets CONTINUES (Caplin · Solara-Synthix · Cohance · SMS) · Janani prep on first-pass demos in segregated eval env · Compliance audit #1 passes · 🔒 Fri 26 Jun: DEMO-READY LOCK + patent filing complete · PR posture for 26 Jun reduced to internal note only (public PR moves to W5 per Commercial Priority Override) | Vimal + Janani + Kavin + Droupathy + Manoj + Contractor | Patent-filing complete confirmed in writing · ArkOS sequence report · audit pass |
| W5 (Mon 29 Jun) — PUBLIC MARKETING UNLOCKS (DUAL GATE) | Public marketing unlocks ONLY when BOTH gates pass: (1) Patent filing complete AND patent counsel confirms in writing that intended public disclosures are covered by the filed materials or are safe to disclose · (2) Compliance gate: contractor onboarded OR Interim-Vimal mitigations live with external counsel retainer. If either gate fails on Mon 29 Jun: Founder 1-to-1 outbound continues; public assets stay drafted-but-unpublished. If both pass: Newsletter #1 ships · Pillar #4 (Schedule M) + Pillar #1 (Annex 22) live · Vimal LinkedIn rhythm begins (3×/wk drafted by Droupathy · Vimal approves) · PR note "design-partner cohort open" published · Webinar #1 invitations sent · Tue 30 Jun G-JUN exit | Vimal + Droupathy + Manoj + Kavin + Patent Counsel + External Compliance Counsel (if Interim-Vimal) | Patent counsel written clearance + Compliance gate documented + assets published or held with reason |
| W5 (continued) · DP discovery + Demo script v1 | DP discovery calls underway · Demo script v1 ready · Janani delivers first-pass demos · Vimal joins from demo 4+ or P0/strategic | Droupathy + Vimal + Janani | Demo book log · discovery notes |
| W6 (Mon 06 Jul) | 🔥 W6 KILL-CHECK (SINGLE GATE): 🟢 GREEN = 1 paid sprint signed OR 1 priced LOI/MSA in legal with scope agreed. 🟡 YELLOW = 2 qualified buyer meetings + named sponsor + written next step. 🔴 RED = no named sponsor / no paid scope acceptance / buyer requires validated production claim — narrow to 6 high-conviction accounts. MQL/SQL volume is NOT a W6 target. Pillar #2 (FDA CSA, see Phase 1 distinction §10) live IF contractor onboarded OR external counsel review complete. Compliance audit #2. | Vimal + Droupathy + Manoj + Contractor (or interim) | KILL-CHECK decision documented · audit pass |
| W7 (Mon 13 Jul) | Webinar #1 LIVE (Wed 15 Jul) · post-event nurture · case study draft begins on discovery learnings · Demo script v2 · Op-ed "Verify vs Validate" draft v1 by Droupathy | Droupathy + Vimal + Janani | Webinar recording · attendee export · op-ed draft v1 |
| W8 (Mon 20 Jul) | Pillar #3 (EU AI Act) live · 2 cluster articles published · webinar funnels live · ISPE event submission | Droupathy + Manoj | 3 URLs live · webinar funnel set |
| W9 (Mon 27 Jul) | 🔒 Fri 31 Jul RC FREEZE + G-8 SIGNED (founding partner) · Webinar #2 LIVE (Wed 30 Jul) · founding-partner messaging unlocked (consent-gated) · Pricing page draft live · Op-ed published · Compliance audit #3 | Vimal + Droupathy + Janani + Legal + Contractor | G-8 in ArkOS · webinar #2 recording · op-ed live URL · audit pass |
| W10 (Mon 03 Aug) | Mon 03 Aug CHANGE-CONTROL FREEZE — no new product claims · Pillar #4 (HITL) live · founding-partner program app closes by Fri 07 Aug · email nurture v2 | Droupathy + Manoj + Kavin | Pillar live · application set closed · ArkOS log |
| W11 (Mon 10 Aug) | Trade-press placements active (Pharmabiz · Indian Pharma Industry · BioSpectrum) · podcast pilot recorded · press list warming begins | Droupathy + Vimal | 5+ warm press contacts · pilot file |
| W12 (Mon 17 Aug) | Webinar #3 LIVE (Wed 19 Aug · founding-partner program) · Pillar #5 (founding partner) live · mid-market US/EU outbound activated (cards drafted but held until 01 Sep confirmation) | Droupathy + Vimal + Kavin | Webinar #3 · pillar live · mid-market sequences drafted |
| W13 (Mon 24 Aug) | Fri 28 Aug G-7 + ENABLEMENT KIT delivered · India QA roundtable (W12 or W13 depending on venue) · launch press releases drafted (both conditional scenarios) · Pillar #6 (evidence pack) live · Compliance audit #4 | Vimal + Janani + Droupathy + Contractor | Press kit · roundtable held · pillar live · audit pass |
| W14 (Mon 31 Aug) | Mon 31 Aug final compliance sign-off (T-1) · 🎯 Tue 01 Sep VERIFIED GO-LIVE (CONDITIONAL): if W12 confirm + W14 per-workflow verified → launch press release + LinkedIn drumbeat + Webinar #4 LIVE + customer story drumbeat; else → "controlled wave / founding-partner verification program" posture · hypercare begins | All | Coverage log · attendance log · LinkedIn engagement log · partner-consent log |
| W14+ (02–06 Sep) | Hypercare: 3 DP onboarding kickoff calls · launch retrospective Fri 06 Sep | Vimal + Janani + Droupathy | Calls held · retrospective doc |
| W15 (08–12 Sep) | Buffer window for backstop activity if required | Vimal | Status update |
| 🛑 W16 (15 Sep) | HARD BACKSTOP — marketing posture confirmation | Vimal | Written confirmation in ArkOS |

# 17. Identified Gap Resolution — Inbound Leads + Product Coordination

Viji's role-clarification memo (18 Jun 2026) explicitly identified a gap: "The identified gap around incoming leads and product coordination is a separate GTM / customer-engagement need and will require a dedicated owner within Marketing / Sales." This section resolves the gap with an interim assignment and a hire-trigger gate.

## 17.1 The Gap

v1.0 split inbound-lead handling across two roles informally:

- §4.2 Inbound pipeline: Droupathy (A) + Kavin (R).

- §Appendix E C3 (Inbound sequence): Vimal personally handles first reply within 4 working hours.

Neither was a dedicated owner. Inbound velocity, product-coordination handover to Janani, and demo-booking → ArkOS opportunity progression had no single accountable point.

## 17.2 The Decision — Option C (Interim + Hire-Trigger)

| Option | Action | Why Not Chosen / Why Chosen |
| --- | --- | --- |
| A — Hire dedicated GTM/CE lead now | New FTE (SDR / BDR / Customer-Engagement) slots into pod by W6 KILL-CHECK | Not chosen: would delay clarity into W6; hiring decision needs a forcing function tied to engineering health |
| B — Expand Janani's scope to own incoming-lead → product-coordination | Janani assumes the dedicated owner role | Not chosen: Janani already at MR-07 capacity risk · would compromise her first-pass demo role + product-ownership decisions |
| C — Droupathy interim · Janani co-pilot · hire-trigger at W6 | Interim now; mandatory hiring decision at W6 KILL-CHECK gate | SELECTED · creates an immediate owner without overloading Janani · ties the hire to the natural pilot gate · forces a decision on or before Mon 06 Jul |

## 17.3 Operating Model (Interim · W3 → W6)

- Owner. Droupathy holds the dedicated owner accountability for inbound leads + product coordination handover.

- Co-pilot. Janani co-pilots on product-coordination handover only (qualification → demo-book → product walkthrough).

- Founder reply rule (unchanged). Vimal still personally replies on inbound from any of the 4 LIVE DP targets within 4 working hours.

- ArkOS hygiene. Every inbound lead lands in the Inbound pipeline within 1 working hour. Routing to discovery vs nurture decided within the same business day.

- Handover SLA. From inbound form-fill / DM to first founder reply ≤ 4 working hours · to first Calendly link sent ≤ 1 business day · to demo-book event ≤ 5 business days for qualified opportunities.

- Volume cap. Droupathy holds the interim role for ≤ 30 net new inbound leads/week. If volume exceeds, escalate to Vimal for hiring acceleration (skip W6 trigger).

## 17.4 Hire-Trigger at W6 KILL-CHECK (Mon 06 Jul)

At the W6 KILL-CHECK gate, Vimal + Droupathy + Janani make one of three decisions on the inbound-lead + product-coordination role:

- HIRE — open requisition same day for SDR / BDR / Customer-Engagement role. Target onboarding by W9 (Mon 27 Jul). Budget impact ~₹2–3 L/month.

- EXTEND INTERIM — Droupathy continues as interim owner through Phase 2 close (W13). Hire deferred to verified-go-live cohort (Q4).

- PIVOT — if W6 KILL-CHECK fails and ICP narrows to 8 high-conviction accounts, inbound velocity may drop enough that the dedicated role is not needed pre-Q4. Interim continues.

## 17.5 Job-Description Anchor (For W6 Hiring Case)

Pre-drafted so the hire decision moves fast at W6. To be reviewed and refined by Droupathy + Vimal before W6.

- Title. GTM / Customer Engagement Lead (Interim title; resolve at hire time).

- Reports to. Droupathy (Marketing Lead) · dotted line to Vimal.

- Owns. Inbound lead velocity + qualification · ArkOS Inbound pipeline hygiene · handover to product (Janani) for demo-book + walkthrough · post-demo follow-up cadence · pipeline-stage accuracy.

- Profile. 2–5 years B2B SaaS inbound / SDR / customer-engagement experience. Regulated-industry preference (pharma / healthcare / fintech / defence).

- Day-1 success. First 30 days: clean Inbound pipeline · standardize qualification rubric · take demo-book SLA from 5 business days to 3.

- Compensation. Market band for India remote-first role. Aligned to seed-stage equity grant.

- Hiring channel. Founder-led referral first (Vimal + Viji networks). External posting if no qualified referral within 5 business days of W6 decision.

# 18. Approvals & Sign-Off

This plan becomes the operating handbook only after the extended pod sign-off window closes. Comments captured in ArkOS Compliance-Review-Log linked to this document. v1.1: roster expanded from 6 to 9 signers to include the Sense7ai DP team named in §2.1.

| Role | Name | Sign-Off Required | Comment Window Closes |
| --- | --- | --- | --- |
| Founder & CEO (final A on all) | Vimal Veereshwarayya, PhD., RAC | Approve | Mon 22 Jun 2026 17:00 IST |
| Marketing Lead | Droupathy | Approve + execute | Mon 22 Jun 2026 17:00 IST |
| Digital Marketing Manager | Kavin | Acknowledge · raise blockers | Mon 22 Jun 2026 17:00 IST |
| Web · SEO/AEO/GEO Lead | Manoj | Acknowledge · raise blockers | Mon 22 Jun 2026 17:00 IST |
| Product Manager (Verixa) | Janani Rangesh | Acknowledge · raise product gaps · confirm interim co-pilot role on §17 | Mon 22 Jun 2026 17:00 IST |
| Technical Ownership (Sense7ai DP) | Raja | Acknowledge · confirm ArkOS automation architecture readiness by W4 | Mon 22 Jun 2026 17:00 IST |
| PM Coordination (Sense7ai DP) | Prakash | Acknowledge · confirm ArkOS automation thread capacity through W14 | Mon 22 Jun 2026 17:00 IST |
| UAT Readiness (Sense7ai DP) | Manisha | Acknowledge · confirm UAT readiness signal cadence through Mon 31 Aug | Mon 22 Jun 2026 17:00 IST |
| Operating + Leadership Support (Sense7ai DP) | Viji Janakiraman | Acknowledge · confirm escalation availability | Mon 22 Jun 2026 17:00 IST |
| External CSV/CSA + RA Contractor | TBD — interim covered by Vimal | Hire close before W6 KILL-CHECK (Mon 06 Jul) · interim Vimal holds first-pass + final until then | Hire-close: Mon 06 Jul 2026 17:00 IST |

Effective date upon all 10 sign-offs (9 named internal reviewers + 1 external CSV/CSA + RA Contractor — or Vimal interim per §Contractor Hard Deadline rule): Mon 22 Jun 2026 (W4 start). Deadline extended to give the named Sense7ai DP team members a full weekend for review.

# Appendix A — Workstream Owner-Action Reference

This appendix points to the source documents that own the per-week, per-owner, per-action detail. Do not duplicate that data here — read the source.

| Document | Path · Pointer | Owner of Source | Use For |
| --- | --- | --- | --- |
| Verixa Pilot Execution Plan v3 MASTER | Verixa GTM / Pilot_Execution_v3_2026-05-31 / Verixa_Pilot_Execution_Plan_v3_MASTER.md | Vimal | Engineering anchor · phase definitions · gates |
| Verixa GTM Launch Flow v2 (HTML) | Verixa GTM / Pilot_Execution_v3_2026-05-31 / Verixa_GTM_Launch_Flow.html | Vimal | Swimlane · workstream bars · gates · KPI tables · sign-off section |
| Verixa GTM Assignee Calendar | Verixa GTM / Pilot_Execution_v3_2026-05-31 / Verixa_GTM_Assignee_Calendar.html | Vimal | 187 work items filtered by owner · weekly load · critical-path filter |
| Verixa GTM Launch Plan 2026 (XLSX, 15 sheets) | Verixa GTM / Pilot_Execution_v3_2026-05-31 / Verixa_GTM_Launch_Plan_2026.xlsx | Vimal | Per-sheet operational catalog · Sheet 14 = Public Claim Register |
| Verixa Pilot Timeline 2026 (XLSX) | Verixa GTM / Pilot_Execution_v3_2026-05-31 / Verixa_Pilot_Timeline_2026.xlsx | Vimal | Engineering timeline mirror |
| Verixa Design Partner Strategy LOCKED | Sense7ai-India / verixa / GTM / 02_Account_Targeting / Verixa_Design_Partner_Strategy_LOCKED_2026-05-22.md | Vimal | LOCKED DP strategy · pricing tiers · 7 MSA clauses · disqualification criteria |
| W4 Founder Outreach Cards | Verixa GTM / Verixa_W4_Outreach_Cards_2026-06-10.md | Vimal | 4 LIVE + 1 BLOCKED · approved phrasing · banned phrases · first-call discovery questions |
| Verixa G7 Supplier Assurance Guide | Verixa GTM / Pilot_Execution_v3_2026-05-31 / Verixa_G7_Supplier_Assurance_Guide.html | Vimal · Contractor | G-7 evidence-pack scope · what marketing can reference from G-7 in claims |
| Verixa Pricing Deck (Branded · v2 Final) | Verixa GTM / Verixa_Pricing_Deck_Branded_2026-06-04.pdf + pptx | Vimal | Locked pricing positioning · DP-A/B/C tiers |

# Appendix B — Apollo Saved-Search Setup Spec (DEFERRED)

Apollo is DEFERRED from the W3-W14 stack (per §7.3). The saved-search library below is retained for fast re-activation if cold email becomes the primary channel for unreached ICPs at W5+. Until then, no seats, no spend. Re-evaluation at W6 KILL-CHECK: activate Apollo only if (a) Sales Nav InMail volume is exhausted for the broader 14 ICPs AND (b) cold email is identified as the actual primary channel.

Saved-search library (held for conditional re-activation only · counts estimated):

| # | Saved Search Name | Key Filters | Persona × Tier |
| --- | --- | --- | --- |
| S-01 | India Pharma · USFDA-approved · Head of Quality | India · pharma · 200–2,000 emp · seniority VP/Director · function Quality | A × 1A |
| S-02 | India Pharma · CDMO · Plant Head | India · CDMO/CMO keyword · 100–1,500 emp · seniority Director+ · function Operations | B × 1B |
| S-03 | India CDMO · CIO / Head of IT | India · CDMO/pharma · IT/IS function · seniority Director+ | C × 1A/1B |
| S-04 | India Pharma · MD / CEO of mid-size mfr | India · pharma · 100–500 emp · seniority C-level/MD/owner | D × 1A |
| S-05 | India Pharma · Head of Regulatory Affairs | India · pharma · function Regulatory Affairs · seniority Director+ | E × 1A/1B |
| S-06 | India MedTech · ISO 13485 + Class B/C/D | India · medical-device · 50–500 emp · Quality function | A × 2 |
| S-07 | US Mid-Market Pharma · Not on Veeva (Phase 3 only) | US · pharma · 100–1,500 emp · function Quality · excludes Veeva mentions | A × 3 — held until 01 Sep confirmation |
| S-08 | US/EU Phase 2/3 Biotech · QA/IT | US/EU · biotech · 50–300 emp · QA or IT function · clinical-trial stage Ph 2/3 | A × 4 |
| S-09 | India ISPE Chapter Members | India · ISPE LinkedIn group filter · pharma + biotech | A × 1A (warm) |
| S-10 | India PDA Chapter Members | India · PDA LinkedIn group filter | E × 1A (warm) |
| S-11 | India Pharma · Recent Job Change · Head of Quality | India · function Quality · seniority Director+ · changed job ≤ 90 days | A × 1A (high-signal) |
| S-12 | Sponsor-Audit-Pressured CDMO | India CDMO · client-list signal (multi-MNC) · revenue 25M+ | B × 1B |

# Appendix C — Clay Enrichment Waterfall + Trigger-Score Spec (DROPPED)

Clay is DROPPED from the W3-W14 stack (per §7.4). The waterfall + trigger-score spec below is retained for reference only — revisit at W14+ when prospect volume exceeds 25/week and manual enrichment fatigue is real. Until then, Janani hand-enriches the 4 LIVE DP targets (USFDA EIR · MCA filings · LinkedIn signals) in an afternoon.

Waterfall + trigger-score spec (held for future scale phase only):

### Waterfall — Step 1: Identity

- Apollo: primary identity lookup (email + title + company).

- Hunter: cross-check email syntax / pattern + verification.

- Dropcontact: GDPR-aware enrichment (EU contacts).

- Anymailfinder: fallback if all three above miss.

### Waterfall — Step 2: Company Signal

- LinkedIn employer history (via Sales Navigator export).

- Crunchbase: funding events.

- USFDA Establishment Registration: site-level inspection history (Verixa workspace corpus).

- FDA 483 narrative corpus (Verixa Validate Dataset · already in workspace) — site-level lookup. INTERNAL ENRICHMENT ONLY. Never cited in outbound copy. Per W4 Outreach Cards rule: never lead with enforcement history.

- MCA (India) filings — board changes, capital raise.

### Waterfall — Step 3: Contact Signal

- LinkedIn recent activity (posts in last 14 days, signal-engagement).

- Job-change detection (LinkedIn snapshot diff over 7 days).

- Speaker / panelist activity (event LinkedIn surfacing).

### Step 4 — Trigger Score (Composite)

| Signal | Weight | Decay |
| --- | --- | --- |
| Public AI-governance commentary by company leadership | +25 | Linear over 180 days · primary positive signal |
| Funding event (Series A/B/C/PE) | +15 | Linear over 180 days |
| Head of Quality job change (≤ 90 days) | +20 | Step-function at 90 days |
| Sponsor audit win/loss (LinkedIn announcement) | +12 | Linear over 90 days |
| New manufacturing site (filing or announcement) | +10 | Linear over 180 days |
| Schedule M readiness mention (LinkedIn / press) | +8 | Linear over 60 days |
| Pre-existing Verixa / founder connection | +30 | No decay |
| ⚠ Recent USFDA 483 / Warning Letter — internal use only | +0 (excluded from positive scoring) | Do not weight; per W4 rules, never lead with enforcement history |

Composite ≥ 30 → ArkOS "Hot Today" list. Composite 15–29 → "Warm This Week". Composite < 15 → "Nurture".

# Appendix D — Sales Navigator Saved-Search + Daily Ritual Spec

Eight saved searches with daily alerts on Vimal's account. Droupathy mirrors a subset on her account. Alerts feed into Clay via manual export each Friday until automated.

| # | Saved Search Name | Filters | Alert Cadence |
| --- | --- | --- | --- |
| SN-01 | India Pharma QA Leaders — Active Posters | India · pharma · Quality function · seniority VP/Director · posted in last 30 days | Daily |
| SN-02 | India CDMO Leadership — Active | India · CDMO/CMO · seniority C-level/Director · activity-led filter | Daily |
| SN-03 | India MD/CEO of mid-size pharma | India · pharma · 100–500 emp · seniority Owner/MD/CEO | Weekly |
| SN-04 | US Mid-Market Pharma Quality (Phase 3 only) | US · pharma · 100–1,500 emp · Quality function · VP/Director | Weekly · holding pattern until 01 Sep |
| SN-05 | Phase 2/3 Biotech US/EU QA | US/EU · biotech · 50–300 emp · Quality function | Weekly |
| SN-06 | ISPE India Members — Active | Member of ISPE group · India · pharma/biotech · activity-led | Daily |
| SN-07 | Decision-Makers Engaged with Veeva/MasterControl/ETQ | Function Quality · seniority VP+ · mentions or engages with Veeva/MasterControl/ETQ posts | Daily |
| SN-08 | Newly Promoted Heads of Quality | Quality function · seniority VP/Director · promoted ≤ 90 days | Daily |

### Vimal's Daily Sales-Nav Ritual (Locked · 09:00–09:30 IST)

- Open Sales Navigator → News + Updates.

- Review 8 saved-search alert digests.

- Promote up to 10 high-signal contacts into ArkOS "Hot Today" list.

- Mark any forward-looking signal worth a comment-engagement for the 09:30–10:30 slot.

- Per W4 rule: forward-looking signals only, never enforcement history.

# Appendix E — ArkOS CRM Sequence Templates

These templates use locked language only. Every outbound email or LinkedIn message must originate from one of the templates below. Marketing team can polish; Vimal final-approves. The W4 Outreach Cards file is the source of truth for the 4 LIVE DP targets — those cards take precedence for Caplin / Solara-Synthix / Cohance / SMS first touches.

### Standard Disclosure (Required Verbatim at Top of Every Card and Pilot Asset)

"Co-design evidence sprint. Phase 1 produces design-partner evidence artifacts, not a validated GxP production deployment. Customer validation of intended use is not included."

### C1 — Cold (India SME Pharma Head of Quality · No Warm Tie)

- Day 0 — LinkedIn view profile + follow + comment on most-recent post.

- Day 1 — LinkedIn connection request, personalized 220 chars, no pitch.

- Day 3 — Email 1, trigger-anchored forward-looking signal (Schedule M deadline · expansion · sponsor change · public AI governance commentary). 1 paragraph + 1 clear ask + universal unsubscribe.

- Day 6 — LinkedIn DM (if connected) OR Email 2, value drop: Loom (≤ 90s) + 1 data point + Verixa one-pager (Phase 1 + 2 scope).

- Day 10 — Email 3, peer evidence (anonymized peer quote, no source disclosure).

- Day 14 — Email 4, final "should I close the loop?" + clear opt-out.

- Day +30 — Quarterly newsletter re-engagement.

### C2 — Warm (Mutual Connection or Content Engagement)

- Day 0 — Founder DM referencing the warm signal.

- Day 2 — Email recap + Calendly link for 25-min discovery.

- Day 5 — Loom (≤ 90s) addressing one specific pain anchored in the Commercial Sprint Scope (deviation → RCA → CAPA → effectiveness check → closure → evidence trail). No unsupported peer percentage claims. No OOS reference (OOS is OUT of Commercial Sprint Scope · belongs to Product Phase 1 module set only).

- Day 9 — Gentle bump.

- Day 14 — Pause; re-engage with newsletter.

### C3 — Inbound (verixa.ai Form-Fill or LinkedIn DM)

- Day 0 — Founder reply within 4 working hours. Direct Calendly link + 1 contextual question.

- Day 1 — If no booking: Loom (≤ 90s) addressing the question + Calendly.

- Day 3 — Gentle bump.

- Day 7 — Archive to Warm Nurture if no engagement, else proceed to discovery.

### C4 — Design-Partner Target (High-Trust, Multi-Stakeholder · For 4 LIVE Targets)

The W4 Outreach Cards file owns the actual first-touch language for Caplin / Solara-Synthix / Cohance / SMS. The cadence below is the wrapper.

- Day 0 — Founder personalized email anchored in W4 hook + Verixa DP brief (excerpts from DP deck v3.4).

- Day 4 — Short Loom (90s) addressing the regulatory pressure they face today (forward-looking framing only).

- Day 10 — Founder calls Plant Head or CIO with reference to first email.

- Day 14 — Bring Janani (PM) on second call for product walkthrough (Phase 1 boundary).

- Day 21–30 — DP brief 2.0 + commercial scope conversation.

### Holding Template T-RECON (For W6 KILL-CHECK Risk)

"We're pausing the demo offer this week while a controlled gate runs. Standing offer: I'll share our quarterly structured-evidence brief — reviewable evidence trail format — on Friday. Reply YES if useful."

# Appendix F — Content Brief + Compliance Review Form

Droupathy uses this brief to commission every content piece. Manoj reviews SEO/AEO/GEO fields. Janani reviews technical claims. Contractor reviews compliance fields. Vimal final-approves.

| Field | Required Input |
| --- | --- |
| Working title | Plain-language, ≤ 70 chars |
| Primary buyer question (AEO) | One sentence — exact form a buyer would ask Perplexity or ChatGPT |
| Persona target | A · B · C · D · E |
| Funnel stage | Awareness · Consideration · Decision |
| Pillar | #1 Annex 22 · #2 FDA CSA · #3 EU AI Act · #4 HITL · #5 Founding Partner · #6 Evidence Pack |
| Primary keyword + 3–5 secondary | From Manoj's keyword research file |
| FAQ questions (≥ 4) | One-line answers — used for schema |
| Internal links (≥ 3) | Pillar page + 2 sibling cluster articles |
| External citations (≥ 3 · all primary sources) | FDA · EMA · ICH · ISPE · PDA · peer-reviewed |
| Ban-phrase check | Pass / Fail (Contractor signs) |
| Evidence-binding check | Every claim has a Public Claim Register row (Contractor signs) |
| MIRA / AI claim check | Generative-AI labeling correct (Contractor signs) |
| Annex 22 / EU AI Act framing check | "Alignment" not "compliance" (Contractor signs) |
| Schema markup | Article + FAQPage (+ HowTo if applicable) |
| Word-count band | 1,400–2,200 |
| Author + reviewed-by | Author = Droupathy / Vimal · Reviewed by Janani (technical) + Contractor (compliance) + Vimal (final A) |
| Publish date | Calendar week (anchored to GTM Launch Flow §3 swimlane) |
| Distribution plan | Newsletter · LinkedIn (Vimal + Verixa Page) · email signature · outbound asset reference |
| Measurement | Primary KPI (e.g., organic sessions 60d) · secondary (e.g., AEO snippet capture) |

# Appendix G — Pre-Publish Compliance Checklist

Reproduced from the W4 Outreach Cards + the GTM Launch Flow guardrails. Every public asset passes this checklist before going live. Owner: Contractor (R) · Vimal (A).

| # | Check | Pass Criteria |
| --- | --- | --- |
| 1 | Ban-phrase scan | Zero hits on: validated · compliant · audit-ready · inspection-ready · regulator-safe · architecturally impossible · defensible under inspection · GxP-compliant out of the box · "we saw your 483 / your deficiencies / your citation" |
| 2 | Approved phrasing used | "designed to support…" · "internally verified under our SDLC" · "the customer validates intended use" · "co-design evidence sprint" · "designed to support emerging expectations such as draft EU GMP Annex 22 — not a compliance claim" |
| 3 | Standard disclosure present | "Co-design evidence sprint. Phase 1 produces design-partner evidence artifacts, not a validated GxP production deployment. Customer validation of intended use is not included." |
| 4 | Phase 1 scope honored | Deviation → RCA → CAPA → effectiveness check → closure → evidence trail. OOS is OUT (Phase 3). |
| 5 | Phase 2/3 claims gated | No Phase 2 claims before 28 Aug G-7 + Kit. No Phase 3 / go-live claims before 01 Sep verified-go-live confirmation. |
| 6 | Public Claim Register row | Every external quantitative claim has a row in Sheet 14 with Contractor sign-off + Vimal sign-off + evidence binding. |
| 7 | Patent / IP boundary | patent-truth-qc applied. Eight India provisional patent claims are not public-disclosure material. |
| 8 | Sense7ai framing | Sense7ai = Development Partner only. Not embedded. Not white-labeled. Not a re-seller. |
| 9 | Founder credentials | Bounded by what is already in investor + DP decks. No expansion without Founder approval. |
| 10 | AI labelling | Generative AI labeled as advisory + human-review-required. Critical GMP functions described as deterministic + HITL. |
| 11 | Annex 22 / EU AI Act | "Alignment" used (not "compliance") for draft frameworks. EU AI Act compliance is NOT claimed. |
| 12 | Comparator framing | Competitor mentions bounded by the deck comparator matrix only. No new competitor claim without external counsel pre-clearance. |
| 13 | Partner-consent gate | No partner name / logo / quote / screenshot used externally without written consent in ArkOS Partner-Consent-Register. |
| 14 | Trademark usage | Verixa · ArkOS · MIRA marked TM. Third-party marks treated as third-party. |
| 15 | Privacy + data | No customer PHI / batch records / device-master data referenced. Privacy notice + cookie banner up-to-date. Unsubscribe + registered address on every email. |
| 16 | Accessibility | WCAG 2.1 AA on verixa.ai pages. |
| 17 | Schema + technical SEO | Manoj verifies schema + canonical + meta + image dimensions. |
| 18 | Final approval record | Contractor sign-off + Vimal sign-off captured in ArkOS Compliance-Review-Log with timestamp + live-URL + live-from date. |

# Appendix I — Active vs Deferred Work (Anti-Drift Reference)

Founder review pass 18 Jun added this appendix to stop the pod from reviving dropped work. If a workstream isn't in the ACTIVE column, it is not part of W3-W14 execution. If unsure, the pod defers — never the reverse.

| Workstream | Status | Notes |
| --- | --- | --- |
| ArkOS CRM build + hygiene | ACTIVE | Kavin operates · Prakash coordinates · Raja architecture sign-off |
| LinkedIn Sales Navigator (2 seats) | ACTIVE | Vimal + Droupathy daily ritual |
| Founder Outbox (vimalv@verixa.ai) | ACTIVE | Hand-crafted to 4 LIVE DP targets · Kavin logs to ArkOS |
| Calendly + Loom/Vidyard | ACTIVE | Meeting booking + async clips |
| verixa.ai + SEO/AEO/GEO | ACTIVE | Manoj · public pages held until W5 dual-gate |
| GA4 + Search Console + Ahrefs | ACTIVE | Manoj reporting only |
| n8n integration glue | ACTIVE | Kavin operates · Raja approves architecture-affecting changes |
| Newsletter (compliance-first cadence) | ACTIVE FROM W5 DUAL-GATE | Held until patent counsel clearance + compliance gate |
| Pillar pages (#1 #4) | ACTIVE FROM W5 DUAL-GATE | Drafted W3-W4 · published W5 if dual-gate passes |
| Founder LinkedIn rhythm (3×/wk) | ACTIVE FROM W5 DUAL-GATE | Droupathy first-drafts · Vimal approves · publishes from W5 if dual-gate passes |
| Webinar #1 (Annex 22) | ACTIVE — INVITES FROM W5 DUAL-GATE · LIVE W7 | Wed 15 Jul live · invites Mon 29 Jun if dual-gate passes |
| Compliance Review (claim register) | ACTIVE (Vimal interim until contractor onboarded) | Weekly Friday audit · external counsel for high-risk claims under Interim-Vimal |
| LinkedIn ABM (small budget · Verixa Page) | ACTIVE FROM W5 DUAL-GATE · creative pre-cleared by Contractor or external counsel | Held until both gates pass |
| DP target outreach (Caplin · Solara-Synthix · Cohance · SMS) | ACTIVE — 1-to-1 founder-led continuous | Pre-FD and post-FD |
| Apollo (B2B contact universe + cold-email sequencer) | DEFERRED — conditional W6 KILL-CHECK | Activate only if Sales Nav InMail volume is exhausted AND cold email becomes primary channel |
| Clay (waterfall enrichment + trigger score) | DROPPED — revisit W14+ | Not in W3-W14 stack. Manual enrichment by Janani for 4 LIVE DP targets. |
| Email warm-up vendor (Instantly / Smartlead) | DROPPED | With Apollo deferred, no bulk warm-up needed. Vimal's outbox sends hand-crafted only. |
| W6 MQL / SQL volume targets | DROPPED FROM W6 GATE | MQL/SQL are secondary KPIs (§1.4) only — never the W6 gate. Single W6 rule applies. |
| "Audit-ready" / "inspection-ready" external phrasing | BANNED — replaced | Use "structured evidence package" · "inspection-supporting evidence" · "reviewable evidence trail" instead (§5.2). |
| "OOS investigation 38%" peer example | DELETED | Unsupported claim · OOS is out of Commercial Sprint Scope · do not reference. |
| Direct "FDA CSA" blanket compliance claim | BANNED — replaced | Use "CSA-aligned risk-based assurance principles where applicable" (§5.2) · CSA scope is medical-device-led per FDA guidance (Appendix H). |
| Direct "EU AI Act high-risk Aug 2027" single date | BANNED — replaced | Use staggered timeline (§Appendix H Glossary entry) · do not state a single date in external copy without legal review. |
| AWS Mumbai / US-East data-residency claim in buyer documents | HELD — pending architecture proof from Raja + security review | Until proven: use "data residency model in design; specifics shared under NDA pending architecture confirmation" (§6.4 item 8). |
| Phase 1 used as commercial scope | BANNED — replaced with two-term distinction | Use "Product Phase 1 module set" (internal) or "Commercial design-partner sprint scope" (customer-facing) — §5.5 |
| Press release / PR splash heavier than "design-partner cohort open" | DEFERRED — until verified-go-live decision | 26 Jun PR posture reduced; bigger PR holds for Sep-01 Evidence Maturity decision |

# Appendix J — W6 KILL-CHECK Gate Sheet

Single-source reference. The pod uses this one page at the W6 KILL-CHECK · no other W6 KPI applies. Droupathy maintains this as the live W6 Gate Sheet artifact.

## Date · Mon 06 Jul 2026 · 11:00 IST

## Attendees · Vimal (decision) · Janani · Droupathy · Kavin · Manoj · Prakash · Manisha · Viji (escalation) · Contractor (or Vimal interim)

### 🟢 GREEN — proceed to W7-W14

- 1 paid design-partner sprint SIGNED · OR

- 1 priced LOI/MSA in legal with scope agreed

Action: continue plan as drafted · activate Webinar #1 · continue founder outbound + content cadence at planned volume.

### 🟡 YELLOW — proceed with discipline

- 2 qualified buyer meetings completed · AND

- Named sponsor identified · AND

- Written next step received

Action: continue plan but Vimal personally drives the next-step closure for all yellow accounts. Hold any net-new prospecting until at least one yellow converts to a priced LOI/MSA in legal. Re-test in 7 days.

### 🔴 RED — narrow scope · pause expansion

- No named sponsor · OR

- No paid scope acceptance · OR

- Buyer requires validated production claim (which we cannot make in Commercial Sprint Scope)

Action: narrow ICP to 6 high-conviction accounts. Pause broad PR / content expansion (return to founder 1-to-1 outbound posture). Activate holding template T-RECON (Appendix E). Re-baseline at the Mon 13 Jul Friday GTM sync.

### What is NOT a W6 gate

- MQL volume (any number) · SQL volume (any number) · LinkedIn follower count · webinar registration count · pillar page views · PR pickup count

All secondary KPIs (§1.4) are amplification color only. They never substitute for the single primary gate above.

# Appendix H — Glossary

| Term | Definition |
| --- | --- |
| AEO | Answer Engine Optimization — visibility in featured snippets, People-Also-Ask, voice search, AI Overviews. |
| ALCOA+ | Data integrity principles: Attributable · Legible · Contemporaneous · Original · Accurate (+ Complete · Consistent · Enduring · Available). |
| Annex 11 | EU GMP Annex 11 — Computerised Systems. |
| Annex 22 (Draft 2025) | EU GMP Annex 22 (Draft) — AI/ML in Pharmaceutical Manufacturing. Enforcement expected 2027–28. |
| ArkOS CRM | In-house Verixa CRM. Single source of truth. Replaces HubSpot. |
| CAPA | Corrective and Preventive Action. |
| CSA | Computer Software Assurance — FDA guidance covering software used in medical device production or quality system software, citing 21 CFR Part 820. Reference as "CSA-aligned risk-based assurance principles where applicable" — NOT as a blanket pharma SaaS validation rule. Applicability to a specific Verixa workflow is fact-dependent. Source: FDA CSA Final Guidance · September 2025. |
| Commercial design-partner sprint scope | Narrow commercial offering that we SELL into the paid sprint: deviation → RCA → CAPA → effectiveness check → closure → evidence trail. OOS is OUT. Used in customer-facing copy. |
| Product Phase 1 module set | Broader product scope shipping in the demo-lock + verified build: Q&A · Deviation Assessment · Risk Assessment · RCA · CAPA · Audit Readiness module · others per product manual. Used internally only — not the commercial offering. |
| Dual gate (W5 public-marketing unlock) | BOTH gates must pass on Mon 29 Jun: (a) patent counsel written clearance that intended public disclosures are covered AND (b) compliance gate: contractor onboarded OR Interim-Vimal mitigations live with external counsel retainer. |
| Interim-Vimal model | Founder decision 18 Jun 2026: if CSV/CSA + RA Contractor not hired by 30 Jun 2026, Vimal holds both first-pass + final claim review with mandatory mitigations (external counsel for high-risk claims, 60% cadence, conservative phrasing, weekly Vimal-only audit, written risk acceptance in ArkOS). |
| Structured evidence package | Replacement phrasing for "audit-ready." Used in customer-facing copy. |
| Inspection-supporting evidence | Replacement phrasing for "inspection-ready." Used in customer-facing copy. |
| Reviewable evidence trail | Replacement phrasing for either. Used in customer-facing copy. |
| DPDP 2023 | India Digital Personal Data Protection Act, 2023. |
| DP | Design Partner — paid early-customer agreement. Tiers: DP-A · DP-B · DP-C (per LOCKED Strategy). |
| DP-A | Anchor tier · Caplin / Synthix / Vimta · US$50K–US$75K Year 1 + US$25K sprint · 12+12mo · 60-day notice. |
| DP-B | First-wave India tier · Windlas / SMS · US$25K–US$40K Y1 + US$15K sprint · 12mo · 60-day exit. |
| DP-C | US Virtual Biotech tier · US$30K–US$50K Y1 + US$20K sprint · 12mo · 60-day exit. |
| EU AI Act | Regulation 2024/1689 — risk-based AI regulation. Application is staggered. General application begins 2 Aug 2026, with high-risk obligations varying by system category and implementation rules (Annex III high-risk systems → 2 Dec 2027; certain Annex I systems → 2 Aug 2028 per current EC published timeline). Do not state a single enforcement date in any external marketing claim without legal review. |
| G-7 | Supplier assurance evidence pack delivered Fri 28 Aug. |
| G-8 | Quality agreement signed at W9 (founding partner) — hard gate. |
| G-DEMO | Segregation gate ending W4 — locks demo-readiness Fri 26 Jun. |
| G-JUN | June exit Go/No-Go Tue 30 Jun. |
| GEO | Generative Engine Optimization — visibility in ChatGPT, Perplexity, Gemini, Claude. |
| HITL | Human-in-the-Loop. |
| ICP | Ideal Customer Profile. |
| KILL-CHECK | W6 binding gate (Mon 06 Jul) — ≥2 red ⇒ narrow scope or re-baseline. |
| MIRA | Verixa's natural-language query / quality copilot — advisory only. |
| MSA | Master Services Agreement — 7 LOCKED clauses non-negotiable. |
| Public Claim Register | Sheet 14 of Verixa GTM Launch Plan 2026 xlsx · auditable claim-control operating system. |
| Schedule M (2024) | India GMP requirements revised in 2024 · mandates QMS documentation at all licensed manufacturers. |
| Sense7ai | Development Partner only — not embedded · not white-labeled · not a re-seller. |
| Verifies-not-validates | Mandatory language rule: Verixa verifies its platform; the customer validates their use. |
| WCAG | Web Content Accessibility Guidelines. |

End of Marketing Plan v1.1 · 18 June 2026 · Authored by Vimal Veereshwarayya · For Extended Pod review (9 reviewers + Contractor) · Effective Mon 22 Jun 2026 upon sign-off.

Subordinate to and consistent with: Pilot Execution Plan v3 MASTER · GTM Launch Flow v2 · DP Strategy LOCKED · W4 Outreach Cards · Role Clarification Memo from Viji (18 Jun 2026). No drift. No hallucination. Inspection-grade.