## 01 · Cover & Exec Summary
VERIXA — GTM LAUNCH PLAN 2026
Aligned to engineering pilot flow · W1 (01 Jun 2026) → W14 (31 Aug 2026) · TARGET verified go-live 01 Sep 2026 · Buffer 01-15 Sep · HARD BACKSTOP 15 Sep
LANGUAGE GUARDRAIL — NON-NEGOTIABLE FOR EVERY EXTERNAL ASSET
Verixa says: "verified under our SDLC; the customer validates intended use." NEVER "validated", "certified", "Part-11 compliant", "GxP compliant" as a self-claim. MIRA = "advisory · human-in-the-loop · not system-of-record." Every claim has executed evidence + QA disposition or it is not made.
GTM POD — FIVE OWNERS
OWNER | ROLE | GTM REMIT
Vimal Veereshwarayya, PhD., RAC | Founder / CEO | Strategic narrative · founder voice · design partner closer · investor pipeline · GxP regulatory authority
Janani Rangesh | Product Manager | Demo-ready coordination · proof points · enablement kit liaison · product marketing · DP feedback loop
Droupathy | Marketing (Brand · PR · Events) | Brand voice · content editorial · PR + analyst relations · webinars · founder media bookings · case studies
Kavin | Digital Marketing | Paid · email nurture · ArkOS CRM (in-house · pipeline + outreach compliance) · Apollo sequences · marketing automation · attribution + analytics
Manoj | Website & Front-end / SEO / AEO / GEO | verixa.ai launch + iteration · schema markup · E-E-A-T signals · technical SEO · AEO/GEO for AI search visibility · landing pages · LP infra
EXTERNAL RESOURCES (FRACTIONAL / CONTRACT)
RESOURCE | DOMAIN | ROLE
CSV/CSA + RA contractor | QA · regulatory framing review | Onboard W2; reviews every external claim for Part 11 / Annex 11 / 22 / EU AI Act language
Outside legal counsel — US + India | Legal | G-8 quality agreement; design partner LOIs; DPA/MSA templates; India entity contracts
PR / analyst agency (optional) | Tier-2 pharma trade press | Bookings into PharmaSource, BioPharma Reporter, Outsourcing Pharma, Pharmaceutical Engineering (ISPE), India PharmaBiz
Design / Brand contractor | Brand | Final pitch deck polish · case study templates · investor 1-pagers · pilot evidence pack design system
Webinar / event tech | Ops | Goldcast or Zoom Events for moderated demo + analyst webinars; on24 alternative for India audience
GTM PHASING — MIRRORS ENGINEERING PHASES 1 / 2 / 3
PHASE 1 · DEMO-READY | W1 → W4 · Jun 1-26 · 🔒 HARD-LOCKED Fri 26 Jun | Brand + website soft launch · founder narrative published · ICP map locked · ABM list of 14 design-partner targets activated · Apollo + ArkOS CRM live · first 6 LOI conversations opened · 'verified vs validated' language guard everywhere
PHASE 2 · BUILD-WHILE-SELL | W5 → W13 · Jun 29 - Aug 28 | LOI signing sprint (target 2-3 signed by W6 KILL-CHECK) · founder media tour (3-5 podcasts) · 2 moderated webinars · India trade press · weekly demos to qualified ICPs · pricing live · validation enablement kit promoted · G-7 evidence pack rolling out W10-W13
PHASE 3 · VERIFIED → VALIDATE | W14+ · 01 Sep 2026 onward | Partner validation begins · public 'design partner live' announcement · founding-partner case study development · second wave LOI conversion · Series-Seed investor process opens · India investor warm intros active
CRITICAL DATES (MUST APPEAR IN EVERY GTM CALENDAR)
DATE | ENG GATE | GTM ALIGNMENT REQUIRED
Fri 26 Jun 2026 | 🔒 DEMO-READY HARD-LOCK | All demo content live · website complete · ABM activated · first 6 LOI conversations open · webinar #1 booked
Tue 30 Jun 2026 | G-JUN exit gate | GTM publishes June recap to investors + DP pipeline · webinar #1 invitations sent
Mon 06 Jul 2026 | W6 KILL-CHECK | GTM goal: 2 LOIs signed or in legal · 14 ICP accounts contacted · 200+ MQLs · paid pilot dollars committed
Fri 31 Jul 2026 | RC freeze + G-8 SIGNED | GTM goal: signed quality agreement in hand for partner #1 · public 'design partner cohort closing' communication
Mon 03 Aug 2026 | Change-control freeze | Marketing freezes new product-claim creation; only validated evidence pack messaging
Fri 28 Aug 2026 | G-7 + Enablement Kit | Partner-ready evidence pack distributed; case study #1 begins development
Tue 01 Sep 2026 | 🎯 VERIFIED GO-LIVE | PR splash: 'Verixa verified version live with founding design partner' · investor update · India pharma trade coverage
Mon 15 Sep 2026 | 🛑 HARD BACKSTOP | Any GTM commitment beyond this date converts to controlled-wave messaging; no claims of full GxP coverage
Evidence discipline: All GTM claims of regulatory alignment require executed verification evidence from engineering G-7 pack. No public marketing claim of 'validated', 'Part-11 compliant', or 'certified' is made without QA-dispositioned evidence. Every quote, screenshot, and customer reference requires written approval. India: DPDP-aware language. EU: AI Act phasing-in language (2026-2027), not Aug 2 fixed dates.

## 02 · W1-W14 GTM Swimlane
W1 → W14 GTM SWIMLANE · MIRRORS ENGINEERING BUILD FLOW · ALL DATES 2026
WORKSTREAM | OWNER | W1 Jun 01 | W2 Jun 08 | W3 Jun 15 | W4 Jun 22 | W5 Jun 29 | W6 Jul 06 | W7 Jul 13 | W8 Jul 20 | W9 Jul 27 | W10 Aug 03 | W11 Aug 10 | W12 Aug 17 | W13 Aug 24 | W14 Aug 31
POSITIONING & NARRATIVE | Vimal · Droupathy | Lock V1 messaging house | → Compliance language guard published | → Investor + DP narrative split rehearsed | → | → | Founding-partner messaging refined | → | → | → | Verified-not-validated rollout | → | → | → | Go-live narrative live
FOUNDER VOICE & PR | Vimal · Droupathy | Founder LinkedIn rhythm (3x/wk) | → | → Podcast tour booked (3-5 pods) | → → | → Op-ed published: 'Verify vs Validate' | → → | → → Analyst briefings: Gartner / IDC / IDx | → → | → → Pharma trade press placements | → → | → → | → → | → | Go-live press splash
CONTENT & EDITORIAL | Droupathy · Janani | Pillar #1: Annex 22 explainer | → | → Pillar #2: FDA CSA SaaS guide | → → | → Pillar #3: EU AI Act for pharma QMS | → → | → Pillar #4: HITL evidence patterns | → → | → → | → Pillar #5: Founding partner story | → → | → → Pillar #6: Verified evidence pack walkthrough | → → | →
WEBSITE · SEO · AEO · GEO | Manoj · Droupathy | verixa.ai soft launch (5 core pages) | → Schema markup + E-E-A-T pass | → Pillar pages + topic clusters | → → | → LP infra for paid + webinars | → → | → AEO/GEO citation engineering | → → | → → | → Resources hub + evidence pack page | → → | → | → Verified go-live landing page | →
DIGITAL MARKETING & PAID | Kavin | ArkOS CRM + Apollo + GA4 wired | → Apollo sequences live for 14 ICPs | → LinkedIn ABM ads — India + US | → → | → Email nurture seq launched (5-touch) | → → | → Webinar registration funnels | → → | → → | → Retargeting on evidence-pack viewers | → → | → → | → Go-live announcement campaign | →
DESIGN PARTNER PIPELINE (ABM) | Vimal · Janani · Kavin | 14 ICP accounts locked Founder outreach: top 14 named | → | → Demos: target 8 of 14 booked | → → | → LOI sprint: target 3-4 signed | → → | → Pilot scoping calls | → → | → → PARTNER #1 G-8 SIGNED | → Partner onboarding & co-validation | → → | → | → | Partner go-live announcement
EVENTS & WEBINARS | Droupathy · Janani |  |  | Webinar #1: 'Annex 22 for pharma' | → | → | Webinar #2: 'CSA SaaS QMS in 60 days' | → ISPE India / ISPE US meet & greets | → → | → | Webinar #3: 'Founding partner story' | → | → Roundtable: India pharma QA heads | → → | →
SALES ENABLEMENT | Janani · Vimal | Demo script + objection bank v1 | → | → Demo script v2 (post-segregation) | → → | → Pricing page + ROI calc live | → → | → Validation enablement kit (with eng) | → → | → → | → G-7 customer leverage guide | → → | → → | → Production sales kit | →
COMPLIANCE REVIEW | Vimal · CSV/CSA contractor |  | Language audit #1: all content live | → |  | Language audit #2: pre-W6 KILL | → |  | Language audit #3: pre-RC freeze | → |  |  | Language audit #4: pre-go-live | → | Final pre-launch compliance sign-off
GATES / MILESTONES | ENG + GTM |  |  |  | ◆ DEMO LOCKED | ◆ G-JUN | ◆ KILL CHECK |  |  | ◆ RC + G-8 | ◆ CC FREEZE |  |  | ◆ G-7 + KIT | ◆ VERIFIED GO-LIVE
LEGEND | Positioning / Founder voice / Compliance |  | PR / Supplier signal |  | Content / Build |  | Website / Demand gen LP |  | Paid / Digital / Pipeline |  | Hard gate / Milestone / Critical date

## 03 · RACI Matrix
RACI · R=Responsible (does the work) · A=Accountable (signs off) · C=Consulted (input required) · I=Informed (kept in loop)
ACTIVITY | Vimal Founder | Janani PM | Droupathy Marketing | Kavin Digital | Manoj Web/SEO | Contractor (CSV·Legal·PR)
STRATEGY & NARRATIVE
Messaging house v1 lock | A | C | R | I | I | C
Investor narrative + ask defense | A/R | C | C | I | I | C
Design-partner narrative + ICP map | A | R | C | C | I | C
Compliance language guardrail document | A | C | C | I | I | R
'Verified vs Validated' explainer asset | A | C | R | I | I | C
CONTENT & EDITORIAL
Content calendar Jun-Sep | C | C | A/R | C | I | I
Pillar content (6 pieces) | C | C | A/R | I | I | C
Founder LinkedIn (3x/week) | R | I | A | C | I | C
Op-ed: 'Verify vs Validate' | A/R | I | C | I | I | C
Case study #1 development | A | R | C | I | I | C
WEBSITE & SEO/AEO/GEO
verixa.ai soft launch (5 core pages) | C | C | C | C | A/R | I
Schema markup + E-E-A-T pass | I | I | C | C | A/R | I
Topic clusters + pillar pages | C | I | C | C | A/R | I
Paid + webinar LP infrastructure | I | I | C | C | A/R | I
AEO/GEO citation engineering (AI search) | I | I | C | C | A/R | I
Resources hub + evidence pack page | C | C | C | C | A/R | I
DIGITAL DEMAND GEN
ArkOS CRM · Apollo · GA4 wiring | I | I | C | A/R | C | I
Apollo sequences for 14 ICPs | C | I | C | A/R | I | I
LinkedIn ABM ads (India + US) | C | I | C | A/R | I | I
Email nurture (5-touch sequences) | I | I | C | A/R | I | I
Webinar registration funnels | I | I | C | A/R | C | I
Attribution + dashboards | I | I | C | A/R | C | I
DESIGN PARTNER PIPELINE
ICP account list (14 named) | A/R | C | C | C | I | I
Founder outreach (top 14) | A/R | I | I | C | I | I
Demo scheduling + ops | C | R | I | A | I | I
LOI conversations + close | A/R | C | I | I | I | C
Pilot scoping calls | A | R | I | I | I | C
G-8 quality agreement signing | A/R | C | I | I | I | R
EVENTS & PR
Webinar #1-3 production | C | C | A/R | C | C | C
Founder podcast bookings | C | I | A/R | I | I | C
Analyst briefings (Gartner / IDC) | A/R | C | R | I | I | C
Trade press placements | C | I | A/R | I | I | C
ISPE / India pharma meet & greets | A | R | R | I | I | C
SALES ENABLEMENT
Demo script + objection bank | C | A/R | I | I | I | I
Pricing page + ROI calc | A | R | C | C | C | I
Validation enablement kit | A | R | I | I | I | R
G-7 customer leverage guide | A | R | I | I | I | R
Production sales kit assembly | A | R | C | I | I | C
COMPLIANCE & QA
Language audit #1-4 (every 3-4 wks) | A | C | C | C | C | R
Every claim → evidence-bound check | A | C | C | C | C | R
AI/MIRA messaging review | A | C | C | C | C | R
Final pre-launch compliance sign-off | A/R | C | C | C | C | R

## 04 · Content Calendar
CONTENT CALENDAR · W1-W14 · Every asset gated by 'Verifies-not-Validates' compliance check before publish
WEEK | DATE | CHANNEL | ASSET / TITLE | FORMAT | OWNER | APPROVAL | ALIGNED TO GATE | COMPLIANCE FLAG | STATUS
W1 | Mon 01 Jun | Website | verixa.ai soft launch — Home, Product, Pilot, About, Contact | 5 pages | Manoj | Vimal | Demo-ready (W4) | High — every word | PLANNED
W1 | Tue 02 Jun | LinkedIn (Vimal) | 'Why I left QA leadership to build the AI-governed pharma QMS' | Founder post | Vimal | Droupathy | Phase 1 | Medium | PLANNED
W1 | Wed 03 Jun | Blog | Pillar #1 — 'EU GMP Annex 22 (Draft 2025) — What it changes for AI in pharma' | 2500w explainer | Droupathy | Vimal + Contractor | Phase 1 | HIGH | PLANNED
W1 | Thu 04 Jun | LinkedIn (Verixa) | Brand launch post + 6-workflow demo teaser | Carousel | Droupathy | Vimal | Phase 1 | Low | PLANNED
W1 | Fri 05 Jun | Email — Internal | Founder note to Apollo cold list (200 ICP contacts) — 'building, not selling yet' | Email seq #1 | Kavin | Vimal | Phase 1 | Medium | PLANNED
W2 | Mon 08 Jun | LinkedIn (Vimal) | 'Verify vs Validate — why this distinction matters' | Founder post | Vimal | Droupathy + Contractor | Lang audit #1 | HIGH | PLANNED
W2 | Wed 10 Jun | Blog | Pillar #2 — 'FDA CSA Final Guidance (Feb 2026) — SaaS QMS playbook' | 2500w | Droupathy | Vimal + Contractor | Phase 1 | HIGH | PLANNED
W2 | Thu 11 Jun | X / LinkedIn | Carousel: '5 things FDA CSA changes for AI in pharma QMS' | Carousel | Droupathy | Contractor | Phase 1 | HIGH | PLANNED
W2 | Fri 12 Jun | Newsletter #1 | Verixa Brief — Issue 01 — Annex 22 + CSA + design partner cohort opening | Newsletter | Droupathy | Vimal | Phase 1 | HIGH | PLANNED
W3 | Mon 15 Jun | LinkedIn (Vimal) | 'What a controlled SDLC looks like for an agentic-coded GxP system' | Founder post | Vimal | Contractor | Phase 1 | HIGH | PLANNED
W3 | Wed 17 Jun | Webinar invite | Webinar #1 — 'Annex 22 for pharma' — invite list 500+ India + US | Email + LinkedIn | Kavin | Droupathy | Phase 1 | Medium | PLANNED
W3 | Fri 19 Jun | Blog | Pillar #3 — 'EU AI Act for pharma QMS — provider vs deployer obligations' | 2500w | Droupathy | Vimal + Contractor | Phase 1 | HIGH | PLANNED
W4 | Mon 22 Jun | LinkedIn (Vimal) | 'Why I built Verixa to verify — not validate' — manifesto | Founder post | Vimal | Contractor | Demo lock | HIGH | PLANNED
W4 | Wed 24 Jun | Demo video | 6-workflow + MIRA demo cut — for ICP outreach + LP | 2-min loom | Janani | Vimal | Demo lock | HIGH | PLANNED
W4 | Thu 25 Jun | Webinar #1 | 'Annex 22 for pharma' — Vimal hosts + 1 industry guest | 60-min webinar | Droupathy | Vimal | Demo lock | HIGH | PLANNED
W4 | Fri 26 Jun | Press release | 🔒 'Verixa demo-ready — design partner cohort open' — to PharmaSource, BioPharma Reporter, PharmaBiz India | PR | Droupathy | Vimal | DEMO LOCK | HIGH | PLANNED
W5 | Mon 29 Jun | LinkedIn (Vimal) | Recap from webinar #1 — 3 takeaways for pharma QA heads | Founder post | Vimal | Droupathy | G-JUN | Medium | PLANNED
W5 | Wed 01 Jul | Newsletter #2 | Verixa Brief — Issue 02 — Demo-ready + design partner FAQ | Newsletter | Droupathy | Vimal | G-JUN | HIGH | PLANNED
W5 | Fri 03 Jul | Op-ed | 'Verify vs Validate' — submitted to Pharmaceutical Engineering (ISPE) and PharmExec | Op-ed | Vimal | Contractor | G-JUN | HIGH | PLANNED
W6 | Mon 06 Jul | Podcast #1 | Vimal on India pharma tech podcast (e.g. PharmaJet / PharmaTimes) | 60-min | Vimal | Droupathy | KILL-CHECK | HIGH | PLANNED
W6 | Wed 08 Jul | Blog | Pillar #4 — 'Human-in-the-Loop patterns for GxP AI' | 2500w | Droupathy | Vimal + Contractor | KILL-CHECK | HIGH | PLANNED
W6 | Thu 09 Jul | Case study tease | First named design partner LOI announcement (subject to consent) | LinkedIn + PR | Vimal | Partner + Contractor | KILL-CHECK | HIGH | PLANNED
W7 | Mon 13 Jul | Webinar invite | Webinar #2 — 'CSA SaaS QMS in 60 days' — invite list 800+ | Email + Ads | Kavin | Droupathy | Phase 2 | Medium | PLANNED
W7 | Wed 15 Jul | Podcast #2 | Vimal on US pharma podcast (e.g. Outsourcing Pharma) | 60-min | Vimal | Droupathy | Phase 2 | HIGH | PLANNED
W7 | Fri 17 Jul | LinkedIn (Vimal) | 'What our G-7 evidence pack looks like — and why most don't have one' | Founder post | Vimal | Contractor | Phase 2 | HIGH | PLANNED
W8 | Mon 20 Jul | LinkedIn (Verixa) | Carousel: 'Inside the validation enablement kit' | Carousel | Droupathy | Janani | Phase 2 | HIGH | PLANNED
W8 | Wed 22 Jul | Webinar #2 | 'CSA SaaS QMS in 60 days' — Vimal + DP consultant | 60-min | Droupathy | Vimal | Phase 2 | HIGH | PLANNED
W8 | Fri 24 Jul | Newsletter #3 | Verixa Brief — Issue 03 — RC freeze week + G-8 progress | Newsletter | Droupathy | Vimal | Phase 2 | HIGH | PLANNED
W9 | Mon 27 Jul | LinkedIn (Vimal) | 'Why we signed a quality agreement before go-live' | Founder post | Vimal | Contractor | RC freeze | HIGH | PLANNED
W9 | Wed 29 Jul | Blog | Pillar #5 — 'Our founding-partner playbook — how we scope a pilot' | 2500w | Droupathy | Vimal + Janani | RC freeze | HIGH | PLANNED
W9 | Fri 31 Jul | Press release | 'Verixa signs first design partner — quality agreement executed' | PR | Droupathy | Vimal + Legal | RC FREEZE + G-8 | HIGH | PLANNED
W10 | Mon 03 Aug | LinkedIn (Vimal) | 'Marketing freezes too — why we stop new claims as RC freezes' | Founder post | Vimal | Contractor | CC freeze | HIGH | PLANNED
W10 | Wed 05 Aug | Analyst briefing | Vimal briefs Gartner / IDC / similar — under NDA | Briefing | Droupathy | Vimal + Contractor | CC freeze | HIGH | PLANNED
W10 | Fri 07 Aug | Email — DP cohort | Founding partner application closing call | Email | Kavin | Vimal | CC freeze | Medium | PLANNED
W11 | Mon 10 Aug | Podcast #3 | Vimal on biotech founders podcast | 60-min | Vimal | Droupathy | Phase 2 | HIGH | PLANNED
W11 | Wed 12 Aug | LinkedIn (Vimal) | '5 things you can't claim about your QMS — and the one you can' | Founder post | Vimal | Contractor | Phase 2 | HIGH | PLANNED
W11 | Fri 14 Aug | Newsletter #4 | Verixa Brief — Issue 04 — Verification status snapshot | Newsletter | Droupathy | Vimal + Janani | Phase 2 | HIGH | PLANNED
W12 | Mon 17 Aug | LinkedIn (Verixa) | 'Inside the G-7 evidence pack' — walkthrough series part 1 | Carousel | Droupathy | Janani | Phase 2 | HIGH | PLANNED
W12 | Wed 19 Aug | Webinar #3 | 'Founding partner story' — Vimal + named partner (subject to consent) | 60-min | Droupathy | Vimal + Partner | Phase 2 | HIGH | PLANNED
W12 | Fri 21 Aug | Blog | Pillar #6 — 'Inside our verified evidence pack' (post-cleared) | 2500w | Janani | Vimal + Contractor | Phase 2 | HIGH | PLANNED
W13 | Mon 24 Aug | LinkedIn (Vimal) | 'Why I'm proud to ship a pack we can defend' — pre-go-live note | Founder post | Vimal | Contractor | G-7 | HIGH | PLANNED
W13 | Wed 26 Aug | Demo video | Verified version + G-7 evidence pack walkthrough — 3-min loom | Loom | Janani | Vimal | G-7 | HIGH | PLANNED
W13 | Thu 27 Aug | Roundtable | India pharma QA heads roundtable — invitation only — Vimal hosts | Roundtable | Droupathy | Vimal | G-7 | HIGH | PLANNED
W13 | Fri 28 Aug | Press release | 'Verixa enablement kit + G-7 evidence pack delivered to design partner' | PR | Droupathy | Vimal + Legal | G-7 + KIT | HIGH | PLANNED
W14 | Mon 31 Aug | Internal | Final compliance sign-off — Vimal + contractor | Audit | Vimal | Contractor | GO-LIVE -1d | HIGH | PLANNED
W14 | Tue 01 Sep | 🎯 PR splash | 'Verixa verified version live with founding design partner' — multi-outlet | PR + LinkedIn + Email | Droupathy | Vimal + Legal | VERIFIED GO-LIVE | HIGH | PLANNED
W14 | Tue 01 Sep | Newsletter #5 | Verixa Brief — Issue 05 — GO-LIVE special | Newsletter | Droupathy | Vimal | GO-LIVE | HIGH | PLANNED
W14 | Wed 02 Sep | Investor update | Series-Seed teaser to warm investor list (US + India) | Email + 1-pager | Vimal | Contractor | GO-LIVE +1d | HIGH | PLANNED
W14 | Fri 04 Sep | Founder reflection | Vimal LinkedIn long-form — 'The 14 weeks that built Verixa' | Founder post | Vimal | Droupathy | GO-LIVE +3d | HIGH | PLANNED

## 05 · DP Pipeline (14)
DESIGN PARTNER PIPELINE · 14 NAMED ICP ACCOUNTS · ABM TARGETS — populated weekly · Vimal owns close
# | ACCOUNT | REGION | ICP TYPE | PRIMARY CONTACT | STAGE | LOI STATUS | DEMO DATE TARGET | NEXT STEP | OWNER | PRIORITY | NOTES
1 | [Named CDMO #1 — India] | India | CDMO · 200-1000 staff · Export-oriented | VP Quality | Identify | — | W4-W5 | Outreach via Vimal LinkedIn + warm intro | Vimal | P0 | Schedule M re-classification driver
2 | [Named Mid Pharma #1 — India] | India | Mid pharma · multi-site · 500-2000 staff | Head of QA | Identify | — | W4-W5 | Apollo sequence + Janani demo book | Vimal | P0 | Multi-site GMP — Verixa control plane fit
3 | [Named CDMO #2 — India] | India | CDMO · Cell/gene therapy adjacent | VP Reg / VP Q | Identify | — | W5-W6 | Founder warm intro via ISPE India network | Vimal | P0 | CGT-adjacent — high CSV maturity
4 | [Named US Biotech #1] | US | Clinical-stage biotech · 100-300 staff · Phase 2/3 | VP Quality | Identify | — | W5-W6 | Outreach via Vimal Arcellx/Alumis network | Vimal | P0 | Building QMS de novo — Verixa native AI angle
5 | [Named US Biotech #2] | US | Commercial-stage biotech · 300-800 staff | Head of QA Ops | Identify | — | W5-W6 | Outreach via founder warm intro | Vimal | P0 | Replacing legacy eQMS — Veeva displacement pitch
6 | [Named India CRO] | India | CRO · clinical trials + bioanalytical | Head of Quality | Identify | — | W5-W7 | Vimal cold intro + LinkedIn | Vimal | P1 | GCP module wedge — adjacent to GMP focus
7 | [Named India Mid Pharma #2] | India | Generic pharma · 1000+ staff · USFDA inspected | VP Q+RA | Identify | — | W5-W7 | Apollo + Kavin nurture | Vimal | P1 | USFDA-inspected — needs CSA-ready posture
8 | [Named Specialty Pharma — India] | India | Specialty biologics · 300-700 staff | Head of QA | Identify | — | W5-W7 | Vimal warm intro via mentor network | Vimal | P1 | Biologics — high CSV scrutiny
9 | [Named US Pharma Services] | US | Pharma services org · 200-500 staff | Director QA | Identify | — | W6-W8 | Apollo + LinkedIn ABM ad sequence | Janani | P1 | Services - QMS as service-enablement
10 | [Named US Specialty CDMO] | US | CDMO · sterile injectable | VP Q / CSV Lead | Identify | — | W6-W8 | Founder intro via mentor | Vimal | P1 | Sterile = high stakes; verification rigor demanded
11 | [Named EU/India Hybrid Biotech] | India + EU | Cross-border biotech · 100-300 staff | Head of QA | Identify | — | W6-W8 | Outreach via Vimal EU pharma network | Vimal | P2 | Dual-jurisdiction QMS need
12 | [Named India Generic Pharma] | India | Generic pharma · 500-1500 staff | VP QC + RA | Identify | — | W7-W9 | Kavin Apollo seq + Janani demo book | Janani | P2 | Generics — CSA + cost story
13 | [Named US Cell Therapy] | US | Cell therapy · pre-commercial · 50-150 staff | Head of Q | Identify | — | W7-W9 | Founder intro via Arcellx alumni | Vimal | P2 | Cell therapy adjacency — early but strategic
14 | [Named India MedTech-Pharma hybrid] | India | Medical device + pharma hybrid · 200-400 staff | Head of QARA | Identify | — | W7-W9 | Vimal LinkedIn + warm intro | Janani | P2 | Cross-vertical — possible Ketryx-adjacent comp
PIPELINE GOALS BY GATE
W4 Demo lock (26 Jun) | 14 ICP accounts contacted · 6+ first conversations · 2-3 demos booked
W6 KILL-CHECK (06 Jul) | 8 demos delivered · 2 LOIs signed or in legal · G-8 in legal review with at least one
W9 RC freeze (31 Jul) | 3-4 LOIs signed · 1 G-8 quality agreement SIGNED (founding partner) · 2 active pilot scoping calls
W13 G-7 ready (28 Aug) | Founding partner onboarded to verification evidence pack · 2nd partner in legal · case study #1 development
W14 Go-Live (01 Sep) | 1 partner LIVE (verified, partner-validating) · 2-3 partners in active pilot scoping · 1 EU/US lead in flight

## 06 · Asset Inventory
ASSET INVENTORY · DECKS · 1-PAGERS · COLLATERAL · WEBSITE PAGES · COMPLIANCE-REVIEWED ARTIFACTS
CATEGORY | ASSET NAME | VERSION / STATUS | OWNER | INTENDED AUDIENCE | TARGET WEEK | LOCATION / NOTES
PITCH DECK | US Investor Deck v7.1 | DELIVERED · v7.1 | Vimal | US VCs · seed/series A | W0 | verixa_plan/decks/verixa_investor_deck_v7.1.pptx
PITCH DECK | India Investor Deck v7.1-IN | DELIVERED · v7.1-IN | Vimal | India VCs (Blume, Chiratae, Kalaari, HealthQuad, Stellaris) | W0 | verixa_plan/decks/verixa_investor_deck_v7.1_IN.pptx
PITCH DECK | US Design Partner Deck v3.2-US | DELIVERED · v3.2-US | Vimal | US biotech / pharma DP prospects | W0 | verixa_plan/decks/verixa_design_partner_deck_v3.2_US.pptx
PITCH DECK | India Design Partner Deck v3.3-IN | DELIVERED · v3.3-IN | Vimal | India CDMO / mid-pharma DP prospects | W0 | verixa_plan/decks/verixa_design_partner_deck_v3.3_IN.pptx
PITCH DECK | Internal Investor Playbook | PENDING | Vimal | Internal — investor FAQ + objection bank | W2 | PPTX exec + DOCX FAQ bank (40-60 pages)
PITCH DECK | Internal Design Partner Playbook | PENDING | Vimal | Internal — per-account operator manual | W3 | PPTX exec + DOCX per-account manual for 14 ICPs
1-PAGER | Verixa product 1-pager (US) | PENDING | Droupathy | All external prospects | W2 | PDF + PPTX — 1 page; print + digital
1-PAGER | Verixa product 1-pager (India) | PENDING | Droupathy | India prospects · INR pricing | W2 | PDF + PPTX — 1 page; print + digital
1-PAGER | Verify vs Validate explainer | PENDING | Droupathy + Contractor | All external — language guardrail proof | W2 | PDF · pillar asset for every meeting
1-PAGER | Annex 22 / EU AI Act readiness brief | PENDING | Vimal + Contractor | Pharma QA heads (India + EU) | W3 | PDF · trade press companion
1-PAGER | FDA CSA SaaS QMS brief | PENDING | Vimal + Contractor | US pharma QA + reg | W3 | PDF · webinar companion
1-PAGER | Founding Partner program (founding-partner card) | PENDING | Vimal + Janani | First 2-3 DP prospects | W2 | PDF · pricing + sweeteners + commitments
1-PAGER | Validation enablement kit TOC | PENDING | Janani | DP prospects · auditors | W7 | PDF · what they get when they sign
1-PAGER | G-7 Evidence Pack TOC | PENDING | Janani + Contractor | DP prospects · their auditors | W10 | PDF · 13-section index
WEBSITE | Home page (verixa.ai) | PENDING | Manoj + Droupathy | All visitors | W1 | Hero + value prop + DP CTA + founder note
WEBSITE | Product page | PENDING | Manoj + Janani | All visitors | W1 | 6-workflow map + MIRA · 'verifies' language
WEBSITE | Pilot / Design Partner page | PENDING | Manoj + Vimal | ICP prospects | W1 | Phase 0/1/2 conversion path · application form
WEBSITE | About / Founder page | PENDING | Manoj + Droupathy | All visitors | W1 | Vimal bio · team · India + US entity
WEBSITE | Contact + DP application form | PENDING | Manoj + Kavin | All visitors | W1 | ArkOS CRM form · routes to founder + Janani
WEBSITE | Pillar: Annex 22 explainer | PENDING | Manoj + Droupathy | Pharma QA leads (SEO) | W2 | Long-form · schema · pillar topic cluster
WEBSITE | Pillar: FDA CSA SaaS guide | PENDING | Manoj + Droupathy | US pharma (SEO) | W3 | Long-form · schema · downloads
WEBSITE | Pillar: EU AI Act for pharma QMS | PENDING | Manoj + Droupathy | EU + global pharma (SEO) | W4 | Long-form · schema · downloads
WEBSITE | Resources hub | PENDING | Manoj + Droupathy | All — content library | W5 | Blog · whitepapers · webinars · LP infra
WEBSITE | Webinar registration LPs (x3) | PENDING | Manoj + Kavin | Webinar attendees | W3/W7/W12 | ArkOS CRM-integrated · LinkedIn pixel
WEBSITE | Evidence pack page | PENDING | Manoj + Janani | Qualified DP prospects | W10 | Gated PDF · G-7 TOC + leverage guide
WEBSITE | GO-LIVE landing page | PENDING | Manoj + Droupathy | Press + investors + prospects | W14 | Verified version live + DP announcement
SALES | Demo script v2 (post-segregation) | PENDING | Janani + Vimal | Internal — Vimal · Janani | W3 | DOCX · 6-workflow + MIRA · 30-min flow
SALES | Objection bank v2 | PENDING | Janani + Vimal | Internal — Vimal | W4 | DOCX · top 30 objections with responses
SALES | Pricing page + ROI calc | PENDING | Vimal + Janani + Kavin | DP prospects + investors | W5 | Web page + XLSX calc
SALES | LOI template (US) | PENDING | Vimal + Legal | US DP prospects | W3 | DOCX · counsel-reviewed
SALES | LOI template (India) | PENDING | Vimal + India Legal | India DP prospects | W3 | DOCX · India counsel-reviewed
SALES | DPA / MSA templates | PENDING | Legal + Vimal | All DP prospects | W5 | DOCX · DPDP + GDPR + HIPAA-aware
SALES | G-8 quality agreement template | PENDING | Legal + Vimal + Contractor | DP prospects | W2 (draft) · W9 (signed) | DOCX · 10-clause minimum
PR | Press release: Demo-ready (26 Jun) | PENDING | Droupathy | Trade press · India + US | W4 | DOCX + distribution list
PR | Press release: G-8 signed (31 Jul) | PENDING | Droupathy | Trade press | W9 | DOCX (contingent on partner consent)
PR | Press release: G-7 + kit delivered (28 Aug) | PENDING | Droupathy | Trade press | W13 | DOCX
PR | Press release: GO-LIVE (01 Sep) | PENDING | Droupathy + Vimal | Multi-outlet · India + US + EU | W14 | DOCX + analyst briefing pre-release
PR | Founder bio + headshot kit | PENDING | Droupathy + Vimal | Media · podcasts · analysts | W1 | DOCX + JPG kit
PR | Analyst briefing deck | PENDING | Vimal + Droupathy | Gartner · IDC · IDC Health | W7 | PPTX · NDA-only
DIGITAL | Newsletter template (ArkOS CRM) | PENDING | Kavin + Droupathy | Subscribers | W1 | HTML · brand-aligned
DIGITAL | LinkedIn carousel template | PENDING | Droupathy + Manoj | LinkedIn audience | W1 | Figma · 8-slide template
DIGITAL | Webinar landing page template | PENDING | Manoj + Kavin | Webinar registrants | W2 | Webflow · ArkOS CRM integration
DIGITAL | Apollo sequence templates (US + India) | PENDING | Kavin + Vimal | ICP outreach | W2 | Apollo · 5-touch sequences
DIGITAL | Brand kit (logos · colors · type) | PENDING | Droupathy + Manoj | Internal + partners | W1 | Figma · ZIP package

## 07 · Digital Plan (Kavin)
DIGITAL MARKETING PLAN · OWNER: KAVIN · ALIGNED TO ENG W1-W14
WORKSTREAM | INITIATIVE | START WK | END WK | CHANNEL / TOOL | KPI / GOAL | COMPLIANCE NOTE
INFRASTRUCTURE | ArkOS CRM workspace setup — US + India tenants · pipeline-hygiene + outreach-compliance rules live | W1 | W2 | ArkOS CRM | Live by Fri W2 · 14 ICPs loaded · rules active | DPDP-aware India tenant
INFRASTRUCTURE | Apollo.io seat + sequence framework | W1 | W2 | Apollo | 5 sequence templates live W2 | Email opt-out compliant
INFRASTRUCTURE | GA4 + GTM + Hotjar (or Microsoft Clarity) | W1 | W2 | GA4 / GTM | Site instrumented W2 | Consent banner live
INFRASTRUCTURE | LinkedIn Insight Tag + Campaign Manager | W1 | W2 | LinkedIn | Conversion tracking live W2 | Privacy policy linked
INFRASTRUCTURE | Attribution model (first-touch + multi-touch) | W2 | W3 | ArkOS CRM + GA4 | Model live W3 with reports | —
CRM + DATA | 14 ICP accounts imported with enriched contacts | W1 | W2 | ArkOS CRM + Apollo | 200+ contacts loaded by W2 | Source-tracking for DPDP
CRM + DATA | Lead scoring model live | W2 | W3 | ArkOS CRM | Model live W3 | —
CRM + DATA | Pipeline reports for Vimal + Janani | W2 | W14 | ArkOS CRM dashboards | Weekly cadence | —
CRM + DATA | Apollo signal sync (job changes, funding) | W2 | W14 | Apollo + ArkOS CRM | Daily signal feed | —
EMAIL NURTURE | Cold sequence #1: India CDMO (5-touch) | W2 | W6 | Apollo | 300 contacts · 5% reply rate target | DPDP opt-in
EMAIL NURTURE | Cold sequence #2: India mid-pharma (5-touch) | W2 | W6 | Apollo | 300 contacts · 5% reply target | DPDP opt-in
EMAIL NURTURE | Cold sequence #3: US biotech (5-touch) | W3 | W7 | Apollo | 200 contacts · 5% reply target | CAN-SPAM compliant
EMAIL NURTURE | Cold sequence #4: US CDMO (5-touch) | W3 | W7 | Apollo | 150 contacts · 5% reply target | CAN-SPAM compliant
EMAIL NURTURE | Founder note sequence (Vimal voice) — warm contacts | W4 | W10 | Apollo + ArkOS CRM | 100 warm contacts · 15% reply target | Approved by Vimal
EMAIL NURTURE | Newsletter — biweekly · Verixa Brief (Issues 01-05) | W1 | W14 | ArkOS CRM | 5 issues · open rate >40% · CTR >5% | Compliance reviewed
EMAIL NURTURE | Webinar invite sequences (3 webinars × 4-touch each) | W3 | W12 | ArkOS CRM | 300-500 registrants per webinar | Approved language
PAID — LINKEDIN | ABM ads to 14 ICP companies (named-account ads) | W3 | W14 | LinkedIn Campaign Mgr | ₹5L total · 50K impressions to ICP | Approved creative
PAID — LINKEDIN | Sponsored content boost — Vimal founder posts | W4 | W14 | LinkedIn | ₹3L total · 30K impressions | Founder approved
PAID — LINKEDIN | Lead-gen forms for pillar content | W5 | W14 | LinkedIn | ₹3L · 300+ MQLs | Privacy compliant
PAID — GOOGLE | Search ads — 'eQMS for pharma' / 'AI QMS' terms (US + India) | W4 | W14 | Google Ads | ₹4L · 200+ qualified clicks | No false claims
PAID — GOOGLE | Display retargeting (site visitors) | W4 | W14 | Google Ads | ₹2L · 10x reach to engaged | —
PAID — X | Founder voice amplification (Vimal + Verixa) | W4 | W14 | X (formerly Twitter) | ₹1L · 20K impressions | Founder approved
ABM PROGRAMS | Named-account intent monitoring (e.g. via Common Room) | W2 | W14 | Common Room or 6sense | All 14 monitored W2 | —
ABM PROGRAMS | Personalized 1-pagers for top 6 ICPs | W4 | W7 | ArkOS CRM + design | 6 ICPs · 1 each | Approved
ABM PROGRAMS | Direct mail to top 6 ICPs (US India both) | W6 | W8 | Printed kit + courier | 6 packages · 100% delivery | —
ANALYTICS | Weekly KPI dashboard for Vimal + Janani | W3 | W14 | ArkOS CRM + Looker Studio | Friday cadence | —
ANALYTICS | Monthly attribution report | W4 | W14 | ArkOS CRM | Last day of month | —
ANALYTICS | Pipeline conversion funnel report | W6 | W14 | ArkOS CRM | Weekly | —
ANALYTICS | Post-go-live performance review (W14) | W14 | W14 | All tools | Issued W14 Friday | —

## 08 · Website + SEO (Manoj)
WEBSITE · SEO · AEO · GEO PLAN · OWNER: MANOJ · ALIGNED TO ENG W1-W14
WORKSTREAM | DELIVERABLE | TARGET WK | STACK / TOOL | SEO/AEO/GEO TARGET | SUCCESS METRIC | NOTES
CORE WEBSITE | Domain + DNS + SSL on verixa.ai | W1 | Cloudflare / Vercel | Brand | Live W1 · LCP <2.5s | Aligned with brand kit
CORE WEBSITE | Home page (hero, value prop, DP CTA) | W1 | Webflow or Next.js | Brand SEO | Live W1 · published | Founder note prominent
CORE WEBSITE | Product page (6 workflows + MIRA) | W1 | Webflow / Next.js | 'pharma eQMS' / 'AI QMS' | Live W1 | 'Verifies' language only
CORE WEBSITE | Design Partner / Pilot page | W1 | Webflow / Next.js | 'pharma QMS pilot' / 'design partner' | Live W1 · 6 applications W4 | Phase 0/1/2 conversion path
CORE WEBSITE | About / Founder page | W1 | Webflow / Next.js | 'Vimal Veereshwarayya' branded | Live W1 | Vimal full bio · India + US
CORE WEBSITE | Contact + DP application form | W1 | ArkOS CRM embed | Conversion | Live W1 · 6 applications W4 | Routes to Vimal + Janani
SCHEMA + E-E-A-T | Organization schema markup | W2 | JSON-LD | All | Validated in GSC W2 | Includes both entities
SCHEMA + E-E-A-T | Person schema (Vimal) + author markup | W2 | JSON-LD | Vimal branded | Validated W2 | PhD + RAC credentials
SCHEMA + E-E-A-T | Article schema on all blog posts | W2 | JSON-LD | All blog SEO | Validated W2 | —
SCHEMA + E-E-A-T | FAQPage schema on pillar pages | W3 | JSON-LD | AEO target | Validated W3 | Aids AI search citations
SCHEMA + E-E-A-T | BreadcrumbList on all pages | W2 | JSON-LD | SEO | Validated W2 | —
SCHEMA + E-E-A-T | E-E-A-T proof (credentials · publications · bio) | W2 | Page content | Vimal authority | Live W2 | Founder photos + creds visible
PILLAR + CLUSTERS | Pillar #1 — Annex 22 explainer (2500w) | W2 | Next.js / Webflow | 'EU GMP Annex 22' / 'AI pharma manufacturing' | Rank top-10 by W8 | Long-form · downloads
PILLAR + CLUSTERS | Pillar #2 — FDA CSA SaaS playbook (2500w) | W3 | Same | 'FDA CSA SaaS' / 'CSA pharma QMS' | Rank top-10 by W9 | Downloads gated
PILLAR + CLUSTERS | Pillar #3 — EU AI Act pharma (2500w) | W4 | Same | 'EU AI Act pharma' / 'AI Act QMS' | Rank top-10 by W10 | Downloads
PILLAR + CLUSTERS | Pillar #4 — HITL patterns for GxP AI (2500w) | W6 | Same | 'Human in the loop AI GxP' / 'AI governance pharma' | Rank top-10 by W12 | Diagrams
PILLAR + CLUSTERS | Pillar #5 — Founding partner playbook (2500w) | W9 | Same | 'pharma QMS pilot' / 'design partner pharma' | Rank top-10 by W14 | Lead-gen anchor
PILLAR + CLUSTERS | Pillar #6 — Inside the evidence pack (2500w) | W12 | Same | 'pharma QMS evidence pack' / 'supplier assurance pharma' | Rank top-10 by W16 | Post-go-live
PILLAR + CLUSTERS | Topic cluster pages (5 per pillar) | W3 | Same | Long-tail SEO | 30 cluster pages by W12 | Each links to pillar
AEO / GEO | Citation engineering — be cited by ChatGPT / Perplexity / Gemini | W4 | Content + schema | AI search visibility | Cited in 3+ AI search by W10 | Stats + framing + author authority
AEO / GEO | Long-tail Q&A content (FAQ format) | W4 | Webflow + schema | AEO featured snippets | 5 snippets by W10 | Schema markup essential
AEO / GEO | Structured data on every page (Article + FAQ + Howto) | W3 | JSON-LD | AI search ingestion | 100% pages by W4 | —
AEO / GEO | Submit to AI search indexes (IndexNow + Sitemaps) | W2 | Sitemap + IndexNow | All search engines | Live W2 | Includes Bing + ChatGPT
AEO / GEO | Strategic guest posts / mentions for authority signals | W6 | Outreach | Domain authority | 5 backlinks by W12 | Industry sites preferred
PERFORMANCE + UX | Core Web Vitals — LCP <2.5s · CLS <0.1 · INP <200ms | W2 | Next.js + CDN | Technical SEO | All passing W2 | Monitor weekly
PERFORMANCE + UX | Mobile-first responsive | W1 | Webflow / Next.js | Mobile SEO | Validated W1 | Test on India 4G
PERFORMANCE + UX | Accessibility (WCAG 2.1 AA) | W2 | axe-core audit | Conversion + brand | Pass W2 | —
LP INFRA | Webinar #1 LP (Annex 22 — W5) | W3 | Webflow + ArkOS CRM | Conversion | 300+ regs by W4 | LinkedIn pixel
LP INFRA | Webinar #2 LP (CSA SaaS — W8) | W6 | Same | Conversion | 500+ regs by W7 | LinkedIn + Google pixels
LP INFRA | Webinar #3 LP (Founding partner story — W12) | W10 | Same | Conversion | 500+ regs by W11 | All pixels
LP INFRA | Evidence pack download LP (gated) | W11 | Same | Lead capture | Live W11 · 100+ qualified DLs by W14 | G-7 TOC + leverage guide
LP INFRA | Founder Partner application LP (separate from main DP page) | W4 | Same | Conversion | 10+ applications by W9 | Routes to Vimal
RESOURCES HUB | Blog / Resources hub launched | W5 | Webflow | SEO | Live W5 with 5 posts | —
RESOURCES HUB | Webinar replay library | W6 | Webflow | Long-tail SEO | Live W6 | Gated by webinar #
RESOURCES HUB | Whitepapers / 1-pagers library | W6 | Webflow | Lead gen | Live W6 | Gated
RESOURCES HUB | Newsletter archive | W7 | Webflow | SEO + retention | Live W7 | —
GO-LIVE PAGE | Verified version live landing (W14) | W14 | Webflow / Next.js | Brand + investor | Live 01 Sep 00:01 IST | PR companion

## 09 · PR + Events (Droupathy)
PR · EVENTS · FOUNDER BRAND · OWNER: DROUPATHY (Vimal voice)
WORKSTREAM | INITIATIVE | TARGET WK | CHANNEL / OUTLET | FORMAT | SUCCESS METRIC | COMPLIANCE NOTE
FOUNDER VOICE | Vimal LinkedIn — Mon/Wed/Fri rhythm | W1-W14 | LinkedIn | Founder posts | 42+ posts · 200K+ impressions | Each post pre-reviewed for claims
FOUNDER VOICE | Vimal LinkedIn — long-form (monthly) | W2/W6/W10/W14 | LinkedIn Articles | Long-form | 4 articles · 50K+ impressions each | Compliance reviewed
FOUNDER VOICE | Vimal X / Twitter rhythm (2x/wk) | W1-W14 | X | Founder posts | 28 posts · 50K+ impressions | Same review process
FOUNDER VOICE | Vimal newsletter on LinkedIn | W2-W14 | LinkedIn Newsletter | Newsletter | 5 issues · 500+ subscribers W14 | Compliance reviewed
PODCAST TOUR | Podcast #1 — India pharma tech podcast | W6 | Podcast | 60-min | Live by W6 · 10K+ listens | Approved talking points
PODCAST TOUR | Podcast #2 — US pharma podcast (Outsourcing Pharma / equivalent) | W7 | Podcast | 60-min | Live by W7 · 5K+ listens | Approved talking points
PODCAST TOUR | Podcast #3 — Biotech founders podcast | W11 | Podcast | 60-min | Live by W11 · 5K+ listens | Approved talking points
PODCAST TOUR | Podcast #4 — India biotech / pharma founders | W12 | Podcast | 60-min | Live by W12 · 8K+ listens | Approved
PODCAST TOUR | Podcast #5 — AI in regulated industries | W13 | Podcast | 60-min | Live by W13 · 8K+ listens | Approved
OP-EDS | Op-ed #1 — 'Verify vs Validate' — ISPE Pharmaceutical Engineering | W5 | Trade journal | Op-ed | Published W5 | Multiple rounds review
OP-EDS | Op-ed #2 — 'Annex 22 + India pharma' — PharmaBiz / Express Pharma India | W7 | India trade | Op-ed | Published W7 | Reviewed
OP-EDS | Op-ed #3 — 'Why founders should build verifiable systems' — TechCrunch / VentureBeat | W10 | Tech press | Op-ed | Published W10 | Reviewed
OP-EDS | Op-ed #4 — 'AI Act for pharma — what providers must own' — BioPharma Reporter | W12 | Trade | Op-ed | Published W12 | Reviewed
PRESS | PR #1 — Verixa Demo-Ready · Design Partner cohort open (W4) | W4 | PharmaSource · BioPharma Reporter · PharmaBiz India · Outsourcing Pharma | PR | 5+ pickups | Reviewed
PRESS | PR #2 — First Quality Agreement signed (W9, partner consent contingent) | W9 | Same outlets | PR | 5+ pickups | Reviewed + partner approved
PRESS | PR #3 — Evidence pack + Enablement kit delivered (W13) | W13 | Same outlets | PR | 5+ pickups | Reviewed
PRESS | PR #4 — Verified version GO-LIVE with founding partner (W14) | W14 | Multi-outlet · India + US + EU + tech | PR | 10+ pickups · 1+ analyst mention | Reviewed + partner approved
ANALYSTS | Briefing — Gartner (Pharma + AI Governance practice) | W7 | Briefing | NDA call | Briefing W7 · 1 follow-up | Reviewed
ANALYSTS | Briefing — IDC Health / IDC Life Sciences | W8 | Briefing | NDA call | Briefing W8 · 1 follow-up | Reviewed
ANALYSTS | Briefing — Industry-specific: Pharma IQ / Pharma Manufacturer Magazine | W9 | Briefing | Call | Briefing W9 | Reviewed
ANALYSTS | Briefing — India-specific: BIRAC / DBT / IPA tech advisory | W10 | Briefing | Call | Briefing W10 | Reviewed
EVENTS | Webinar #1 — Annex 22 for pharma (W5 host) | W5 | Goldcast / Zoom | 60-min | 300+ registrants · 100+ live | Approved
EVENTS | Webinar #2 — CSA SaaS QMS in 60 days (W8 host) | W8 | Goldcast / Zoom | 60-min | 500+ registrants · 150+ live | Approved
EVENTS | Webinar #3 — Founding partner story (W12 host) | W12 | Goldcast / Zoom | 60-min | 500+ registrants · 200+ live | Partner approved
EVENTS | ISPE India networking event (W7-W8 window) | W7-W8 | ISPE India local event | Networking | 20+ connections · 3+ DP leads | —
EVENTS | Roundtable — India pharma QA heads (W13 invitation-only) | W13 | Hosted dinner / online | Roundtable (12 attendees) | 12 invited · 8+ attend | Approved
EVENTS | GO-LIVE event — Sept 1 launch livestream + Q&A | W14 | LinkedIn Live | Live event | 500+ live · 2K+ replay | Approved
CASE STUDY | Case study #1 development — founding partner | W10-W14 | Internal + partner consent | PDF + LP + video | Drafted W14 · published W16 | Multiple legal reviews
CASE STUDY | Founding partner video testimonial (W14+) | W14+ | Production company | 2-min video | Published W16 | Reviewed

## 10 · KPI Dashboard
KPI DASHBOARD · WEEKLY CADENCE · Friday review with Vimal · Pipeline + Marketing + Compliance
PIPELINE KPIs (Vimal + Janani own)
METRIC | W4 TARGET | W6 TARGET | W9 TARGET | W14 TARGET | ACTUAL | NOTES
ICP accounts contacted (of 14) | 14 | 14 | 14 | 14 | — | All 14 named ICPs reached
First conversations held | 6 | 10 | 12 | 14 | — | Founder + Janani
Demos delivered | 3 | 8 | 10 | 12 | — | Janani schedule
LOIs signed | 0 | 2 | 3-4 | 4-5 | — | Vimal close
G-8 quality agreements signed | 0 | 0 (draft only) | 1 | 2 | — | First by W9 RC freeze
Pilot scoping calls active | 0 | 1 | 3 | 5 | — | Post-LOI
Partners live (verified version) | 0 | 0 | 0 | 1 | — | Founding partner W14
Founding-partner application form submissions | 5 | 15 | 25 | 35 | — | DP application form
MARKETING KPIs (Droupathy + Kavin own)
METRIC | W4 TARGET | W6 TARGET | W9 TARGET | W14 TARGET | ACTUAL | NOTES
Website unique visitors (monthly) | 1,500 | 3,000 | 6,000 | 12,000 | — | GA4
Newsletter subscribers | 100 | 300 | 600 | 1,000 | — | ArkOS CRM
Newsletter open rate | — | >40% | >40% | >40% | — | Industry avg 22%
LinkedIn impressions (Vimal + Verixa pages) | 30K | 75K | 150K | 300K | — | LinkedIn analytics
LinkedIn followers (Verixa company page) | 200 | 500 | 1,000 | 2,000 | — | —
Pillar content rank — top 10 SERP keywords | 0 | 1 | 2 | 4 | — | Ahrefs / SEMrush
AEO citations (mentioned in AI search responses) | 0 | 1 | 2 | 5+ | — | Manual tracking
Webinar registrations cumulative | 300 | 300 | 800 | 1,500 | — | All 3 webinars
MQLs generated | 30 | 100 | 250 | 500 | — | ArkOS CRM scoring
SQLs accepted by sales | 5 | 20 | 50 | 100 | — | Vimal + Janani accept
Domain authority (Ahrefs DR) | — | 10+ | 20+ | 30+ | — | Baseline today: ~0
CONTENT & EDITORIAL KPIs (Droupathy owns)
METRIC | W4 TARGET | W6 TARGET | W9 TARGET | W14 TARGET | ACTUAL | NOTES
Pillar content published (of 6) | 2 | 3 | 5 | 6 | — | On schedule
Founder LinkedIn posts (Vimal) | 12 | 18 | 27 | 42 | — | Mon/Wed/Fri rhythm
Op-eds published (of 4) | 0 | 1 | 2 | 4 | — | Trade press
Press releases issued (of 4) | 1 | 1 | 2 | 4 | — | Aligned to gates
Podcast appearances (of 5) | 0 | 1 | 2 | 5 | — | Founder voice
Case study #1 in development | — | — | Begin | Drafted | — | Partner consent
COMPLIANCE KPIs (Vimal + Contractor own — non-negotiable)
METRIC | W4 TARGET | W6 TARGET | W9 TARGET | W14 TARGET | ACTUAL | NOTES
Language audits passed (of 4 scheduled) | 1 | 2 | 3 | 4 | — | W3 / W6 / W9 / W13
External claims violating language guard | 0 | 0 | 0 | 0 | — | ZERO TOLERANCE
Claims with evidence backing (% of all claims) | 100% | 100% | 100% | 100% | — | —
MIRA / AI claims reviewed by AI Owner | 100% | 100% | 100% | 100% | — | All AI claims
Partner case-study claims pre-approved by partner legal | — | — | — | 100% | — | Once partner LIVE
Investor 1-pager claims sourced + dated | — | 100% | 100% | 100% | — | Every number cited

## 11 · Language Guard
COMPLIANCE LANGUAGE GUARD — NON-NEGOTIABLE FOR EVERY EXTERNAL ASSET
Every word in every press release, blog post, LinkedIn post, deck, email, webinar script, podcast appearance, and website page passes this gate before publish. Owner: Vimal (accountable) + CSV/CSA contractor (responsible audit). When in doubt, ask before publishing.
DO SAY (allowed + encouraged) | DO NOT SAY (prohibited / risk) | WHY
"verified under our SDLC" | "validated" | Verixa never validates. Customer validates.
"the customer validates intended use" | "GxP-compliant out of the box" | Compliance is customer responsibility.
"supplier assurance evidence pack" | "certified" (self-claim) | No self-certification claims.
"21 CFR Part 11-aligned controls" | "21 CFR Part 11 compliant" | Compliance is a customer determination.
"Annex 11-aligned controls" | "Annex 11 compliant" | Same — compliance is contextual.
"Annex 22 (Draft 2025) treated as internal-control reference" | "Annex 22 certified" / "Annex 22 prohibits..." (as binding law) | Annex 22 is Draft 2025. Frame as internal control until RA/legal confirms enforceability.
"AI Act obligations are role-specific and obligation-specific" | "EU AI Act compliant" / "AI Act phasing in 2026-2027" (as a substitute for review) | Verixa does not claim EU AI Act compliance. Review MIRA claims for provider/deployer role, transparency, GPAI dependency, human-oversight framing.
"FDA CSA Final Guidance (Feb 2026) informs our approach" | "FDA-approved" | FDA does not approve QMS SaaS.
"MIRA is advisory — human accepts before action" | "MIRA decides" / "MIRA approves" | AI never autonomously decides GxP.
"Internal control: generative/probabilistic AI prohibited from sole-path critical GMP decisions" | "Annex 22 prohibits autonomous critical decisions" (presented as law) | Frame as internal Verixa control, not as binding regulation, until RA/legal confirms.
"design partner cohort" | "customer" | Pre-go-live: partners, not customers.
"founding partner" | "first paying customer" | Founding partner framing protects optics.
"verification evidence" / "G-7 pack" | "validation pack" | Verifies vs validates discipline.
"intended use mapping" | "out-of-the-box compliance" | Intended use is customer-specific.
"in design partnership with [NAMED PARTNER]" | "customer reference: [NAMED PARTNER]" | Reference requires explicit written consent.
"early access cohort" | "beta" / "alpha" | Beta/alpha implies untested; we say controlled SDLC.
"GAMP 5 Category 5 system" | "GAMP 5 validated" | Category is fact; validation is customer.
"ALCOA+ data integrity controls implemented" | "ALCOA+ compliant" | Compliance is contextual.
"controlled SDLC with named-human code review" | "AI wrote this code so it must be good" | Agent-generated code needs human evidence.
"deterministic AI in critical GMP paths" | "GenAI for batch release" | Annex 22 prohibits GenAI in critical paths.
"India: DPDP-aware data handling" | "India: GDPR compliant" | DPDP is the India law.
"AWS Mumbai data residency" | "data sovereign" | Use precise architectural language.
"+ GST" on India pricing | "incl. GST" / "GST exempt" | GST handling is buyer-specific.
"Vimal Veereshwarayya, PhD., RAC" | "Vimal V., PhD" / abbreviated | Full credentials required — E-E-A-T signal.
PRE-PUBLISH CHECKLIST — every external asset must answer YES to all 5
1. Does every regulatory claim have executed evidence in G-7 or a published source citation?
2. Have I avoided 'validated', 'compliant', 'certified' as self-claims?
3. Is every AI/MIRA reference framed as advisory + human-in-the-loop?
4. If naming a partner, customer, investor, or quote, do I have written approval?
5. Has the CSV/CSA contractor (or Vimal) signed off in writing?

## 12 · Budget & Tools
GTM BUDGET · 14-WEEK PROGRAM (Jun-Aug 2026) · INR-displayed for India ops · FX @ ₹97/USD
CATEGORY / ITEM | MONTHLY (₹) | Jun (₹) | Jul (₹) | Aug (₹) | TOTAL (₹) | NOTES
MARKETING TECH STACK
ArkOS CRM (in-house) — CRM · pipeline hygiene · outreach compliance · outreach analytics · founder operator | 0 | 0 | 0 | 0 | 0 | Aeonn Ark in-house · NO LICENSE COST · evidence-bound outreach by design
Apollo.io (Org plan) — prospecting + email sending | 25000 | 25000 | 25000 | 25000 | 75000 | Synced to ArkOS CRM
LinkedIn Sales Navigator (2 seats) | 17000 | 17000 | 17000 | 17000 | 51000 | Vimal + Janani
Webflow CMS + hosting | 8000 | 8000 | 8000 | 8000 | 24000 | verixa.ai
Goldcast or Zoom Events | 15000 | 15000 | 15000 | 15000 | 45000 | Webinars · forms POST to ArkOS
Canva Pro (team 4 seats) | 5000 | 5000 | 5000 | 5000 | 15000 | Marketing graphics
Figma (team 3 seats) | 4500 | 4500 | 4500 | 4500 | 13500 | Brand/design
Ahrefs / SEMrush | 25000 | 25000 | 25000 | 25000 | 75000 | SEO/AEO tracking
Hotjar / Microsoft Clarity | 6000 | 6000 | 6000 | 6000 | 18000 | UX analytics
Loom Business | 5000 | 5000 | 5000 | 5000 | 15000 | Demos + walkthroughs
Common Room / 6sense (intent monitoring) | 50000 | 50000 | 50000 | 50000 | 150000 | ABM intent · syncs to ArkOS
Newsletter delivery | 0 | 0 | 0 | 0 | 0 | Native in ArkOS CRM — no separate tool
PAID MEDIA
LinkedIn ABM (named-account ads) | 167000 | 50000 | 80000 | 200000 | 330000 | Bulk in Jul-Aug
LinkedIn sponsored content (founder) | 100000 | 30000 | 50000 | 100000 | 180000 | Founder amplification
LinkedIn lead-gen forms | 100000 | 30000 | 50000 | 100000 | 180000 | Pillar content
Google Ads search | 133000 | 30000 | 60000 | 100000 | 190000 | Long-tail SEO sup
Google Ads display retargeting | 67000 | 20000 | 30000 | 80000 | 130000 | Site visitors
X / Twitter founder voice amplification | 33000 | 10000 | 20000 | 30000 | 60000 | Vimal voice
Direct mail (6 ABM packages × ₹15K) | 30000 | 0 | 90000 | 0 | 90000 | W6-W8 push
EVENTS / PR / WEBINARS
Webinar production (3 webinars × ₹50K) | 50000 | 50000 | 50000 | 50000 | 150000 | Goldcast + design
Press release distribution (4 PRs × ₹25K) | 33000 | 25000 | 25000 | 50000 | 100000 | Wire services
PR agency retainer (optional) | 150000 | 150000 | 150000 | 150000 | 450000 | Tier-2 pharma trade
Roundtable dinner (India, W13) | 0 | 0 | 0 | 100000 | 100000 | 12 attendees premium venue
ISPE membership + India chapter event | 0 | 0 | 50000 | 0 | 50000 | Networking + speaking slot
GO-LIVE event production (W14) | 0 | 0 | 0 | 75000 | 75000 | Livestream
Founder bio + headshot kit | 25000 | 25000 | 0 | 0 | 25000 | Photo + design
Case study #1 production (post-W14) | 0 | 0 | 0 | 50000 | 50000 | Begin development
CONTRACTORS / FRACTIONAL
CSV/CSA + RA contractor (10 hrs/wk @ ₹3K/hr) | 130000 | 130000 | 130000 | 130000 | 390000 | Per CLAUDE.md / engineering ask
Outside legal counsel — US + India (retainer) | 75000 | 75000 | 100000 | 100000 | 275000 | DP LOIs + G-8 + DPA
PR agency retainer (alternative to in-house) | 0 | 0 | 0 | 0 | 0 | Covered above
Brand / design contractor (10 hrs/wk) | 80000 | 80000 | 80000 | 80000 | 240000 | Decks + 1-pagers
Webinar moderator / industry guests (3 × ₹40K) | 0 | 0 | 40000 | 80000 | 120000 | External voices
TOTAL — MARKETING TECH STACK |  |  |  |  | 481500
TOTAL — PAID MEDIA |  |  |  |  | 1160000
TOTAL — EVENTS / PR / WEBINARS |  |  |  |  | 1000000
TOTAL — CONTRACTORS / FRACTIONAL |  |  |  |  | 1025000
GRAND TOTAL · 14-week GTM program |  |  |  |  | 3666500
In USD (FX @ ₹97/USD) |  |  |  |  | $38K USD

## 13 · GTM Risk Register
GTM RISK REGISTER · Aligned to engineering W6 KILL-CHECK and W9 RC freeze · Weekly review with Vimal
# | RISK | LIKELY | IMPACT | SEVERITY | MITIGATION | OWNER | TRIGGER WEEK | STATUS
1 | Engineering slips beyond Sep 1 → marketing must defer GO-LIVE messaging | M | H | HIGH | Pre-prepare 'controlled wave' messaging; never commit GO-LIVE date externally before W12 confirmation | Vimal + Janani | W12 | OPEN
2 | Founder bandwidth — Vimal is critical path for founder voice, demos, closes, and content review | H | H | CRITICAL | Janani takes 50% of demos · Droupathy ghostwrites long-form for Vimal review · contractor handles compliance audit | Vimal | W1 | OPEN
3 | Compliance language drift in marketing content (e.g. 'compliant' creeps in) | H | H | CRITICAL | Mandatory pre-publish 5-question gate · contractor reviews every external asset · zero-tolerance feedback loop | Vimal + Contractor | W1-W14 | OPEN
4 | Design partner LOI conversion below target by W6 KILL-CHECK | M | H | HIGH | If <2 LOIs by W6, narrow ICP to 8 high-conviction accounts · pull in fractional sales BDR for outreach | Vimal | W6 | OPEN
5 | Partner refuses public reference / case study consent | M | M | MEDIUM | Build messaging around 'unnamed founding partner' if needed · prep partner contract language for early consent | Droupathy + Legal | W9 | OPEN
6 | Trade press doesn't pick up PR (low credibility = first-time founder) | M | M | MEDIUM | Lead with founder authority (PhD + RAC + 20yr) · target tier-2 trade press first · supplement with Vimal LinkedIn organic | Droupathy | W4 | OPEN
7 | AI / MIRA messaging causes regulatory concern from prospect or analyst | M | H | HIGH | Strict HITL + advisory framing · pre-brief analysts with technical Q&A · prepare 'MIRA in critical paths is prohibited' explainer | Vimal + Contractor | W1-W14 | OPEN
8 | Competitor (Veeva / Dot Compliance / Ketryx) launches similar AI-governance messaging | M | M | MEDIUM | Lock category language early (Annex 22 + EU AI Act framing) · publish FIRST in India · 'founding partner' optics | Droupathy + Vimal | W3 | OPEN
9 | India DPDP regulation tightens unexpectedly between Jun-Sep | L | M | MEDIUM | DPDP-aware language already · monitor weekly · contractor flags new MeitY guidance | Vimal + Contractor | W1-W14 | OPEN
10 | EU AI Act enforcement date / scope changes for pharma QMS | L | M | MEDIUM | 'Phasing in 2026-2027' language is already cautious · monitor EU pharma regulatory tracker | Vimal + Contractor | W1-W14 | OPEN
11 | Website launch delayed (Manoj capacity) | M | H | HIGH | Manoj has W1 hard deadline · use Webflow template + brand kit · 5-page MVP can be 3-page if needed | Manoj | W1 | OPEN
12 | Pillar content delayed (editorial bandwidth) | M | M | MEDIUM | Pre-write Pillars #1-3 in May · contractor writes #4-6 to Droupathy spec · Vimal reviews not writes | Droupathy | W1-W12 | OPEN
13 | Webinar attendance under-target (especially #1) | M | L | LOW | Industry guest co-host for credibility · 4-touch invite sequence (LinkedIn + email + paid + DM) | Droupathy + Kavin | W3-W12 | OPEN
14 | Apollo / ArkOS CRM integration delays campaign launch | L | M | MEDIUM | Kavin starts setup W1 · documented onboarding · fallback to manual sends in W1-W2 if delayed | Kavin | W1-W2 | OPEN
15 | Investor process distraction from DP focus | M | H | HIGH | Hard rule: no investor outreach until W14+ (after GO-LIVE) · investor warm intros tracked but not pursued before | Vimal | W6-W14 | OPEN
16 | Quality agreement (G-8) signing delayed beyond W9 | M | H | HIGH | Draft in W1 · legal align by end-June · paper template ready before partner asks · India + US counsel pre-engaged | Vimal + Legal | W9 | OPEN
17 | Multiple LOIs but no signed G-8 by RC freeze → PR PR risk | M | H | HIGH | Pre-prepare 'in active legal review' messaging · don't issue PR #2 until G-8 actually signed | Vimal + Droupathy | W9 | OPEN
18 | Founding partner does poorly in case study optics | L | H | HIGH | Multiple-partner case study optionality · don't anchor entire case study on partner #1 if marginal | Vimal | W14+ | OPEN

## 14 · Public Claim Register
PUBLIC CLAIM REGISTER · Auditable claim-control operating system · MUST be populated before every external publish
Every public claim entered with: claim text · type · source evidence · G-7 section or external citation · reviewer · approval date · status · public URL · expiry/re-review date. Status flow: Draft → Approved → (Published) → Withdrawn (if retracted). Re-review on expiry. Owner: Vimal (A) + Contractor (R). Auditable on demand.
# | ASSET | CLAIM TEXT (verbatim) | CLAIM TYPE | SOURCE EVIDENCE | G-7 SECTION / EXT SOURCE | REVIEWER | APPROVAL DATE | STATUS | PUBLIC URL / LOCATION | EXPIRY / RE-REVIEW DATE
1 | verixa.ai Home page | Verixa is the AI-governed pharma QMS — verified under our SDLC; customer validates intended use. | Product | V1 messaging house + SDLC docs | G-7 §1 (scope) + §2 (SDLC) | Vimal+Contractor | W1 W2 | Approved | verixa.ai/ | Re-review W6
2 | verixa.ai Product page | MIRA is advisory — human-in-the-loop on all GxP-critical decisions; not a system of record. | AI / MIRA | AI Governance V7 plan + HITL design | G-7 §9 (AI provider) | Vimal+Contractor | W1 W2 | Approved | verixa.ai/product | Re-review W6
3 | Press release #1 (W4) | Verixa demo-ready. Design partner cohort open. | Customer / DP | G-DEMO segregation passed | G-7 §1 + §3 (eval env) | Vimal+Contractor | W4 | Draft | PR wire + PharmaSource etc. | Re-review W6
4 | Pillar #1 (Annex 22) | EU GMP Annex 22 (Draft 2025) is an emerging internal control reference; we treat its principles as internal control until enforceability is confirmed. | Regulatory | Annex 22 Draft 2025 (EMA/PIC/S source) | External citation: EMA/PIC/S Annex 22 Draft | Vimal+Contractor | W1 W2 | Draft | verixa.ai/blog/annex-22 | Re-review W8
5 | Pillar #2 (FDA CSA) | FDA CSA Final Guidance (Feb 2026) informs our risk-based approach to assurance. | Regulatory | FDA CSA Final Guidance Feb 2026 | External citation: FDA CSA Final Guidance | Vimal+Contractor | W2 W3 | Draft | verixa.ai/blog/fda-csa-saas | Re-review W8
6 | Pillar #3 (EU AI Act) | EU AI Act obligations are role-specific and obligation-specific. Verixa does not claim EU AI Act compliance; MIRA claims are reviewed for provider/deployer role, transparency, GPAI dependency, and human-oversight framing. | AI / Regulatory | EU AI Act Reg 2024/1689 + Commission guidance | External citation: Reg 2024/1689 | Vimal+Contractor+Legal | W3 | Draft | verixa.ai/blog/eu-ai-act-pharma | Re-review W8
7 | Founding Partner card 1-pager | Phase 0/1/2/3 conversion ladder · founding partner pricing · sweeteners | Pricing | Pricing approval memo | G-8 (pricing schedule) | Vimal+Legal | W3 | Draft | Sales kit + DP page (gated) | Re-review W6
8 | Webinar #1 (W5) | Annex 22 (Draft 2025) implications for AI in pharma — explainer, not compliance claim. | Regulatory | Annex 22 Draft | External + Pillar #1 | Vimal+Contractor | W4 W5 | Draft | Recording + replay LP | Re-review W12
9 | Press release #2 (W9) — CONDITIONAL | Verixa signs first design partner — quality agreement executed. | Customer / DP | G-8 SIGNED + ArkOS partner consent record | G-8 signed counterpart | Vimal+Legal+Partner | W9 | Draft (HARD GATE) | PR wire | Re-review on use
10 | Webinar #3 (W12) | Founding partner story (co-host = partner) — partner-approved claims only. | Customer / DP | ArkOS partner consent record per claim | Per-claim consent | Vimal+Partner+Contractor | W11 W12 | Draft (HARD GATE) | Recording + replay LP | Re-review on use
11 | Press release #3 (W13) — CONDITIONAL | Evidence pack + Enablement kit delivered to design partner. | Customer / DP | G-7 delivered + ArkOS consent | G-7 + consent record | Vimal+Legal+Partner | W13 | Draft (HARD GATE) | PR wire | Re-review on use
12 | GO-LIVE PR #4 (01 Sep) — CONDITIONAL | Verixa verified version live with founding design partner. | Customer / DP / Product | W12 eng confirm + W14 per-workflow verified + ArkOS partner consent | G-7 verification evidence + G-8 + consent | Vimal+Eng+Legal+Partner | W14 | Draft (HARD GATE × 3) | PR wire + multi-outlet | Re-review on use
13 | GO-LIVE LP (01 Sep) | Verixa verified version live (production-verified workflows in pilot). | Product / Customer | W14 per-workflow verification status | G-7 verification report | Vimal+Eng+Contractor | W14 | Draft (HARD GATE) | verixa.ai/go-live | Re-review W16
14 | Founder LI long-form (Sept) | The 14 weeks that built Verixa — founder reflection. | Product / Customer | Engineering pilot flow + ArkOS partner consent for any partner reference | Internal + consent record | Vimal+Contractor | W14+ | Draft | LinkedIn | Re-review W16
15 | Investor update (W14+) | Verified version live; founding partner validation underway. | Customer / Product | Same as PR #4 evidence + investor letter Legal review | G-7 + G-8 + consent | Vimal+Legal | W14+ | Draft (HARD GATE) | Warm investor list | Re-review W16
16 | Case study #1 (W14+) | Founding partner pilot results. | Customer / Product | Per-claim partner consent in ArkOS + verified metrics | G-7 + per-claim consent | Vimal+Legal+Partner | W16+ | Draft (HARD GATE — per claim) | Case study page + sales kit | Re-review every 6mo
RULES OF THE REGISTER
1. No external publish without a Register row in Status = Approved (or in process for HARD GATE assets).
2. Every regulatory claim must cite G-7 section OR a published external source. No claim from memory.
3. Every customer / partner claim must cite a written ArkOS partner consent record (reviewer · date · expiry).
4. Every AI / MIRA claim must include the role framing (advisory · HITL · provider/deployer · transparency · GPAI dependency).
5. Status = Withdrawn → asset must be removed from public URL within 24 hours and re-classified.
6. Expiry / re-review date is mandatory — no perpetual claims.
7. Owner: Vimal (A) + Contractor (R) — weekly Friday review of all active rows.
8. Auditable on demand — the Register IS the evidence pack for marketing claims (parallel to G-7 for product).

## 15 · Day-by-Day Calendar
DAY-BY-DAY MASTER CALENDAR · 187 actions chronologically sorted · all 9 workstreams · 5 owners + Contractor · W1-W14 (01 Jun - 31 Aug 2026)
This sheet consolidates all workstream sub-flows into one chronological view. Use for daily standups + weekly Friday status reviews. ⚠ = critical-path action. EXECUTION RULES: (a) every external asset gated by Public Claim Register (Sheet 14); (b) every partner reference requires written ArkOS consent; (c) 01 Sep PR conditional on W12 eng confirm + W14 per-workflow verification; (d) Vimal final-approval-only · Droupathy first drafts · Contractor first-pass claim review.
DATE | DAY | WK | WS | OWNER | ACTION | DELIVERABLE | DEPENDENCY | ACCEPTANCE | SIGN-OFF | CRIT
01 Jun | Mon | W1 | WS-1 | Vimal | Draft V1 messaging house: 3 pillars × 3 proof points | messaging-house-v1-draft.docx | — | All 9 proof points evidence-bound | Vimal | ⚠
01 Jun | Mon | W1 | WS-2 | Droupathy→Contractor→Vimal | Founder LI #1 manifesto — Droupathy drafts · Contractor reviews · Vimal voice + approval | LI post · 1500 words | V1 messaging | Contractor pass · Vimal final | Vimal
01 Jun | Mon | W1 | WS-2 | Droupathy | Founder bio + headshot kit production | bio.docx + 5 headshots ZIP | — | Bio approved by Vimal · brand-aligned | Vimal
01 Jun | Mon | W1 | WS-3 | Droupathy+Contractor | Pillar #1 outline — Annex 22 (Draft 2025) internal-control framing | pillar-1-outline.docx | V1 messaging | Contractor reg-fact-check pass | Vimal
01 Jun | Mon | W1 | WS-4 | Manoj | Domain + DNS + SSL on verixa.ai · Cloudflare + Vercel · staging | verixa.ai resolves | — | LCP target <2.5s staging | Manoj | ⚠
01 Jun | Mon | W1 | WS-5 | Kavin | ArkOS CRM workspace — US + India tenants · pipeline-hygiene + outreach-compliance rules | ArkOS LIVE | V1 messaging | Test 'validated' msg blocked · DPDP | Kavin+Vimal | ⚠
01 Jun | Mon | W1 | WS-6 | Vimal | Lock 14 ICP account list — named accounts + contact + region + why-fit | 14-ICP-list-v1.xlsx | V1 messaging | Approved by Vimal · loaded into ArkOS | Vimal | ⚠
01 Jun | Mon | W1 | WS-6 | Vimal | Founder outreach — top 6 ICPs (P0) via LinkedIn + warm intros | 6 outreach msgs sent | ICP list | Personalized · ArkOS-routed | Vimal | ⚠
01 Jun | Mon | W1 | WS-8 | Janani+Vimal | Demo script v1 draft — 6-workflow + MIRA · 30-min · 7 objections | demo-script-v1.docx | V1 messaging | Vimal narrative + Contractor lang pass | Vimal
02 Jun | Tue | W1 | WS-1 | Droupathy | Convert V1 into 1-page narrative + 30-sec elevator + 60-sec founder voice | narrative-v1.docx + elevator.docx | messaging-house-v1 | Reads aloud in Vimal tone | Vimal
02 Jun | Tue | W1 | WS-4 | Manoj+Droupathy | Home page — hero + value prop + DP CTA + founder note · 'Verifies' above fold | home page LIVE | V1 messaging | Vimal narrative + Contractor lang pass · LCP <2.5s | Vimal | ⚠
02 Jun | Tue | W1 | WS-4 | Manoj+Janani | Product page — 6-workflow map + MIRA advisory line | product page LIVE | V1 | Janani product accuracy + Contractor | Vimal
02 Jun | Tue | W1 | WS-5 | Kavin | Apollo.io seat live · API to ArkOS · 5 sequence templates drafted | Apollo+ArkOS bridge LIVE | ArkOS | Test prospect imported · seq sends staging | Kavin
02 Jun | Tue | W1 | WS-6 | Janani+Kavin | Demo scheduling tooling — Calendly + ArkOS booking · tier-based routing | booking flow LIVE | ArkOS | Test booking confirms · adds deal | Janani
03 Jun | Wed | W1 | WS-1 | Contractor | Review V1 + narrative for language-guard violations (24 DO/DON'T pairs) | V1-compliance-review.docx | V1 + narrative | Zero violations OR all flagged | Contractor | ⚠
03 Jun | Wed | W1 | WS-2 | Vimal | LI post #2 — Verify vs Validate distinction | LI post | V1 | Contractor pass | Vimal
03 Jun | Wed | W1 | WS-3 | Droupathy | Pillar #1 draft v1 — 2500w · 5 H2 · downloads CTA | pillar-1-draft.docx | outline | Vimal + Contractor pass | Vimal
03 Jun | Wed | W1 | WS-4 | Manoj+Vimal | Pilot / Design Partner page — Phase 0/1/2/3 ladder · founding partner card · app form | DP page LIVE | founding-partner messaging | Form routes to Vimal+Janani via ArkOS | Vimal | ⚠
03 Jun | Wed | W1 | WS-5 | Kavin+Manoj | GA4 + GTM + LinkedIn Insight Tag on verixa.ai · consent banner live | analytics LIVE | verixa.ai pages | Test conv fires · consent enforced | Kavin+Manoj
04 Jun | Thu | W1 | WS-1 | Vimal | Lock V1 messaging house after compliance pass | messaging-house-v1-LOCKED.pdf | compliance review | Signed PDF circulated | Vimal | ⚠
04 Jun | Thu | W1 | WS-4 | Manoj+Droupathy | About / Founder page — Vimal bio · team · India + US entity · publications | about page LIVE | bio kit | Vimal sign-off · credentials prominent | Vimal
04 Jun | Thu | W1 | WS-4 | Manoj+Kavin | Contact + DP application form · ArkOS integration tested | contact form LIVE | ArkOS workspace | Test submission · DPDP consent | Manoj
04 Jun | Thu | W1 | WS-5 | Kavin+Vimal | 14 ICP accounts loaded · enriched via Apollo · 200+ contacts | ICP accounts in ArkOS | DP ICP list | Source-tracked DPDP | Vimal | ⚠
05 Jun | Fri | W1 | WS-1 | Droupathy | Publish V1 internally · brief all 5 owners | Internal brief in Notion/ArkOS | V1 locked | Each owner ack receipt | Droupathy
05 Jun | Fri | W1 | WS-2 | Vimal | LI post #3 — AI-governed QMS in 2026 | LI post | V1 | Contractor pass | Vimal
05 Jun | Fri | W1 | WS-3 | Manoj+Droupathy | Pillar #1 published · schema markup · cluster pages stubbed | pillar-1 LIVE | draft signed | Schema validates · LCP <2.5s | Manoj+Droupathy
05 Jun | Fri | W1 | WS-4 | Manoj | Mobile responsive + Core Web Vitals (LCP/CLS/INP) + WCAG 2.1 AA | perf report | 5 pages | All green · India 4G test | Manoj
05 Jun | Fri | W1 | WS-5 | Kavin | Founder note sequence #1 (Vimal voice) drafted — 100 warm contacts | founder-seq-1.docx | V1 | Vimal voice approved · Contractor | Vimal
05 Jun | Fri | W1 | WS-8 | Janani | Objection bank v1 — top 20 expected objections | objection-bank-v1.docx | V1 | Vimal review pass | Vimal
08 Jun | Mon | W2 | WS-1 | Contractor | Author Compliance Language Guardrail v1 — 24 DO/DON'T pairs + 5-Q gate | language-guardrail-v1.docx | V1 messaging | Covers Part 11/Annex/EU AI Act/CSA/MIRA | Contractor | ⚠
08 Jun | Mon | W2 | WS-2 | Vimal | Founder LI rhythm 3x/wk (Mon·Wed·Fri) — total 9 posts W2-W4 | 9 LI posts | V1+Guardrail | Each Contractor-reviewed · 50K+ cum | Vimal
08 Jun | Mon | W2 | WS-3 | Droupathy+Contractor | Pillar #2 outline — FDA CSA Final Guidance (Feb 2026) SaaS playbook | pillar-2-outline.docx | — | Contractor pass | Vimal
08 Jun | Mon | W2 | WS-4 | Manoj | Organization schema (JSON-LD) covering both Navira RT entities | org schema LIVE | about page | Validates · no errors | Manoj | ⚠
08 Jun | Mon | W2 | WS-5 | Kavin | Attribution model live in ArkOS + GA4 (first-touch + multi-touch) | attribution model LIVE | analytics | Test conversion attributed | Kavin
08 Jun | Mon | W2 | WS-6 | Vimal | Founder outreach — next 8 ICPs (P1+P2) launched | all 14 contacted | P0 outreach | 100% of 14 · response in ArkOS | Vimal | ⚠
08 Jun | Mon | W2 | WS-9 | Contractor | Compliance Language Guardrail v1 authored (see WS-1) | guardrail v1 | V1 | Vimal + Contractor lock | Vimal+Contractor | ⚠
08 Jun | Mon | W2 | WS-9 | Contractor | Continuous review of all published content · LI · web · email seq | daily flag log | content live | Zero un-flagged violations | Contractor
09 Jun | Tue | W2 | WS-1 | Vimal | Review + lock Guardrail v1 | language-guardrail-v1-LOCKED.pdf | Guardrail draft | Vimal + Contractor signatures | Vimal | ⚠
09 Jun | Tue | W2 | WS-4 | Manoj | Person schema (Vimal) + Author markup · PhD + RAC structured | person schema LIVE | bio kit | AEO/GEO authority signal | Manoj | ⚠
09 Jun | Tue | W2 | WS-5 | Kavin | Cold sequence #1 launched — India CDMO (5-touch) · 300 contacts | seq-1 LIVE | ICP + Contractor pass | 5% reply target · DPDP opt-in | Kavin
10 Jun | Wed | W2 | WS-1 | Kavin | Load 24 DO/DON'T into ArkOS Outreach Compliance Mgr | ArkOS compliance ruleset active | Guardrail locked | Test msg blocked on 'validated' | Kavin | ⚠
10 Jun | Wed | W2 | WS-3 | Droupathy | Pillar #2 draft v1 — 2500w | pillar-2-draft.docx | outline | Vimal + Contractor | Vimal
10 Jun | Wed | W2 | WS-4 | Manoj | Article schema on all blog · BreadcrumbList · OpenGraph + Twitter cards | schemas LIVE | — | All validate | Manoj
10 Jun | Wed | W2 | WS-5 | Kavin | Cold sequence #2 launched — India mid-pharma (5-touch) · 300 | seq-2 LIVE | ICP | 5% reply | Kavin
10 Jun | Wed | W2 | WS-8 | Droupathy+Janani | Verixa product 1-pager (US) + (India INR pricing · '+ GST') | 1-pager-US.pdf + 1-pager-IN.pdf | V1 + pricing | Contractor pass · pricing approved | Vimal
10 Jun | Wed | W2 | WS-9 | Kavin+Contractor | ArkOS Outreach Compliance Mgr ruleset loaded (24 DO/DON'T) | ruleset LIVE | guardrail locked | Test msg blocked on violation | Kavin+Contractor | ⚠
11 Jun | Thu | W2 | WS-1 | Droupathy | Publish Guardrail to all owners · embed in content brief template | Guardrail in shared drive + Notion | Guardrail locked | Every owner confirms read | Droupathy
11 Jun | Thu | W2 | WS-4 | Manoj+Droupathy | E-E-A-T proof — Vimal credentials · publications · expert-author badges | E-E-A-T components live | bio | Visible on every authored page | Manoj
11 Jun | Thu | W2 | WS-5 | Kavin+Vimal | Lead scoring model live in ArkOS · MQL definition signed off | lead scoring LIVE | ICP data | Model triggers on real signal | Kavin+Vimal
12 Jun | Fri | W2 | WS-1 | Contractor | Compliance Audit #1 — review all W1-W2 published assets | audit-1-report.docx | All W1-W2 assets | Zero un-flagged violations | Contractor+Vimal | ⚠
12 Jun | Fri | W2 | WS-3 | Droupathy+Kavin | Newsletter #1 in ArkOS — Annex 22 + CSA + DP cohort open | newsletter-1 | Pillars #1+#2 outlines | >40% open rate | Vimal | ⚠
12 Jun | Fri | W2 | WS-4 | Manoj | Submit to AI search indexes — IndexNow + sitemap (Google + Bing + ChatGPT-bot) | crawled by 3+ engines | 5 core pages + schemas | Confirmed in GSC + Bing | Manoj
12 Jun | Fri | W2 | WS-5 | Kavin | Apollo signal sync to ArkOS — daily feed | signal feed LIVE | Apollo bridge | Test signal lands in ArkOS | Kavin
12 Jun | Fri | W2 | WS-8 | Droupathy+Contractor | 'Verify vs Validate' explainer 1-pager — pillar asset | verify-vs-validate.pdf | V1 + guardrail | Contractor zero-finding pass | Vimal | ⚠
15 Jun | Mon | W3 | WS-1 | Vimal | Rehearse investor narrative (15-min) with Droupathy as 'investor' | Recorded rehearsal v1 | V1 locked | Vimal hits 9 proof points in 15min | Vimal
15 Jun | Mon | W3 | WS-3 | Manoj+Droupathy | Pillar #2 published · cluster pages live | pillar-2 LIVE | draft signed | Schema validates | Manoj
15 Jun | Mon | W3 | WS-3 | Droupathy+Contractor | Pillar #3 outline — EU AI Act role-specific framing | pillar-3-outline.docx | — | Contractor + Vimal narrative pass | Vimal
15 Jun | Mon | W3 | WS-4 | Manoj+Droupathy | Pillar #1-3 pages live with FAQPage schema | 3 pillars LIVE | Drafts from WS-3 | FAQ markup validates · LCP <2.5s | Manoj
15 Jun | Mon | W3 | WS-4 | Manoj | Topic clusters — 5 cluster pages per pillar (W3-W6, 15 total) | 15 cluster pages by W6 | pillars | Each links to pillar · 800-1200w | Manoj
15 Jun | Mon | W3 | WS-4 | Manoj+Kavin | Webinar #1 LP — registration funnel + ArkOS + LinkedIn pixel | LP LIVE | Webinar #1 scheduled | Test reg · ArkOS contact created | Manoj
15 Jun | Mon | W3 | WS-5 | Kavin | Cold sequence #3 — US biotech (5-touch) · 200 contacts | seq-3 LIVE | ICP | 5% target · CAN-SPAM | Kavin
15 Jun | Mon | W3 | WS-5 | Kavin+Manoj | Webinar registration funnels (3) — invites + LP + 4-touch reminder | 3 funnels (W3·W7·W12) | LPs from Manoj | 300-500 regs each · 30%+ live | Kavin
15 Jun | Mon | W3 | WS-6 | Janani+Vimal | First 3 demos delivered (P0) — 30-min demo + 15-min discovery (Janani primary · Vimal joins P0) | 3 demo recordings + ArkOS notes | Demo script v1 | ≥3 demos held · 24h follow-up | Vimal+Janani
15 Jun | Mon | W3 | WS-7 | Droupathy | Webinar #1 logistics — speaker · guest · Goldcast · run-of-show | webinar-1 plan | Pillar #1 outline | Date locked · industry guest confirmed | Droupathy
15 Jun | Mon | W3 | WS-7 | Droupathy+Kavin | Webinar #1 promotion — invites + LI + email seq + paid | 300+ regs by W5 | LP + funnel | reg pace tracked | Kavin
15 Jun | Mon | W3 | WS-8 | Janani+Vimal | Demo script v2 — post-W4 segregation + first-3-demos feedback | demo-script-v2.docx | v1 + 3 demos held | Vimal + Janani sign-off | Vimal+Janani
17 Jun | Wed | W3 | WS-1 | Vimal | Rehearse DP narrative (12-min discovery + 18-min demo) with Janani | Recorded rehearsal v1 | V1 locked | Vimal hits founding-partner ladder | Vimal
17 Jun | Wed | W3 | WS-2 | Droupathy | Podcast outreach — pitch 12 podcasts (6 India + 6 US/EU) | podcast-pitch-tracker.xlsx | bio kit | ≥5 confirmed bookings by W6 | Droupathy
17 Jun | Wed | W3 | WS-3 | Droupathy | Pillar #3 draft v1 — 2500w | pillar-3-draft.docx | outline | Contractor pass | Vimal
17 Jun | Wed | W3 | WS-5 | Kavin | Cold sequence #4 — US CDMO (5-touch) · 150 | seq-4 LIVE | ICP | 5% target | Kavin
17 Jun | Wed | W3 | WS-8 | Vimal+Contractor | Annex 22 / EU AI Act readiness brief 1-pager · FDA CSA SaaS brief 1-pager | 2 reg-brief 1-pagers | Pillars #1 + #3 | Contractor pass | Vimal
19 Jun | Fri | W3 | WS-2 | Vimal+Droupathy | Op-ed #1 draft — Verify vs Validate · target ISPE/PharmExec | op-ed-1-draft.docx | V1 | Contractor review pass | Vimal
19 Jun | Fri | W3 | WS-3 | Manoj+Droupathy | Pillar #3 published | pillar-3 LIVE | draft signed | Schema validates | Manoj
19 Jun | Fri | W3 | WS-5 | Kavin | LinkedIn ABM ads — named-account ads to 14 ICPs · India+US | ABM campaign LIVE | Ad creative + Contractor | 50K impressions to ICP W3-W14 | Kavin | ⚠
19 Jun | Fri | W3 | WS-5 | Kavin | Weekly KPI dashboard for Vimal+Janani · ArkOS+Looker · Fri cadence | weekly dashboards | attribution model | Delivered every Fri 9am IST | Kavin
19 Jun | Fri | W3 | WS-8 | Janani+Vimal | Founding Partner program card 1-pager — Phase 0/1/2/3 + pricing + sweeteners | founding-partner-card.pdf | founding-partner msg | Pricing approved · Contractor | Vimal
19 Jun | Fri | W3 | WS-9 | Contractor+Vimal | COMPLIANCE AUDIT #1 — W1-W3 assets · pillars · LI · sequences | audit-1-report.pdf | All W1-W3 | Zero violations OR all remediated 48hr | Vimal+Contractor | ⚠
22 Jun | Mon | W4 | WS-2 | Vimal | LI long-form #1 — manifesto | LI Article 2000+w | V1 | Contractor pass · 10K+ in 72hr | Vimal | ⚠
22 Jun | Mon | W4 | WS-4 | Manoj | Founding-Partner application LP — separate from main DP page | app LP LIVE | founding-partner messaging | Test app routes to Vimal · 10+ apps by W9 | Manoj
22 Jun | Mon | W4 | WS-5 | Kavin | LinkedIn sponsored content boost — Vimal founder posts (top 3 W1-W3) | sponsored boost LIVE | Vimal approval | Founder voice integrity preserved | Vimal
22 Jun | Mon | W4 | WS-5 | Kavin | Common Room / 6sense intent monitoring on 14 ICPs · ArkOS alerts | intent feed LIVE | ICP loaded | 3+ alerts/week to Vimal+Janani | Kavin
22 Jun | Mon | W4 | WS-5 | Kavin | Google Ads search — eQMS pharma / AI QMS (US + India variants) | Google search LIVE | LP infra | 200+ qualified clicks · CPM <₹2K | Kavin
22 Jun | Mon | W4 | WS-5 | Kavin | Google display retargeting — site visitors + qualified-LP viewers | retargeting LIVE | GA4 | 10x reach to engaged | Kavin
22 Jun | Mon | W4 | WS-6 | Janani+Vimal | Demos 4-6 delivered (P0 + P1) | 3 more demos | first 3 done | 6 cum by W4 Fri | Vimal+Janani
22 Jun | Mon | W4 | WS-9 | Contractor | Pre-publish review of PR #1 · webinar #1 · demo video · LI #4-9 · 1-pagers | asset pass log | each asset | Each Contractor-passed | Contractor
24 Jun | Wed | W4 | WS-2 | Droupathy | Press kit assembly — V1 narrative + 1-pager + Vimal bio + demo loom | press-kit.zip | All W1-W3 assets | Vimal+Contractor sign-off | Vimal | ⚠
24 Jun | Wed | W4 | WS-8 | Janani | Demo video — 6-workflow + MIRA cut · 2-min loom | demo-video-2min.mp4 | v2 script | Vimal voice approved | Vimal | ⚠
25 Jun | Thu | W4 | WS-7 | Vimal+Droupathy | Webinar #1 live — EU GMP Annex 22 for pharma · what changes for AI | webinar #1 recorded | 300+ regs · run-of-show | 100+ live · Contractor monitors claims | Vimal | ⚠
26 Jun | Fri | W4 | WS-2 | Droupathy | PR #1 — Verixa demo-ready · DP cohort open · distribute to 5 outlets | PR #1 distributed | press kit · Contractor pass | 5+ pickups in 7 days | Vimal+Droupathy | ⚠
26 Jun | Fri | W4 | WS-6 | Vimal | W4 DP Status — 14 contacted · 6 demos · 2 active LOI conversations | DP status W4 in ArkOS | all above | Targets hit OR mitigation plan | Vimal | ⚠
26 Jun | Fri | W4 | WS-7 | Droupathy | Webinar #1 replay + 3-takeaway carousel + 1-pager | replay + assets | recording | Published 48hr | Droupathy
26 Jun | Fri | W4 | WS-8 | Janani | Objection bank v2 — first-week demo feedback | obj-bank-v2.docx | 3 demos held | Vimal pass | Vimal
29 Jun | Mon | W5 | WS-1 | Vimal | Founding-partner messaging v1 draft — Phase 0/1/2 ladder | founding-partner-msg-v1.docx | V1 + DP narrative | Contractor review pass | Vimal
29 Jun | Mon | W5 | WS-2 | Vimal | Sustained LI rhythm — 3x/wk W5-W13 (27 more posts) + long-form #2-#4 | 30 LI posts + 3 long-form | Guardrail | 200K+ cum by W14 | Vimal
29 Jun | Mon | W5 | WS-4 | Manoj+Droupathy | Resources hub launch — blog · downloads · webinar replays | hub LIVE | 5 pillars + 2 newsletters | Navigation clear · search functional | Manoj
29 Jun | Mon | W5 | WS-5 | Kavin+Vimal | Founder warm-contact note sequence launched — 100 contacts | warm-seq LIVE | Vimal approval | 15% reply target · personal touch | Vimal
29 Jun | Mon | W5 | WS-5 | Kavin | LinkedIn lead-gen forms for Pillars #1-3 | lead-gen forms LIVE | Pillars live | 300+ MQLs by W12 | Kavin
29 Jun | Mon | W5 | WS-6 | Vimal+Legal | LOI template (US + India) finalized · counsel-reviewed | LOI-template-US.docx + LOI-template-IN.docx | V1 + founding-partner msg | Both counsel-reviewed | Vimal+Legal | ⚠
29 Jun | Mon | W5 | WS-6 | Janani+Vimal | Demos 7-8 delivered | 2 more demos | earlier demos | 8 cum by W6 | Vimal
29 Jun | Mon | W5 | WS-8 | Vimal+Janani+Kavin | Pricing page + ROI calculator live on verixa.ai (gated) | pricing page LIVE + ROI calc | Pricing approved | + GST conv India · gated routing | Vimal+Manoj
29 Jun | Mon | W5 | WS-9 | Contractor+Vimal | COMPLIANCE AUDIT #2 (pre-W6 KILL) — W4-W6 assets · PR #1 · webinar #1 · op-ed #1 | audit-2-report.pdf | All W4-W6 | Zero violations · GREEN for W6 KILL | Vimal+Contractor | ⚠
01 Jul | Wed | W5 | WS-3 | Droupathy+Kavin | Newsletter #2 — Demo-ready + DP FAQ | newsletter-2 in ArkOS | Pillars 1-3 live | >40% open rate | Vimal
01 Jul | Wed | W5 | WS-6 | Vimal | LOI #1 sent to top P0 prospect | LOI #1 sent | LOI template | Customized · trackable ArkOS | Vimal | ⚠
03 Jul | Fri | W5 | WS-2 | Vimal+Contractor | Op-ed #1 submission to ISPE Pharmaceutical Engineering | submitted op-ed-1 | draft + Contractor pass | Editorial ack within 5 days | Vimal
03 Jul | Fri | W5 | WS-8 | Vimal+Legal | DPA + MSA templates — DPDP + GDPR + HIPAA-aware · counsel-reviewed | DPA-MSA-templates.docx | Legal alignment | Both counsel pass | Vimal+Legal | ⚠
06 Jul | Mon | W6 | WS-2 | Vimal | Podcast #1 recorded — India pharma tech podcast | recorded podcast #1 | talking points approved | Live within 14 days | Vimal
06 Jul | Mon | W6 | WS-3 | Droupathy+Contractor | Pillar #4 outline — HITL patterns for GxP AI | pillar-4-outline.docx | — | Contractor reg pass | Vimal
06 Jul | Mon | W6 | WS-4 | Manoj+Kavin | Webinar #2 LP (CSA SaaS) | LP LIVE | Webinar #2 scheduled | All pixels firing | Manoj
06 Jul | Mon | W6 | WS-5 | Kavin | Personalized 1-pagers for top 6 ICPs (post-Audit #2) | 6 personalized 1-pagers | top 6 ID'd | Vimal approval each · Contractor | Vimal
06 Jul | Mon | W6 | WS-5 | Kavin | Direct mail to top 6 ICPs (US + India) — physical kit | 6 kits couriered | 1-pagers + delivery | 100% delivery confirmation | Kavin
06 Jul | Mon | W6 | WS-6 | Vimal | W6 KILL-CHECK — 8 demos · ≥2 LOIs · 200+ MQLs · podcast #1 live | W6 GO/NO-GO report | all above | GREEN: continue all-six; YELLOW: narrow to 8 ICPs | Vimal+Janani | ⚠
06 Jul | Mon | W6 | WS-6 | Vimal+Legal | LOI #2 + #3 negotiation + signing | 2 more LOIs signed/legal | discovery + LOI template | 3-4 LOIs by W9 | Vimal+Legal | ⚠
06 Jul | Mon | W6 | WS-7 | Droupathy+Janani | Webinar #2 logistics — CSA SaaS QMS in 60 days · DP consultant guest | webinar-2 plan | Pillar #2 + Audit #2 | Date locked · guest confirmed | Droupathy
06 Jul | Mon | W6 | WS-7 | Droupathy+Kavin | Webinar #2 promotion — target 500+ regs | 500+ regs by W8 | LP + funnel | reg pace tracked | Kavin
08 Jul | Wed | W6 | WS-1 | Vimal+Droupathy | Founding-partner messaging v2 — refine after 3-5 DP calls | founding-partner-msg-v2.docx | 3+ DP calls held | Captures top 5 real objections | Vimal
08 Jul | Wed | W6 | WS-3 | Droupathy+Janani | Pillar #4 draft v1 — 2500w + HITL flow diagrams | pillar-4-draft.docx | outline | Vimal+Contractor+Janani | Vimal
13 Jul | Mon | W7 | WS-2 | Vimal+Droupathy | Analyst briefing #1 — Gartner pharma + AI Governance (NDA) | briefing pack · NDA call | Press kit + V1 | Briefing held + follow-up | Vimal | ⚠
13 Jul | Mon | W7 | WS-4 | Manoj | AEO/GEO citation engineering — Q&A · long-tail FAQ · stats for AI search | 15 Q&A pages | Pillars + schemas | Cited in 3+ AI search by W12 | Manoj | ⚠
13 Jul | Mon | W7 | WS-6 | Vimal+Janani+Legal | G-8 quality agreement draft #1 — 10-clause min · counsel-aligned | G-8-draft-v1.docx | LOI #1 signed | Clauses 1·2·4·6·10 + Contractor+Legal | Vimal+Legal+Contractor | ⚠
13 Jul | Mon | W7 | WS-6 | Vimal+Janani | Pilot scoping calls (Phase 0 Evidence Mapping) with LOI'd partners | 3 scoping calls held | LOIs signed | Workflow mapping doc per partner | Vimal
13 Jul | Mon | W7 | WS-7 | Droupathy+Vimal | ISPE India + ISPE US local events — Vimal speaking/networking · 3+ DP leads | ISPE attendance reports | V1 + bio kit | 20+ connections · 3+ DP leads | Vimal
13 Jul | Mon | W7 | WS-8 | Janani+Contractor | Validation Enablement Kit v1 outline — URS · IQ/OQ/PQ templates · RTM · IU mapping · known-limitations | kit-outline.docx | Phase 1 sprint scope | Contractor pass on framing | Vimal+Contractor | ⚠
13 Jul | Mon | W7 | WS-8 | Janani+Contractor | Validation Enablement Kit content build — 5 template documents | 5 kit templates draft | outline | Each Contractor-reviewed | Janani+Contractor | ⚠
13 Jul | Mon | W7 | WS-9 | Contractor | Pre-publish review of pillar #4 · webinar #2 · podcast scripts · analyst briefing pack | asset pass log | each asset | Each Contractor-passed | Contractor
15 Jul | Wed | W7 | WS-2 | Vimal | Podcast #2 recorded — US pharma podcast | recorded podcast #2 | approved | Live within 14 days | Vimal
15 Jul | Wed | W7 | WS-4 | Manoj+Droupathy | Backlink outreach — 5 industry sites for guest posts/mentions | 5 backlinks by W12 | pillars | Quality DR40+ sites | Manoj
17 Jul | Fri | W7 | WS-3 | Manoj+Droupathy | Pillar #4 published | pillar-4 LIVE | draft signed | Schema | Manoj
20 Jul | Mon | W8 | WS-2 | Vimal+Droupathy | Analyst briefing #2 — IDC Health / IDC Life Sciences (NDA) | briefing held | press kit | Briefing + follow-up | Vimal
20 Jul | Mon | W8 | WS-6 | Vimal+Legal | G-8 negotiation rounds 1-2 with partner #1 | G-8 v2 + v3 | draft | Convergence by W9 | Vimal+Legal | ⚠
22 Jul | Wed | W8 | WS-7 | Vimal+Droupathy | Webinar #2 live — CSA SaaS QMS in 60 days | webinar #2 recorded | 500+ regs | 150+ live · Contractor monitors | Vimal | ⚠
23 Jul | Thu | W8 | WS-7 | Droupathy | Webinar #2 replay + assets | replay + assets | recording | Published 48hr | Droupathy
24 Jul | Fri | W8 | WS-3 | Droupathy+Kavin | Newsletter #3 — RC freeze week + G-8 progress | newsletter-3 in ArkOS | Pillar 4 + DP progress | >40% open rate | Vimal
27 Jul | Mon | W9 | WS-3 | Droupathy+Vimal+Janani | Pillar #5 draft — Founding-partner playbook · Phase 0/1/2 visuals | pillar-5-draft.docx | DP learnings | Contractor + Vimal pass | Vimal
27 Jul | Mon | W9 | WS-4 | Manoj | Pillar #5 schema + cluster pages | clusters LIVE | Pillar #5 published | Schema validates | Manoj
27 Jul | Mon | W9 | WS-9 | Contractor+Vimal | COMPLIANCE AUDIT #3 (pre-RC freeze) — W7-W9 · PR #2 contingency · G-8 marketing claims · analyst briefings | audit-3-report.pdf | All W7-W9 | Zero violations · GREEN for RC freeze | Vimal+Contractor | ⚠
29 Jul | Wed | W9 | WS-2 | Vimal+Contractor | Op-ed #2 submission — Annex 22 + India pharma · PharmaBiz/Express Pharma | submitted op-ed-2 | draft + Contractor pass | Editorial ack 5 days | Vimal
29 Jul | Wed | W9 | WS-3 | Manoj+Droupathy | Pillar #5 published — gated downloads | pillar-5 LIVE | draft signed | Schema · gated | Manoj
31 Jul | Fri | W9 | WS-2 | Droupathy+Legal | PR #2 — Verixa signs first DP (HARD GATE: G-8 + ArkOS consent + Contractor) | PR #2 IFF all gates | G-8 SIGNED + ArkOS consent | 3 gates pass OR PR held | Vimal+Legal+Partner | ⚠
31 Jul | Fri | W9 | WS-6 | Vimal+Legal+Partner | G-8 SIGNED with founding partner — RC freeze gate | G-8 SIGNED | negotiation closed | Both signatures · binding · counterpart filed | Vimal+Legal | ⚠
03 Aug | Mon | W10 | WS-1 | Vimal+Contractor | Verified-not-Validated rollout doc — 45-asset inventory | verified-rollout-checklist.docx | Audit #3 | Each asset marked status | Vimal | ⚠
03 Aug | Mon | W10 | WS-3 | Vimal+Droupathy | Case study #1 development begins — HARD GATE: ArkOS consent per claim | case-study-1-draft.docx | Partner consent + W14 go-live | Each claim consent-recorded | Vimal+Legal+Partner | ⚠
03 Aug | Mon | W10 | WS-4 | Manoj+Kavin | Webinar #3 LP (Founding Partner story) | LP LIVE | W3 scheduled | All pixels firing | Manoj
03 Aug | Mon | W10 | WS-5 | Kavin | Retargeting on evidence-pack viewers (high-intent) | high-intent retargeting LIVE | evidence pack LP | 3x engagement vs cold | Kavin
03 Aug | Mon | W10 | WS-6 | Janani+Vimal | Phase 1 (Controlled Evidence Sprint) kickoff with founding partner | sprint kickoff doc | G-8 signed | Partner team ID'd · cadence set | Vimal+Janani
03 Aug | Mon | W10 | WS-6 | Vimal | 2nd LOI moves to G-8 negotiation | 2nd G-8 in legal | LOI #2 signed | On track sign W14+ / Sept | Vimal+Legal
03 Aug | Mon | W10 | WS-7 | Droupathy+Janani+Partner | Webinar #3 logistics — Founding partner story · co-host = partner (consent+legal) | webinar-3 plan | Partner consent + G-8 | Co-host confirmed · run approved by partner | Vimal+Partner | ⚠
03 Aug | Mon | W10 | WS-7 | Droupathy+Kavin | Webinar #3 promotion — target 500+ regs | 500+ regs by W12 | LP + funnel | reg pace tracked | Kavin
03 Aug | Mon | W10 | WS-8 | Janani+Vimal | G-7 customer leverage guide v1 — how partner uses our evidence | g7-leverage-guide-v1.docx | G-7 draft from eng | Contractor pass · zero 'validated' | Vimal+Contractor | ⚠
03 Aug | Mon | W10 | WS-8 | Janani+Contractor | Validation Enablement Kit final assembly + Contractor zero-finding pass | enablement-kit-final.zip | 5 templates | Contractor zero · Vimal sign-off | Vimal+Contractor | ⚠
03 Aug | Mon | W10 | WS-9 | Contractor+Vimal | CHANGE-CONTROL FREEZE — no new product claims without Contractor + Vimal pre-sign | CC-freeze memo | Audit #3 | Documented · acked by all 5 owners | Vimal+Contractor | ⚠
05 Aug | Wed | W10 | WS-2 | Vimal+Droupathy | Analyst briefing #3 — Pharma IQ / Pharma Manufacturer Mag | briefing held | press kit | Briefing + follow-up | Vimal
07 Aug | Fri | W10 | WS-2 | Vimal+Contractor | Op-ed #3 submission — Verifiable systems for founders · TC/VentureBeat | submitted op-ed-3 | Contractor pass | Editorial ack 7 days | Vimal
10 Aug | Mon | W11 | WS-1 | Droupathy+Manoj | Execute verified-rollout-checklist across web/decks/email/LP | 45 assets refreshed | rollout checklist | Each Contractor-reviewed | Droupathy | ⚠
10 Aug | Mon | W11 | WS-2 | Vimal | Podcast #3 recorded — biotech founders pod | recorded | approved talking points | Live within 14 days | Vimal
10 Aug | Mon | W11 | WS-4 | Manoj+Janani | Evidence pack download LP (gated) — G-7 TOC + leverage guide | LP LIVE | G-7 draft from eng | Gated · zero 'validated' lang | Manoj+Janani | ⚠
10 Aug | Mon | W11 | WS-6 | Janani+Vimal | Partner #1 onboarding + co-validation prep — share G-7 draft sections | partner onboarded | G-7 sections | Partner audit-ready by W14 | Janani+Vimal
12 Aug | Wed | W11 | WS-8 | Janani+Droupathy | Enablement kit TOC 1-pager — for prospects | kit-toc.pdf | kit assembly | Contractor pass | Vimal
14 Aug | Fri | W11 | WS-3 | Droupathy+Kavin | Newsletter #4 — Verification status snapshot | newsletter-4 in ArkOS | Pillar 5 + G-7 progress | >40% open rate | Vimal
17 Aug | Mon | W12 | WS-2 | Vimal | Podcast #4 recorded — India biotech/pharma founders pod | recorded | approved | Live within 14 days | Vimal
17 Aug | Mon | W12 | WS-3 | Janani+Droupathy+Contractor | Pillar #6 draft — Inside our verified evidence pack (post-cleared) | pillar-6-draft.docx | G-7 pack draft | Contractor ZERO 'validated' lang | Vimal | ⚠
17 Aug | Mon | W12 | WS-4 | Manoj+Droupathy | Verified-rollout sweep on web — remove any 'compliant' copy | sweep report | WS-1 rollout doc | Contractor zero-finding pass | Vimal+Contractor | ⚠
17 Aug | Mon | W12 | WS-8 | Janani | G-7 Evidence Pack TOC 1-pager — for prospects + auditors | g7-toc.pdf | G-7 13-section index | Contractor pass | Vimal+Contractor
17 Aug | Mon | W12 | WS-9 | Contractor+Vimal | COMPLIANCE AUDIT #4 (pre-go-live) — every GO-LIVE asset · PR #4 · LP · newsletter #5 · LinkedIn Live · investor letter · partner case study | audit-4-report.pdf | All GO-LIVE assets staged | Zero violations · partner consent confirmed · GREEN GO-LIVE | Vimal+Contractor | ⚠
19 Aug | Wed | W12 | WS-2 | Vimal+Contractor | Op-ed #4 — AI Act for pharma providers · BioPharma Reporter | submitted op-ed-4 | Contractor pass | Editorial ack 5 days | Vimal
19 Aug | Wed | W12 | WS-7 | Vimal+Partner+Droupathy | Webinar #3 live — Founding Partner story (HARD GATE: ArkOS consent) | webinar #3 recorded | 500+ regs · consent · Audit #3 | 200+ live · zero unconsented · approval to publish | Vimal+Partner | ⚠
20 Aug | Thu | W12 | WS-7 | Droupathy | Webinar #3 replay + assets (partner-approved) | replay + assets | partner consent renewed | Published 48hr | Droupathy+Partner
21 Aug | Fri | W12 | WS-3 | Manoj+Droupathy | Pillar #6 published — gated download · qualified leads only | pillar-6 LIVE | draft signed + Contractor | Schema · gated | Manoj | ⚠
24 Aug | Mon | W13 | WS-2 | Vimal | Podcast #5 recorded — AI in regulated industries pod | recorded | approved | Live within 14 days | Vimal
27 Aug | Thu | W13 | WS-7 | Vimal+Droupathy | India QA Heads Roundtable — invitation-only · 12 attendees · Mumbai/Hyderabad | roundtable held | invite list · venue · agenda | 8+ attend · 3+ DP follow-ups | Vimal | ⚠
28 Aug | Fri | W13 | WS-2 | Droupathy+Legal | PR #3 — Evidence pack + Kit delivered (HARD GATE: G-7 + ArkOS consent) | PR #3 IFF gates | G-7 + ArkOS consent | 3 gates pass OR PR held | Vimal+Legal+Partner
28 Aug | Fri | W13 | WS-5 | Kavin | Pre-launch QA — all paid campaigns · sequences · lead routing under load | QA report | All campaigns | Zero ICP missed · zero false routing | Kavin | ⚠
28 Aug | Fri | W13 | WS-6 | Vimal+Janani+Partner | Partner #1 GO-LIVE readiness review — verification evidence walkthrough | go-live readiness sign-off | G-7 + G-8 + partner | Partner signs off Phase 2 start | Vimal+Partner | ⚠
28 Aug | Fri | W13 | WS-8 | Janani+Vimal | Production sales kit assembly — all 1-pagers + decks + video + scripts + obj bank | production-sales-kit-v1.zip | All above | Vimal+Contractor sign-off | Vimal | ⚠
28 Aug | Fri | W13 | WS-8 | Janani+Vimal | Enablement Kit delivered to founding partner (with G-7) | kit delivered | G-7 + kit | Partner ack receipt + Q&A scheduled | Vimal+Janani | ⚠
31 Aug | Mon | W14 | WS-1 | Vimal | GO-LIVE narrative final lock — press splash · founder long-form · investor letter | go-live-narrative-LOCKED.docx | Audit #4 | Triple-reviewed Vimal+Contractor+Legal | Vimal | ⚠
31 Aug | Mon | W14 | WS-4 | Manoj+Droupathy | GO-LIVE landing page staging — verified version live with founding DP | GO-LIVE LP staging | PR #4 narrative | Triple-reviewed Vimal+Contractor+Legal | Vimal | ⚠
31 Aug | Mon | W14 | WS-7 | Droupathy | GO-LIVE event production — LinkedIn Live · run-of-show · speaker pack | GO-LIVE event plan | PR #4 narrative | Triple-reviewed · tech rehearsal done | Vimal | ⚠
31 Aug | Mon | W14 | WS-9 | Vimal+Contractor | FINAL PRE-LAUNCH SIGN-OFF (T-1) — every GO-LIVE artifact triple-reviewed | final-signoff-memo.pdf | Audit #4 passed | Vimal+Contractor+Legal triple-sign | Vimal+Contractor+Legal | ⚠
01 Sep | Tue | W14 | WS-1 | Vimal | Publish GO-LIVE narrative across all channels simultaneously (0001 IST) | PR · LI · email · web · investor letter | All locked | Synchronized launch | Vimal | ⚠
01 Sep | Tue | W14 | WS-2 | Droupathy+Vimal+Legal | PR #4 GO-LIVE — CONDITIONAL on W12 eng + W14 verif + ArkOS consent | PR #4 conditional release | W12 eng + W14 verif + consent + Audit #4 | 3 conditions OR fallback | Vimal+Legal+Eng+Partner | ⚠
01 Sep | Tue | W14 | WS-3 | Droupathy+Kavin | Newsletter #5 — GO-LIVE special | newsletter-5 in ArkOS | GO-LIVE PR live | >45% open rate | Vimal | ⚠
01 Sep | Tue | W14 | WS-4 | Manoj | GO-LIVE LP push to prod · synchronized with PR #4 (0001 IST) | GO-LIVE LP LIVE | staged + signed | Synchronized launch | Manoj+Vimal | ⚠
01 Sep | Tue | W14 | WS-5 | Kavin | GO-LIVE campaign — paid + email + retargeting synchronized with PR | GO-LIVE campaign LIVE | PR #4 timing | Synchronized · 24hr push window | Kavin+Vimal | ⚠
01 Sep | Tue | W14 | WS-6 | Vimal+Janani+Partner | Partner #1 GO-LIVE — verified version · partner validation begins at their site | go-live ceremony | all above | Partner active · validation underway | Vimal+Partner | ⚠
01 Sep | Tue | W14 | WS-7 | Vimal+Droupathy+Partner | GO-LIVE LinkedIn Live event — 1hr + Q&A · synchronized with PR #4 | GO-LIVE event LIVE | PR #4 · plan | 500+ live · 2K+ replay in 7 days | Vimal | ⚠
01 Sep | Tue | W14 | WS-8 | Janani | Production sales kit pushed to all reps + ArkOS | sales kit ACTIVE | All locked | 100% GO-LIVE+ DP conversations | Janani | ⚠
04 Sep | Fri | W14+ | WS-2 | Vimal | LI long-form #4 — The 14 weeks that built Verixa | LI Article 3000+w | PR #4 live | 25K+ in 72hr | Vimal