## Master Timeline
VERIXA PILOT — MASTER TIMELINE (Demo-ready version -> Verified version)
Start 01-Jun-2026 ¦ Demo-ready: HARD-LOCKED 26-Jun (W4) ¦ Verified version TARGET 01-Sep (buffer to 15-Sep) ¦ Model: Verixa verifies; design partner validates ¦ Status: all PLANNED (no executed evidence)
ID | Phase | Workstream | Task | Owner (role) | Start | End | Dependency | Evidence / Gate | W1 Jun 01 | W2 Jun 08 | W3 Jun 15 | W4 Jun 22 | W5 Jun 29 | W6 Jul 06 | W7 Jul 13 | W8 Jul 20 | W9 Jul 27 | W10 Aug 03 | W11 Aug 10 | W12 Aug 17 | W13 Aug 24 | W14 Aug 31 | W15 Sep 07 | W16 Sep 14
D1 | Phase 1 — Demo-ready | Decision | Approve VRX-PILOT-001 (IUS) + VRX-PILOT-002 (Scope Matrix) | Founder+QA | 2026-06-01 | 2026-06-05 | - | Signed V1/V2 (unlock)
A0 | Phase 1 — Demo-ready | SDLC | AI-assisted-dev control: human review evidence + CI gates | Eng Lead+QA | 2026-06-01 | 2026-06-12 | - | SDLC control evidence
CI | Phase 2 — Verified version | SDLC | Stand up CI verification-gate (CLAUDE.md gates) - auto evidence capture | Eng Lead+DevOps | 2026-06-01 | 2026-06-12 | - | CI gate live + evidence retained
PDF | Phase 2 — Verified version | Decision | Decide PDF generation library (shared WP-12 + WP-13) | Eng Lead | 2026-06-01 | 2026-06-05 | - | PDF approach locked
D2 | Phase 1 — Demo-ready | Demo | Eval env stand-up (segregated tenant/infra, synthetic data) | DevOps+FS0.5 | 2026-06-01 | 2026-06-12 | - | Eval env + segregation checklist
D3 | Phase 1 — Demo-ready | Demo | Wire all-six demo flows (stubs where backend incomplete) | Product+FS0.5 | 2026-06-08 | 2026-06-26 | D2 | Demo script v1/v2
D4 | Phase 1 — Demo-ready | Demo | G-DEMO segregation gate (QA-checked, enforced) | QA | 2026-06-22 | 2026-06-26 | D2 | Signed G-DEMO -> demo live
DL | Phase 1 — Demo-ready | MILESTONE | DEMO-READY [HARD-LOCKED 26-Jun] - fixed commercial date | Founder+Product | 2026-06-22 | 2026-06-26 | D4 | Demo live 26-Jun-2026 |  |  |  | ◆
D5 | Phase 1 — Demo-ready | Commercial | Customer identification + onboarding; design-partner LOI | Founder/Commercial | 2026-06-01 | 2026-08-28 | - | LOI / named validation owner
V1 | Phase 2 — Verified version | MIRA V7 (AI provider) | V7 A: feature inventory, intended/prohibited use, risk, EU AI Act | AI Owner (QA1) | 2026-06-01 | 2026-06-05 | - | V7 sec A
V2 | Phase 2 — Verified version | MIRA V7 (AI provider) | V7 B: control matrix, oversight, output control, audit events, test coverage | QA1 | 2026-06-08 | 2026-06-12 | V1 | V7 sec B
V3 | Phase 2 — Verified version | MIRA V7 (AI provider) | V7 C: set acceptance thresholds + monitoring + supplier needs | QA1 | 2026-06-15 | 2026-06-19 | V2 | V7 thresholds set
V4 | Phase 2 — Verified version | MIRA V7 (AI provider) | V7 D: readiness gate + handoffs (CSV/CSA, Test, DI) | QA1->QA | 2026-06-22 | 2026-06-26 | V3 | V7 plan approved
P1 | Phase 2 — Verified version | Integrity core | WP-4 e-sig substrate verification (change-control, RCA, batch) | FS-1 | 2026-06-08 | 2026-06-12 | V1/V2 | Part 11 e-sig evidence
P2 | Phase 2 — Verified version | Integrity core | WP-13b fail-closed LLM audit (no un-audited inference) | FS-2 | 2026-06-08 | 2026-06-12 | V1/V2 | AI audit evidence
P3 | Phase 2 — Verified version | Platform | WP-2 event-spine linkage subset (in-scope only) | FS-1+FS-2 | 2026-06-15 | 2026-06-19 | V1/V2 | Event coverage test
P4 | Phase 2 — Verified version | Platform | WP-1 single-tenant/site lock (scope-switch disabled) | FS0.5+DevOps | 2026-06-15 | 2026-06-19 | V1/V2 | Config + P6 test plan
P5 | Phase 2 — Verified version | Integrity core | Integration + staging smoke (integrity core) | All eng | 2026-06-22 | 2026-06-26 | P1-P4 | Smoke evidence
GJ | Phase 2 — Verified version | GATE | G-JUN exit gate: integrity core + V7 + demo + O3 | Founder+QA | 2026-06-29 | 2026-07-03 | P5,V4 | Go/No-Go into July |  |  |  |  | ◆
KC | Phase 2 — Verified version | GATE | W6 KILL-CHECK: WP-4/13b + LOI + G-8 + hires + WP-12/13 design | Founder+QA | 2026-07-06 | 2026-07-10 | - | >=2 red => narrow/re-baseline | [5 empty] | ◆
CN | Phase 2 — Verified version | Capacity | Onboard fractional CSV/CSA + RA contractor (REQUIRED) | Founder+QA | 2026-06-01 | 2026-06-12 | - | Contractor engaged
O1 | Phase 2 — Verified version | O3 Supplier | Evidence request - Anthropic + Azure (SOC2/ISO/DPA/model cards) | QA2/Proc | 2026-06-01 | 2026-06-05 | - | Request log
O2 | Phase 2 — Verified version | O3 Supplier | Supplier evidence assessment vs risk criteria | QA2 | 2026-06-08 | 2026-06-19 | O1 | Gap log
O3 | Phase 2 — Verified version | O3 Supplier | Supplier risk rating + QA disposition | QA | 2026-06-22 | 2026-06-26 | O2 | Supplier disposition
O4 | Phase 2 — Verified version | O3 Supplier | Finalize qualification / handoff Supplier Quality (G-7 s10) | QA2 | 2026-08-03 | 2026-08-14 | O3 | Supplier qual evidence
B1 | Phase 2 — Verified version | Build (agentic) | WP-6 Document Control core (persist+hash, distribution, read-ack) | FS-1 | 2026-07-06 | 2026-07-17 | RC scope | Built + unit
B2 | Phase 2 — Verified version | Build (agentic) | WP-7 Deviation gaps (critical co-sign as scoped) | FS-2 | 2026-07-06 | 2026-07-10 | - | Built + unit
B3 | Phase 2 — Verified version | Build (agentic) | WP-8 RCA substrate-verify approve + CAPA handoff | FS-1 | 2026-07-13 | 2026-07-17 | WP-4 | Built + unit
B4 | Phase 2 — Verified version | Build (agentic) | WP-9 CAPA effectiveness e-sig + closure-on-open-actions | FS-2 | 2026-07-13 | 2026-07-17 | - | Built + unit
B5 | Phase 2 — Verified version | Build (agentic) | WP-10 Findings -> CAPA gate (pulled to W7: WP-12 depends on it) | FS-1 | 2026-07-13 | 2026-07-17 | WP-2 | Built + unit
B6 | Phase 2 — Verified version | Build (agentic) | WP-12 Inspection export (FRONT-LOADED, +build hand) | FS-2+Hire1 | 2026-07-13 | 2026-07-24 | - | Built + unit
B7 | Phase 2 — Verified version | Build (agentic) | WP-13 MIRA guardrails + PDF (FRONT-LOADED, +build hand) | Hire1+AI | 2026-07-13 | 2026-07-24 | WP-13b | Built + unit
BH | Phase 2 — Verified version | Capacity | +1 build hand (REQUIRED, confirm W5) - WP-12/scorecard/tests ONLY, not integrity core | Founder+Eng | 2026-06-29 | 2026-07-31 | - | Hire confirmed W5
EB | Phase 2 — Verified version | Verification | Per-workflow evidence burndown (weekly, W7->W14) | QA+contractor | 2026-07-13 | 2026-09-04 | - | Weekly burndown status
RC | Phase 2 — Verified version | GATE | Release Candidate freeze (VRX-REL-001) | Eng+QA | 2026-07-27 | 2026-07-31 | B1-B7 | RC frozen + declared | [8 empty] | ◆
C0 | Phase 2 — Verified version | Freeze | Code + change-control freeze (defects only) | All | 2026-08-03 | 2026-09-04 | RC | Freeze in effect
C1 | Phase 2 — Verified version | Verification | Verification testing six workflows (unit/integ/E2E/regression) | Eng+QA | 2026-08-03 | 2026-08-21 | RC | Verification evidence (G-7 s6)
C2 | Phase 2 — Verified version | Verification | Part 11 control evidence (e-sig/audit/RLS/access) | QA | 2026-08-03 | 2026-08-14 | - | G-7 s7
C3 | Phase 2 — Verified version | Verification | Tenant isolation (P6) + penetration test | Security/DevOps+QA | 2026-08-03 | 2026-08-21 | - | G-7 s8
C4 | Phase 2 — Verified version | Verification | DR backup/restore test | DevOps+QA | 2026-08-10 | 2026-08-14 | - | DR evidence
C5 | Phase 2 — Verified version | Verification | Controlled defect fix | Eng | 2026-08-10 | 2026-08-28 | C1 | Defect closure
V5 | Phase 2 — Verified version | MIRA V7 (AI provider) | MIRA guardrail verification (starts as guardrails land, W8/W9->W12) | QA1+Eng | 2026-07-20 | 2026-08-21 | B7 | AI test evidence
V6 | Phase 2 — Verified version | MIRA V7 (AI provider) | MIRA AI provider assurance pack finalize (G-7 s9) | AI Owner | 2026-08-17 | 2026-08-28 | V5 | AI provider pack
G8a | Phase 2 — Verified version | G-8 Agreement | G-8 draft (W1) + commercial/legal alignment by end June | QA+RA+counsel | 2026-06-01 | 2026-06-26 | - | Draft agreement
G8b | Phase 2 — Verified version | G-8 Agreement | Quality agreement SIGNED (no later than RC freeze) | Founder+QA+Partner | 2026-07-27 | 2026-07-31 | G8a,LOI | Signed agreement (hard gate)
G7o | Phase 2 — Verified version | G-7 Assurance | G-7 assurance pack OUTLINE + enablement kit drafted | QA(+contractor) | 2026-06-01 | 2026-06-12 | - | Pack outline + kit templates
G7 | Phase 2 — Verified version | G-7 Assurance | G-7 populated CONTINUOUSLY from W7 as evidence lands; W10-13 = closure not first authoring | QA(+contractor) | 2026-07-13 | 2026-08-28 | - | G-7 delivered
EK | Phase 2 — Verified version | G-7 Assurance | Customer Validation Enablement Kit (URS/IQOQPQ/RTM/limits) | QA+contractor | 2026-07-13 | 2026-08-21 | - | Enablement kit
GO | Phase 2 — Verified version | GATE | Go-live acceptance gate G-1..G-9 (integrity core+AI pack+O3+sec+pack+agreement) | Founder+QA | 2026-08-31 | 2026-09-04 | all | Production-ready sign-off | [13 empty] | ◆
MV | Phase 2 — Verified version | MILESTONE | TARGET: VERIFIED VERSION go-live Sep 1 | Founder+QA | 2026-09-01 | 2026-09-01 | GO | Target go-live Sep 1 2026 | [13 empty] | ◆
BUF | Phase 3 — Partner validation | BUFFER | BUFFER ONLY (Sep 1-15): per-workflow slip / defect closure / verification catch-up | Founder+QA | 2026-09-01 | 2026-09-15 | - | Contingency, NOT a baseline
BS | Phase 3 — Partner validation | MILESTONE | HARD BACKSTOP Sep 15 (close or defer to wave) | Founder+QA | 2026-09-15 | 2026-09-15 | BUF | Sep 15 2026 backstop | [15 empty] | ◆
Z1 | Phase 3 — Partner validation | Go-live | Production deployment to design partner | Eng+QA | 2026-09-01 | 2026-09-01 | GO | Deployed Sep 1
Z2 | Phase 3 — Partner validation | Partner validation | Design partner IQ/OQ/PQ + intended-use validation (their site) | Design Partner | 2026-09-01 | 2026-09-01 | G7,G8b | Sep+ after production deployment
Z3 | Phase 3 — Partner validation | Phase-2 backlog | RCA auto-handoff, training auto-trigger, dashboard, scope enforce (change-controlled) | Eng | 2026-08-31 | 2026-09-04 | - | Phase-2 waves (Sep+)
Legend: | Demo (Phase 1) | Build/Verify (Phase 2) | MIRA V7 / AI provider | Supplier/Agreement/Assurance | Gate/Milestone | Phase 3 / Freeze

## Milestones & Gates
MILESTONES & GATES
Gate / Milestone | Week | Date | What it proves | Owner
G-DEMO — demo segregation gate | W4 | 22-Jun-2026 | Eval env segregated, synthetic-only, watermarked, no record-of-record | QA
MILESTONE: DEMO-READY (HARD-LOCKED 26-Jun-2026) | W4 | 26-Jun-2026 [LOCKED] | Fixed, non-movable commercial commitment. All-six + MIRA demoable. G-DEMO segregation must pass by this date | Founder+Product
G-JUN — June exit Go/No-Go | W5 | 30-Jun-2026 | Integrity core (WP-4,WP-13b) built+tested; V7 approved; O3 rated; demo live | Founder+QA
W6 KILL-CHECK | W6 | 06-Jul-2026 | WP-4/13b built+evidence-started; LOI signed-or-legal; G-8 in review; build hand + contractor confirmed; WP-12/13 design ready. >=2 red => narrow/re-baseline | Founder+QA
RC freeze | W9 | 31-Jul-2026 | Release Candidate frozen + declared (VRX-REL-001) | Eng+QA
Change-control freeze | W10 | 03-Aug-2026 | No new features; defects only via deviation process | QA
G-8 quality agreement SIGNED | W9 | 31-Jul-2026 | Validation-responsibility split signed by RC freeze (hard gate; draft in W1) | Founder+QA+Partner
G-7 assurance pack delivered | W13 | 28-Aug-2026 | Leverageable verification evidence pack issued to partner | QA
Go-live acceptance (G-1..G-9) | W14 | 31-Aug-2026 | Integrity core verified + MIRA provider pack + O3 + security + pack + agreement | Founder+QA
MILESTONE: VERIFIED VERSION / GO-LIVE (TARGET) | W14 | 01-Sep-2026 | Target go-live. Production-verified workflows deployed to design partner | Founder+QA
BUFFER (contingency only) | W15-16 | 01-15 Sep 2026 | Sep 1-15 buffer for per-workflow slip / defect closure / verification catch-up. NOT a planning baseline | Founder+QA
HARD BACKSTOP | W16 | 15-Sep-2026 | Any workflow not production-verified by Sep 15 -> deferred to a change-controlled wave | Founder+QA
GO-LIVE RULE (per-workflow) | W14 | 01-Sep-2026 | A workflow goes live ONLY if built + verification-tested + in G-7 + in signed G-8 + no open integrity/AI/security/supplier blocker; else disabled/demo-only | Founder+QA
Design-partner validation (Sept+) | post | Sep-2026+ | Partner executes IQ/OQ/PQ + intended-use validation at their site | Design Partner

## Owners & Capacity
OWNERS & CAPACITY (confirmed 2026-05-31)
Team: 2 full-stack + 0.5 full-stack (2.5 FS eng) ¦ 1 DevOps ¦ 2 QA. No dedicated AI Owner/RA/Validation Lead — carried by QA + Founder. Build via Claude Code + Cursor agents.
Workstream | Skill needed | Est. load | Assigned (role) | Lane
WP-4 e-sig verify | Backend (auth/e-sig) | M ~4d | FS-1 | Eng
WP-13b fail-closed AI audit | Backend + AI | M ~4d | FS-2 | Eng
WP-2 linkage subset | Backend (events) | L ~8d | FS-1+FS-2 | Eng
WP-1 single-tenant lock | Backend + config | M ~4d | FS0.5+DevOps | Eng/Infra
Demo env + segregation + polish | Infra + FE | M ~5d | DevOps+FS0.5 | Infra
July six-workflow build | Backend (agentic) | XL | FS-1+FS-2 + agents | Eng
Aug verification testing | Eng + QA | L | Eng+QA | Verify
MIRA V7 / AI provider pack | AI Owner (-> QA1) | L ~8d | QA-1 | QA
O3 supplier qualification | QA/Procurement | S ~2d | QA-2 | QA
G-7 assurance pack | QA (+contractor) | L | QA+contractor | QA
G-8 quality agreement | QA+RA+counsel | M | QA+counsel | QA/Legal
Capacity verdict:
• June = feasible (eng headroom). Agentic build makes July six-workflow build plausible.
• Binding relief: design partner performs VALIDATION (IQ/OQ/PQ) -> internal validation ceiling lifted.
• Verixa-side hard items remain: integrity core, MIRA AI provider pack, O3, security, G-7 pack, G-8 agreement.
• Critical path (7): WP-4, WP-13b, MIRA provider pack, O3 supplier qual, security+isolation, G-7, G-8. Miss any -> narrow go-live scope.
• Go-live rule is PER-WORKFLOW: ship only fully-evidenced workflows; disable/demo-only the rest.
• REQUIRED (not optional): +1 fractional CSV/CSA + RA contractor for G-7 pack, G-8 agreement, enablement kit. 2 QA cannot own all assurance lanes alone.

## Phase & Responsibility
PHASE MODEL & RESPONSIBILITY SPLIT
PHASES
Phase | When | What
Phase 1 — Demo-ready version [HARD-LOCKED 26-Jun-2026] | June (W1-W4) | FIXED DATE. Segregated eval env; all-six + MIRA; synthetic data; drives customer identification + onboarding. Not validated, labelled evaluation. G-DEMO must pass by 26-Jun.
Phase 2 — Verified version | Jun-Aug -> TARGET 01-Sep (buffer to 15-Sep) | Production system built under controlled SDLC; Verixa internal verification + testing only; supplier assurance pack (G-7) + signed quality agreement (G-8). Target go-live Sep 1; Sep 1-15 buffer is contingency only, not a baseline.
Phase 3 — Partner validation | Sep+ | Design partner performs validation (CSV/CSA, IQ/OQ/PQ, intended use) at their site, leveraging G-7. Phase-2 backlog rolls out under change control.
RESPONSIBILITY SPLIT — Verixa verifies; Design Partner validates
Area | Verixa (supplier) — verifies | Design Partner — validates
Controlled SDLC + AI-dev controls | Owns | Assesses in supplier qualification
Requirements | Product URS/FS/DS | Intended-use URS / user requirements
Testing | Verification (unit/integ/E2E/regression) | Leverages as supplier evidence
Validation (IQ/OQ/PQ, summary) | Does NOT execute | Owns + signs in their environment
Part 11 controls (e-sig/audit/RLS) | Owns working controls + evidence | Validates for their Part 11 needs; owns 11.100(c) cert
MIRA / AI governance | Owns PROVIDER obligations | Owns DEPLOYER obligations; validates AI for their use
Sub-suppliers (Anthropic/Azure) | Owns qualification | May request evidence
Security (pen-test, isolation, DR) | Owns evidence | Reviews; may run own assessment
Assurance evidence pack (G-7) | Owns + provides | Consumes to accelerate validation
SOPs / training | Product operating guidance | Owns controlled SOPs + user training
Language guard: Verixa states "verified under controlled SDLC; customer validates intended use" — NEVER "validated".

## Notes & Sources
NOTES, EVIDENCE DISCIPLINE & SOURCES
Status | All tasks PLANNED. No executed evidence. Implementation/verification of WP-4, WP-13b, six workflows, MIRA governance, O3, pen-test, tenant isolation, DR = Unknown — evidence required.
Skills applied | pharma-biotech-saas-head-of-qa (disposition) + verixa-ai-validation-governance-expert (MIRA provider). Rendered via xlsx skill.
Critical-path long poles | MIRA V7 AI provider pack (Wk1 start), O3 supplier qualification (external), G-7 assurance pack, G-8 signed agreement, pen-test/DR scheduling.
Hard dependency | G-8 cannot finalize without a named design partner + LOI. G-7 sections move off 'Unknown' only with executed evidence + QA disposition.
Capacity | 2.5 FS eng + 1 DevOps + 2 QA + agentic coding. REQUIRED: +1 fractional CSV/CSA + RA contractor for G-7, G-8, evidence pack, enablement kit, Part 11 framing. + REQUIRED +1 build hand (WP-12/WP-13).
Regulatory — FDA CSA | FDA, Computer Software Assurance for Production and Quality Management System Software — issued 03-Feb-2026; supersedes 24-Sep-2025 final guidance (verified via fda.gov).
Regulatory — GAMP 5 | ISPE GAMP 5 Guide, 2nd Edition (2022) — supplier leverage, service/cloud, AI/ML, critical thinking.
Regulatory — EU AI Act | Reg. (EU) 2024/1689; GPAI provider rules effective Aug-2025 — MIRA provider obligations non-delegable.
Disclaimer | Advisory. Final go/no-go + risk acceptance are human QA + Founder decisions. Not legal, not validation, not inspection clearance. Read-only — no Verixa repo files modified.