## Overview
Verixa — India Pilot Launch Playbook
Owner Seat | Vimal — Founder, Chairman & MD, Aeonn Ark Group
Date | 2026-04-25
Pilot market | India only (Founder LOCK)
Launching entity | NOT Verixa Inc (USA) — Indian entity to launch and contract
Regulatory perimeters | US FDA + India only — NO EU
Rationale | Indian customer base; product must support US FDA-compliant workflows — Indian sponsors manufacturing/testing for US export are FDA-inspected, and Verixa as vendor system is downstream-inspected via the customer
Founder Advisor verdict | PASS — CEG-positive (capital exposure capped; no EU AI Act/Annex 22/GDPR cost) and Revenue-Orientation-positive (closeable beats complete; Indian sponsor pipeline = fastest path to first paid revenue)
Estimated savings from EU exclusion | ~30% of prior parallel-track effort; ~40% of certification cost line
Companion docs (S2/S3 future use) | Verixa_Commercial_Launch_Readiness_2026-04-25; Verixa_Parallel_Workstreams_While_Engineering_2026-04-25
Source file | Verixa_India_Pilot_Launch_Playbook_2026-04-25.md

## F0 Entity Options
F0 — The One Founder Decision That Unblocks Everything
Companion lock: inbound IP license + services agreement at arm's length (transfer-pricing safe). CFO + CLO to draft within 30 days of F0 lock.
Option | Launching Entity | Pros | Cons | Recommendation
A | Aeonn Health Pvt Ltd (existing) | Zero new incorporation; matches doctrine path 'Verixa lives in Aeonn Health → Navira → Verixa'; uses existing GST/PAN/banking | Co-mingles Verixa P&L with broader Aeonn Health verticals; harder unit economics; future carve-out friction | Default if speed matters
B | Navira Healthcare Pvt Ltd (Unknown — confirm whether Navira is a separate Indian entity or only a brand) | Cleaner P&L; stronger brand alignment; pre-positions for spin-out | +30–45 days incorporation if not existing; new GST/PAN/banking onboarding | Recommended if Navira-India already incorporated
C | New Verixa India Pvt Ltd (incorporate fresh) | Cleanest carve-out; investor-friendly; mirrors Verixa Inc structure | 45–60 days incorporation + onboarding; new tax registrations; new bank account; fresh inter-co agreements | Recommended if optionality for outside capital dominates

## EU Deferred
Section 1 — What Drops From the Plan (EU Exclusion)
Item Removed | Reason
GDPR Art. 28 DPA + RoPA EU lens + EU SCCs (Modules 2 & 3) | No EU customers
UK GDPR addendum + UK ICO + UK Representative | No UK customers
EU Representative (Art. 27 GDPR) | No EU establishment needed
EU GMP Annex 11 attestation (still mapped in product; no certification push) | India + US FDA cover same control surface
EU GMP Annex 22 (AI/ML) conformity | Not in scope
EU AI Act risk classification + conformity assessment | Not in scope
EMA / MHRA inspection readiness pack | Not in scope
EU residency hosting region | Not in scope
ISO 13485 (medical device QMS) | Optional anyway; defer
ISO/IEC 42001 (AI MS) | Defer to S2 (US enterprise & EU re-entry)
Trade-shows: ISPE Annual EU, PDA EU, CPHI Worldwide | Defer; replace with India equivalents
Trademark filings: EU + UK + Madrid | Defer; file India + US first

## Surviving Tracks
Section 2 — What Survives & Gets India-First Flavor
Track | Why Still Required | India-First Adjustment | Status
US FDA 21 CFR Part 11 | Indian sponsors with US-bound batches/clinical data are FDA-inspected | Keep full Part 11 controls; produce Part 11 Compliance Statement | KEEP
US FDA Computer Software Assurance (CSA) | Same logic | Keep alignment statement | KEEP
GAMP 5 Category 5 | Universal validation framework; Indian sponsors expect it | Keep | KEEP
ICH Q9 / Q10 | Universal | Keep | KEEP
CDSCO + Schedule M v2024 | Primary regulatory perimeter for India pharma | VX-CDSCO-001 becomes marquee artifact | PRIMARY TRACK
DPDPA 2023 | Primary privacy framework for India | Replace GDPR-first lens | PRIMARY TRACK
HIPAA BAA-readiness | No US customers in pilot | Defer | DEFER to S2
SOC 2 Type II | US enterprise demand driver | Defer; consider SOC 2 Type I as cheaper interim if Indian buyer asks | DEFER to S2
ISO 27001 | Indian enterprise procurement gate | Indian-affiliated TIC body (BSI India / TÜV India / DNV / Bureau Veritas India / Intertek India) | KEEP
ISO 9001:2015 | Indian enterprise procurement gate | Keep | KEEP
CERT-In | India sectoral cyber-incident reporting (6-hour rule) | Must add | NEW TRACK
MeitY / Cloud / Data localization | India regulatory expectation (likely sectoral) | Must add | NEW TRACK

## India Reg Stack
Section 3 — Indian Regulatory & Compliance Stack (Full List)
# | Item | Lead Time | Owner | Notes
IN-1 | VX-CDSCO-001 — India pharma compliance bundle | 10 days | CHO + CLO | Marquee artifact; flagged 10-day blocker for Indian sponsor onboarding
IN-2 | Schedule M v2024 alignment evidence | 14 days | CHO + CQCO | Map URS-001…035 controls to Schedule M Annexure I
IN-3 | CDSCO eSubmission readiness (e-Office, SUGAM, CDSCO Online) | 30 days | CHO + CTO | Where Verixa exports records to CDSCO portals
IN-4 | DPDPA 2023 §11 controls (consent, notice, processing principles) | 30 days | CLO + CISO | EXEC_SUMMARY flagged 10% framework coverage; close to 100%
IN-5 | DPDPA 2023 §16 controls (data principal rights workflow) | 30 days | CLO + CCO | Was PARTIAL per EXEC_SUMMARY
IN-6 | DPDPA Significant Data Fiduciary (SDF) self-classification | 14 days | CLO + CISO | If SDF: heavier obligations incl. DPO + DPIA + audit
IN-7 | DPO appointment (India) | 30 days | CPO + CLO | Likely required even pre-SDF
IN-8 | CERT-In incident reporting integration | 21 days | CISO + CTO | 6-hour reporting rule; build into IRP
IN-9 | MeitY data-localization assessment + sectoral hosting in India | 21 days | CISO + CTO | Pick India CSP region (AWS Mumbai/Hyderabad, Azure India, GCP Mumbai/Delhi, or Indian sovereign cloud)
IN-10 | GST registration (state-wise + IGST for inter-state SaaS billing) | 14 days | CFO | Depends on F0 entity lock
IN-11 | Equalization Levy / Section 194-O assessment | 14 days | CFO + CLO | If billing flows from Indian entity to international IP holder
IN-12 | Indian withholding-tax + transfer-pricing position on intercompany IP/services flows | 21 days | CFO + CLO | Critical given F0 entity choice
IN-13 | Trademark — Verixa™ India (all relevant classes) | 30–60 days to file; 12–18 months to register | CLO | Class 9 + Class 42 minimum
IN-14 | Domain portfolio — .in, .co.in, .health.in | 7 days | CMO | Add to existing portfolio
IN-15 | FEMA position on receipts in INR vs USD billing | 14 days | CFO + CLO | Indian entity → Indian customers: INR-only is cleanest
IN-16 | MSA (India law-governed) + DPA (DPDPA-aligned) + SLA (INR credit) | 30 days | CLO | India-only versions
IN-17 | Indian counsel of record (corporate, IP, pharma-regulatory, privacy) | 14 days | CLO + Founder | Approve panel
IN-18 | Cyber insurance — India market | 30–60 days | CFO + CISO | Indian broker; INR tower; CFO sets size
IN-19 | Indian Pharmacopoeia (IP) + WHO-GMP cross-references | 21 days | CHO | Buyer-facing one-pager
IN-20 | Drugs and Cosmetics Act + Rules alignment statement | 14 days | CLO + CHO | —

## FDA Items
Section 4 — US-FDA Boundary Items (kept for Indian-customer use)
# | Item | Lead Time | Owner | Notes
FDA-1 | 21 CFR Part 11 Compliance Statement + e-sig validation evidence | 21 days | CQCO | Bundle into Customer Audit Pack
FDA-2 | CSA (Sept-2022 draft guidance) alignment statement | 14 days | CQCO + CTO | Sponsor-facing one-pager
FDA-3 | GAMP 5 Cat 5 declaration | 14 days | CQCO | Already implied in VX-SDLC-002
FDA-4 | ICH Q9 risk-management evidence + Q10 PQS alignment | 21 days | CQCO | —
FDA-5 | FDA inspection-readiness playbook for Indian sponsors | 21 days | CHO + CQCO | Indian sponsor's FDA inspector may inspect Verixa as the QMS vendor
FDA-6 | MIRA AI v1 in advisory mode + GMLP / SaMD applicability scan | 21 days | AI Gov Lead + CQCO | Avoids 483 risk
FDA-7 | Audit trail FDA-export format (XML/CSV per Part 11 expectation) | 14 days | CTO + CQCO | Customer-facing feature
FDA-8 | HIPAA BAA template | DEFER to S2 | CLO | Not needed for India pilot
FDA-9 | SOC 2 Type II | DEFER to S2 | CISO | Type I optional interim

## Talent Plan
Section 5 — Re-Scoped Talent Plan (India Launch)
# | Role | Why Critical | Lead Time | Founder Ask
TA-1 | Head of QA (India) | Sponsor audit will request CV; QMS owner | 60–120 days | Approve req
TA-2 | AI Governance Lead | Annex 22 + FDA GMLP awareness even for India sponsors | 60–90 days | Approve req
TA-3 | DPO (India) | DPDPA likely mandatory post-SDF assessment | 30–60 days | Approve req
TA-4 | Validation Lead | IQ/OQ/PQ + VMP ownership | 60–90 days | Approve req
TA-5 | InfoSec Officer (India) | ISO 27001 + CERT-In ownership | 60–90 days | Approve req
TA-6 | Customer Success / Implementation Lead (India) | Onboarding + validation services | 60–90 days | Approve req
TA-7 | Sales Engineer — pharma regulated (India) | Pre-sales + demo + validation conversations | 60–90 days | Approve req
TA-8 | External advisors (India) — CDSCO consultant, FDA-regulated counsel (India practice), DPDPA counsel, intercompany tax counsel | Advisory panel | 30 days | Approve panel
— | DPO EU / UK Representative / EU Representative | Not needed (EU excluded) | — | —

## GTM Plan
Section 6 — Re-Scoped GTM Plan (India)
# | Item | Lead Time | Owner | Notes
GTM-1 | Pricing in INR — tiered (per user / site / study / workflow) + implementation services | 21 days | CSO + CFO | Optional USD billing for Indian customers exporting to US
GTM-2 | Capabilities deck — India sponsor variant | 30 days | CMO + CHO + CSO | Lead with CDSCO + Schedule M; secondary US FDA Part 11
GTM-3 | Battlecards — India market | 21 days | CMO + CSO | AmpleLogic, Trackwise (Sparta India), MasterControl India, Veeva Vault India, Caliber, Qualityze, ComplianceQuest, ZenQMS, Indian-built systems
GTM-4 | Trade body memberships | 14 days | CMO | OPPI, IPA, IDMA, BDMA, ISPE-India, PDA-India, DIA-India, NASSCOM Pharma SIG
GTM-5 | Trade-shows — India calendar | 30 days | CMO + CSO | Pharma Pro&Pack, India Pharma Expo, CPHI India, P-MEC India, ISPE-India Annual, PDA-India Annual, BioAsia
GTM-6 | Analyst briefings — India-aware | 30–60 days | CMO | Gartner India, IDC India, ISG India; Indian pharma analyst desks
GTM-7 | Partner / SI ecosystem (India) | 60 days | CSO + CCO | TCS Pharma, Infosys Life Sciences, Tata Elxsi, Wipro Pharma, Cognizant LSx, HCL Tech, Mu Sigma; Big4 India life-sciences; boutiques
GTM-8 | Website (verixa.in / verixa.co.in / verixa.health) v1.0 — India-first IA | 45 days | CMO + CTO | Approve domain choice
GTM-9 | Demo environment storyline — Indian sponsor with US-export workflow | 30 days | CMO + CCO | Approve script
GTM-10 | Reference customer programme — Indian design partners | 60–90 days | CSO + CCO + Founder | Lock 3 names
GTM-11 | Indian press launch + thought leadership (BioSpectrum India / Express Pharma / Pharmabiz) | 30 days | CMO | Approve
GTM-12 | Webinar series — India | Continuous | CMO + CHO | Approve themes

## Design Partners
Section 7 — Indian Design Partner Anchor Profile (Founder to lock 3 names)
Founder Advisor flags this as the single highest-leverage decision for the pilot launch window.
Profile | Why High-Leverage
Mid-tier Indian formulator with US-export footprint (≥1 USFDA-inspected site) | Already pays validation overhead; Part 11 + Schedule M dual-frame solves real pain
Indian biotech / clinical-stage company with active US IND/NDA path | GCP + Part 11 use case
Indian CRO with multi-sponsor footprint | Multi-tenant + Context Gate + RBAC sells naturally
Indian generic manufacturer with Schedule M v2024 obligation pressure | CDSCO + Schedule M control mapping is the wedge

## 90-Day Plan
Section 8 — Re-Scoped 90-Day Plan (India Pilot)
Phase | Phase Name | Deliverable / Action
Days 0–14 | Founder Lock Week | F0: Lock launching Indian entity (A/B/C) — everything downstream depends on this
Days 0–14 | Founder Lock Week | Lock 3 design partners (named)
Days 0–14 | Founder Lock Week | Lock pilot pricing (INR)
Days 0–14 | Founder Lock Week | Lock MIRA v1 = advisory only
Days 0–14 | Founder Lock Week | Lock canonical doc set (35 URS v2.0 vs 36 SDLC v4.0 vs 54 quality PDF)
Days 0–14 | Founder Lock Week | Resolve VX-VP-004 tech-stack contradiction (pure doc fix)
Days 0–14 | Founder Lock Week | Authorize VX-CDSCO-001 creation (10-day artifact)
Days 0–14 | Founder Lock Week | Engage Indian counsel panel (corporate, IP, pharma-regulatory, privacy)
Days 0–14 | Founder Lock Week | Open 7 senior India hires (TA-1 through TA-7)
Days 0–14 | Founder Lock Week | Bind cyber insurance market sounding (India broker)
Days 0–14 | Founder Lock Week | Engage ISO 27001 + ISO 9001 cert bodies (India-affiliated)
Days 14–45 | India Drafting Sprint | VX-CDSCO-001 delivered (Day 24)
Days 14–45 | India Drafting Sprint | Quality Manual + 7 policies signed
Days 14–45 | India Drafting Sprint | 15 SOPs drafted; 8 signed by Day 45
Days 14–45 | India Drafting Sprint | DPDPA §11 + §16 controls documented
Days 14–45 | India Drafting Sprint | DPDPA SDF assessment complete
Days 14–45 | India Drafting Sprint | DPO India appointed
Days 14–45 | India Drafting Sprint | VMP + VP + IQ/OQ/PQ templates drafted
Days 14–45 | India Drafting Sprint | MSA + DPA + SLA + AUP drafted (India law)
Days 14–45 | India Drafting Sprint | RoPA + Data Map (India lens)
Days 14–45 | India Drafting Sprint | Capabilities deck v1.0 (Indian sponsor variant)
Days 14–45 | India Drafting Sprint | Battlecards (India set)
Days 14–45 | India Drafting Sprint | Pricing locked in INR
Days 14–45 | India Drafting Sprint | F0 entity → GST/PAN/banking onboarding initiated (or confirmed if Aeonn Health Pvt Ltd)
Days 14–45 | India Drafting Sprint | Inter-co IP-license + services agreement drafted
Days 14–45 | India Drafting Sprint | Trademark Verixa™ India filed
Days 14–45 | India Drafting Sprint | Domain portfolio India-first secured
Days 14–45 | India Drafting Sprint | ISO 27001 gap assessment underway
Days 45–75 | India Evidence Sprint | Cyber insurance bound (INR tower)
Days 45–75 | India Evidence Sprint | ISO 27001 remediation in flight
Days 45–75 | India Evidence Sprint | Schedule M v2024 alignment evidence complete
Days 45–75 | India Evidence Sprint | CDSCO eSubmission integration plan
Days 45–75 | India Evidence Sprint | CERT-In integration into IRP complete
Days 45–75 | India Evidence Sprint | MeitY data-localization decision; CSP region locked
Days 45–75 | India Evidence Sprint | Customer Audit Pack skeleton (India lens) complete
Days 45–75 | India Evidence Sprint | Validation Bridge Document template
Days 45–75 | India Evidence Sprint | Vendor questionnaire response library — Indian-sponsor templates
Days 45–75 | India Evidence Sprint | AI governance pack: Annex 22 SOP kept as internal control (future-proof)
Days 45–75 | India Evidence Sprint | Per-regulator one-pagers — FDA + CDSCO only
Days 45–75 | India Evidence Sprint | Trade body memberships activated
Days 45–75 | India Evidence Sprint | Analyst briefings booked (India desks)
Days 45–75 | India Evidence Sprint | Indian SI partner LOIs (1–2)
Days 45–75 | India Evidence Sprint | 4 of 7 senior hires offered; 2 closed
Days 45–75 | India Evidence Sprint | Demo environment storyline locked
Days 75–90 | Mock Audit + Pilot Readiness | Mock sponsor audit (CDSCO + FDA-style) — internal first, then mock-external
Days 75–90 | Mock Audit + Pilot Readiness | Pen test executed; executive summary in Audit Pack
Days 75–90 | Mock Audit + Pilot Readiness | 21 CFR Part 11 Compliance Statement signed
Days 75–90 | Mock Audit + Pilot Readiness | Schedule M alignment statement signed
Days 75–90 | Mock Audit + Pilot Readiness | DPDPA compliance statement signed
Days 75–90 | Mock Audit + Pilot Readiness | Customer Audit Pack release-candidate
Days 75–90 | Mock Audit + Pilot Readiness | Stage-1 demo environment live (anonymized data)
Days 75–90 | Mock Audit + Pilot Readiness | First two design-partner conversations active (LOI / paid POC structure)
Days 75–90 | Mock Audit + Pilot Readiness | Founder Advisor pre-launch gate review
Days 75–90 | Mock Audit + Pilot Readiness | Stage-1 pilot launch authorization
Day 90 | FOUNDER GATE | F0 closed; ≥2 design partners in active engagement; mock audit pass; Head of QA + DPO India onboarded; SDF status decided; ISO 27001 stage-2 audit scheduled; cyber insurance bound; canonical doc set declared and stable

## Top 12 Monday
Section 9 — Top 12 to Start Monday (India-Pilot Edition)
# | Action
1 | F0 — Founder lock launching Indian entity (Aeonn Health vs Navira-India vs new Verixa India Pvt Ltd)
2 | VX-CDSCO-001 authorization — 10-day artifact, marquee India regulatory bundle
3 | 3 design partners locked (named, written commitment in flight)
4 | DPDPA SDF self-classification — drives DPO + DPIA + audit obligations
5 | ISO 27001 + ISO 9001 cert body engagement (India-affiliated TIC)
6 | Cyber insurance — India market sounding (broker engaged)
7 | Indian counsel panel locked (corporate, IP, pharma-regulatory, privacy, tax)
8 | Open 7 senior India reqs (Head of QA, AI Gov Lead, DPO, Validation Lead, InfoSec Officer, CS Lead, Sales Engineer)
9 | Lock pricing in INR + tiered model + implementation services
10 | Trademark Verixa™ India filed + domain portfolio locked (.in / .co.in / .health.in)
11 | Resolve VX-VP-004 tech-stack contradiction + declare canonical doc set
12 | Quality Manual + 15 SOPs drafting kickoff — assign owners; first 3 signed in Days 0–14

## Risks
Section 10 — Risks Specific to India-Pilot Scope
# | Risk | Detail
1 | F0 entity ambiguity | Every contract, billing, GST, intercompany flow stalls until locked
2 | DPDPA SDF classification | If SDF, obligations cascade (DPO + DPIA + algorithmic-audit), shifting timelines
3 | CSP / data-localization rules | Sectoral guidance for pharma-regulated SaaS in India still emerging; CSP region choice must be defensible against likely 12–18-month tightening
4 | Indian trademark squat risk | File Verixa™ India fast
5 | Schedule M v2024 transitional deadlines | Indian sponsors under pressure; pricing too high prices Verixa out; too low signals immaturity
6 | CERT-In 6-hour reporting rule | Most SaaS vendors miss this; build IRP to comply day-one
7 | Inter-co IP / services flow with Verixa Inc + Aeonn Ark | Transfer-pricing risk if not arm's length
8 | No EU now ≠ no EU forever | Keep architecture EU-capable so S2/S3 doesn't require rebuild; just don't certify or contract there yet
9 | MIRA v1 scope creep | If any India sponsor demands it bind GxP records, hold the line: advisory-only
10 | Sponsor-audit credentials | Head of QA's CV will be requested; do not pilot with the seat empty

## Founder Decisions
Section 11 — Founder Decisions (India-Pilot)
# | Decision | Default if No Decision
F0 | Launching Indian entity (Aeonn Health Pvt Ltd / Navira-India / new Verixa India Pvt Ltd) | Recommend Aeonn Health Pvt Ltd if speed dominates; new Verixa India Pvt Ltd if optionality dominates
F1 | Confirm 'no EU' lock | Locked per this brief
F2 | Confirm 'USFDA boundary preserved for Indian-customer use' interpretation | Locked per this brief
F3 | Approve VX-CDSCO-001 creation | Recommend approve
F4 | Lock MIRA v1 = advisory-only | Recommend approve
F5 | Lock 3 design partners (named) | Unknown — Founder + CSO
F6 | Approve cyber insurance INR tower | Unknown — Founder + CFO
F7 | Approve ISO 27001 + ISO 9001 cert body | Unknown — Founder + CISO + CQCO
F8 | Lock pricing tiers + INR pricing axes | Unknown — Founder + CFO + CSO
F9 | Approve 7 India senior hires (req open) | Recommend approve
F10 | Lock Indian counsel panel | Unknown — Founder + CLO
F11 | Lock CSP region (AWS Mumbai/Hyderabad / Azure India / GCP / Indian sovereign) | Unknown — Founder + CTO + CISO
F12 | Confirm Verixa Inc TN relocation closure timing (non-blocking for India pilot; needed for S2 US launch) | In progress — confirmation required
F13 | Approve Aeonn Ark ↔ Indian launching entity ↔ Verixa Inc IP-licensing + services-boundary mapping | Unknown — Founder + CLO + CFO