## Dashboard
VERIXA PATENT FILING — EXECUTIVE DASHBOARD
FAIL-SAFE: Current law and fees must be verified from the official IP India source (ipindia.gov.in) before filing or any docketed deadline. Counsel-review work product, not legal advice. Attorney review required before filing. See Legal_Corrections sheet for fact-fixes applied.
Status snapshot (today: 2026-05-25; provisional NOT YET FILED)
Inventor / Applicant | Vimal Veereshwarayya (US national, India resident)
Eventual assignee | Verixa newco (standalone — to be incorporated)
Current status | Provisional DRAFTED. NOT YET FILED. Phase 4 (pre-filing prep) in progress.
TODAY (project start) | 2026-05-25 (Mon)
FD — Filing day TARGET | 2026-06-15 (Mon) — anchors all post-filing dates
§39 clock end | 2026-07-27 (FD+6w)
PCT/intl decision + Form 3 #1 | 2026-12-15 (FD+6mo)
Complete spec deadline | 2027-06-15 (FD+12mo, HARD)
Publication | 2027-12-15 (FD+18mo)
US/EU national-phase (PCT) | 2028-12-15 (FD+30mo)
RFE deadline (CORRECTED) | 2029-01-15 (FD+31mo, HARD — Rule 24B amended 2024)
Patent expiry | 2046-06-15 (FD+20yr)
Fee estimate | ₹1,600 – ₹6,400 (natural person, e-filing)
Total tasks tracked | 81
Critical path tasks | 23
Filing readiness score | 72/100 (file as-is) — 82/100 (recommended w/ counsel review)
Phase completion summary
Phase | Done | In Progress | Pending | Optional
Phase 0 — Discovery & Strategy | 6 | 0 | 0 | 0
Phase 1 — India Prior-Art Search | 7 | 0 | 0 | 0
Phase 2 — Invention Disclosure + Counsel Package | 9 | 0 | 0 | 0
Phase 3 — Provisional Filing Documents (DRAFTED — NOT FILED) | 5 | 0 | 0 | 0
Phase 4 — Pre-Filing Preparation (CURRENT) | 1 | 1 | 1 | 2
Phase 5 — E-Filing (FD = 2026-06-15 target) | 0 | 0 | 9 | 0
Phase 6 — §39 6-week Window (POST-FILING) | 0 | 0 | 3 | 0
Phase 7 — Priority Year Months 1-6 (POST-FILING) | 0 | 0 | 8 | 0
Phase 8 — Priority Year Months 6-12 (POST-FILING) | 0 | 0 | 5 | 0
Phase 9 — Examination (Years 2-5) | 0 | 0 | 5 | 2
Phase 10 — Post-Grant (Years 5-20) | 0 | 0 | 6 | 1
Phase 11 — International Track (Parallel) | 0 | 0 | 3 | 1
Phase 12 — Verixa Newco Workstream (Parallel) | 0 | 0 | 5 | 1
TOTAL | 28 | 1 | 45 | 7

## Phase_Tracker
PHASE TRACKER — WBS + PREDECESSORS + SUCCESSORS + DATES (TODAY=2026-05-25; FD target=2026-06-15)
WBS | CP | Phase | Task | Status | Owner | Start | Finish | Predecessors | Successors | Notes
0.1 | ◄ | Phase 0 — Discovery & Strategy | Doctrine routing + role activation | Done | Vimal | 2026-05-24 | 2026-05-24 |  | 0.2 | Doctrine acknowledged
0.2 | ◄ | Phase 0 — Discovery & Strategy | Founder Decision Memo synthesis | Done | Vimal | 2026-05-24 | 2026-05-24 | 0.1 | 0.3, 0.4, 0.5, 0.6 | Verixa_Patent_Strategy_Founder_Memo.docx
0.3 |  | Phase 0 — Discovery & Strategy | Counsel Handoff Brief (pre-existing) | Done | Pre-existing |  |  | 0.2 | 0.6 | Verixa_Patent_Counsel_Handoff_Brief.docx
0.4 |  | Phase 0 — Discovery & Strategy | Deep Patent Search Report (pre-existing) | Done | Pre-existing |  |  | 0.2 | 0.6, 1.1 | Verixa_Deep_Patent_Search_Report.docx
0.5 |  | Phase 0 — Discovery & Strategy | IP Narrative for investor data room | Done | Pre-existing |  |  | 0.2 |  | Verixa_IP_Narrative_Investor_DataRoom.docx
0.6 | ◄ | Phase 0 — Discovery & Strategy | Portfolio framing (21 inventions identified) | Done | Vimal | 2026-05-24 | 2026-05-24 | 0.2, 0.3, 0.4 | 1.1, 2.1 | 00_Portfolio_Index.md
1.1 | ◄ | Phase 1 — India Prior-Art Search | Search log + 66 IP India queries executed | Done | Vimal | 2026-05-24 | 2026-05-24 | 0.6 | 1.2, 1.3, 1.4, 1.5, 1.6, 1.7 | India_Public_Search_2026-05-24/Search_Log.md
1.2 | ◄ | Phase 1 — India Prior-Art Search | Summary memo synthesizing findings | Done | Vimal | 2026-05-24 | 2026-05-24 | 1.1, 1.3, 1.4, 1.5, 1.6, 1.7 | 2.1, 2.4 | India_Public_Search_2026-05-24/Summary_Memo.md
1.3 |  | Phase 1 — India Prior-Art Search | Hit #1 Persistent IDE plugin captured | Done | — | 2026-05-24 | 2026-05-24 | 1.1 | 1.2 | 202521064491
1.4 |  | Phase 1 — India Prior-Art Search | ★★★ Hit #2 Persistent conflict scoring captured | Done | — | 2026-05-24 | 2026-05-24 | 1.1 | 1.2 | 202521129005
1.5 |  | Phase 1 — India Prior-Art Search | ★★ Hit #3 Poornima blockchain QA captured | Done | — | 2026-05-24 | 2026-05-24 | 1.1 | 1.2 | 202511131214
1.6 |  | Phase 1 — India Prior-Art Search | ★★★★ Hit #4 Semaladhari runtime control captured (CRITICAL) | Done | — | 2026-05-24 | 2026-05-24 | 1.1 | 1.2, 4.2 | 202641053068 — closest blocking-risk record
1.7 |  | Phase 1 — India Prior-Art Search | GxP-variants expanded search (11 queries) | Done | Vimal | 2026-05-24 | 2026-05-24 | 1.1 | 1.2, 7.2 | Confirms Verixa GxP claim space wide open in India
2.1 | ◄ | Phase 2 — Invention Disclosure + Counsel Package | IDD v1 (746 lines, 15 sections, 32 claims, 12 figures) | Done | Vimal | 2026-05-24 | 2026-05-24 | 1.2, 0.6 | 2.2, 2.3, 2.4, 2.5, 2.6, 2.7, 2.8, 2.9, 3.1, 8.2 | Verixa_Invention_Disclosure_Document.md
2.2 |  | Phase 2 — Invention Disclosure + Counsel Package | Counsel Cover Letter | Done | Vimal | 2026-05-24 | 2026-05-24 | 2.1 |  | 01_Cover_Letter.md
2.3 |  | Phase 2 — Invention Disclosure + Counsel Package | Filing Strategy doc (with §39 callout) | Done | Vimal | 2026-05-25 | 2026-05-25 | 2.1 |  | 02_Filing_Strategy.md
2.4 |  | Phase 2 — Invention Disclosure + Counsel Package | Prior Art Comparison Matrix | Done | Vimal | 2026-05-24 | 2026-05-24 | 1.2, 2.1 | 2.5 | 03_Prior_Art_Comparison_Matrix.md
2.5 |  | Phase 2 — Invention Disclosure + Counsel Package | Claim-to-Prior-Art Map | Done | Vimal | 2026-05-24 | 2026-05-24 | 2.4 | 2.6, 4.2 | 04_Claim_to_Prior_Art_Map.md
2.6 |  | Phase 2 — Invention Disclosure + Counsel Package | Risk Register (15 risks) | Done | Vimal | 2026-05-24 | 2026-05-24 | 2.4, 2.5 | 2.7 | 05_Risk_Register.md
2.7 |  | Phase 2 — Invention Disclosure + Counsel Package | Decisions Log (11 decisions locked) | Done | Vimal | 2026-05-24 | 2026-05-24 | 2.6 | 2.8 | 06_Decisions_Log.md
2.8 |  | Phase 2 — Invention Disclosure + Counsel Package | Open Items for Counsel (15 questions) | Done | Vimal | 2026-05-24 | 2026-05-24 | 2.7 | 4.2, 4.3 | 07_Open_Items_for_Counsel.md
2.9 | ◄ | Phase 2 — Invention Disclosure + Counsel Package | External reviewer feedback applied (35→72→82 score) | Done | Vimal | 2026-05-25 | 2026-05-25 | 2.1, 2.2, 2.3, 2.4, 2.5, 2.6, 2.7, 2.8 | 3.1 | Cleaner Form 2 produced
3.1 | ◄ | Phase 3 — Provisional Filing Documents (DRAFTED — NOT FILED) | Form 2 Provisional Specification (clean, technical-first) — DRAFTED | Done | Vimal | 2026-05-25 | 2026-05-25 | 2.1, 2.9 | 3.2, 3.3, 3.4, 3.5, 4.1, 4.4, 4.5, 5.2 | Drafted. NOT YET FILED. Filed/Verixa_Form2_Provisional_Specification.md
3.2 |  | Phase 3 — Provisional Filing Documents (DRAFTED — NOT FILED) | Form 1 Application — DRAFTED | Done | Vimal | 2026-05-25 | 2026-05-25 | 3.1 | 4.5, 5.2 | Drafted. NOT YET FILED.
3.3 |  | Phase 3 — Provisional Filing Documents (DRAFTED — NOT FILED) | Form 3 Section 8 Statement — DRAFTED | Done | Vimal | 2026-05-25 | 2026-05-25 | 3.1 | 4.5, 5.2, 7.8 | Drafted. NOT YET FILED.
3.4 |  | Phase 3 — Provisional Filing Documents (DRAFTED — NOT FILED) | Form 5 Declaration of Inventorship — DRAFTED | Done | Vimal | 2026-05-25 | 2026-05-25 | 3.1 | 4.5, 5.2 | Drafted. NOT YET FILED.
3.5 |  | Phase 3 — Provisional Filing Documents (DRAFTED — NOT FILED) | Fee calculation (₹1,600-6,400 estimate) | Done | Vimal | 2026-05-25 | 2026-05-25 | 3.1 | 5.3 | Filed/Verixa_Fee_Calculation.md
4.1 | ◄ | Phase 4 — Pre-Filing Preparation (CURRENT) | Drawings — 8 figures produced | In Progress | Vimal / illustrator | 2026-05-25 | 2026-05-30 | 3.1 | 4.5, 5.2 | Hand-sketch first; digitize via draw.io / Visio. ₹4-16K if outsourced. ~3-5 days
4.2 |  | Phase 4 — Pre-Filing Preparation (CURRENT) | OPTIONAL: Patent agent review of Claim 1 vs Semaladhari 053068 | Optional | Counsel (₹15-25K) | 2026-05-26 | 2026-06-08 | 2.5, 2.8, 1.6 | 4.5, 5.2, 8.3 | Lifts score 72→82. Recommended. ~1-2 weeks
4.3 |  | Phase 4 — Pre-Filing Preparation (CURRENT) | OPTIONAL: Sense7AI MSA + engineer IP-assignment review | Optional | Counsel | 2026-05-26 | 2026-06-01 | 2.8 | 4.5, 5.9 | Verifies sole-inventorship declaration in Form 5. ~1 week
4.4 |  | Phase 4 — Pre-Filing Preparation (CURRENT) | GitHub history confirmation (no public exposure) | Done | Vimal | 2026-05-25 | 2026-05-25 | 3.1 | 4.5 | Self-certified clean
4.5 | ◄ | Phase 4 — Pre-Filing Preparation (CURRENT) | Generate Form 1/2/3/5 PDFs (A4) + verify page counts | Pending | Vimal | 2026-06-12 | 2026-06-14 | 4.1, 4.4, 3.1, 3.2, 3.3, 3.4, 4.2, 4.3 | 5.2, 3.5 | Pandoc or Word. Confirm pdf page count for fee calc. ~1 day
5.1 | ◄ | Phase 5 — E-Filing (FD = 2026-06-15 target) | Log into IP India e-filing portal (ipindiaonline.gov.in) | Pending | Vimal | 2026-06-15 | 2026-06-15 | 4.5 | 5.2 | DSC required (already held). FD = filing day target
5.2 | ◄ | Phase 5 — E-Filing (FD = 2026-06-15 target) | ★ E-FILE: Upload Form 1 + Form 2 + drawings + Form 3 + Form 5 ★ | Pending | Vimal | 2026-06-15 | 2026-06-15 | 5.1, 4.5, 4.1, 4.4 | 5.3 | A4 PDF; max 10 MB per file. THIS IS THE FILING ACT
5.3 | ◄ | Phase 5 — E-Filing (FD = 2026-06-15 target) | Pay fee via online gateway | Pending | Vimal | 2026-06-15 | 2026-06-15 | 5.2, 3.5 | 5.4 | Net banking / card / UPI
5.4 | ◄ | Phase 5 — E-Filing (FD = 2026-06-15 target) | Receive application number + filing acknowledgement | Pending | IP India | 2026-06-15 | 2026-06-15 | 5.3 | 5.5 | Application number issued same day. PRIORITY DATE LOCKED
5.5 | ◄ | Phase 5 — E-Filing (FD = 2026-06-15 target) | Save filing receipt + ack + uploaded PDFs + SHA-256 hash of each | Pending | Vimal | 2026-06-15 | 2026-06-15 | 5.4 | 5.6, 5.7, 5.8, 5.9, 7.1, 7.2, 12.1 | Critical evidence for priority date defense
5.6 |  | Phase 5 — E-Filing (FD = 2026-06-15 target) | Calendar §39 6-week clock | Pending | Vimal | 2026-06-15 | 2026-06-15 | 5.5 | 6.1, 6.2, 7.8 | Ends 2026-07-27
5.7 | ◄ | Phase 5 — E-Filing (FD = 2026-06-15 target) | Calendar complete-spec deadline (FD+12mo) AND RFE deadline (FD+31mo) | Pending | Vimal | 2026-06-15 | 2026-06-15 | 5.5 | 8.4, 9.1 | Complete spec HARD: 2027-06-15. RFE HARD: 2029-01-15 (Rule 24B(1)(i) as amended 2024 — verify current law)
5.8 |  | Phase 5 — E-Filing (FD = 2026-06-15 target) | Calendar PCT/international decision (FD+6mo) | Pending | Vimal | 2026-06-15 | 2026-06-15 | 5.5 | 7.4 | Decision deadline: 2026-12-15
5.9 |  | Phase 5 — E-Filing (FD = 2026-06-15 target) | Notify counsel of filing (if engaged) | Pending | Vimal | 2026-06-15 | 2026-06-15 | 5.5, 4.3 | 7.1
6.1 |  | Phase 6 — §39 6-week Window (POST-FILING) | Monitor IP India for any §35 secrecy direction | Pending | Vimal / counsel | 2026-06-15 | 2026-07-27 | 5.6 | 6.3 | Rare for software inventions but legally required
6.2 |  | Phase 6 — §39 6-week Window (POST-FILING) | No foreign filings during this window | Pending | Vimal | 2026-06-15 | 2026-07-27 | 5.6 | 6.3 | §39 prohibition (US, PCT, EU, JP — nothing)
6.3 |  | Phase 6 — §39 6-week Window (POST-FILING) | §39 window cleared confirmation | Pending | Vimal / counsel | 2026-07-27 | 2026-07-28 | 6.1, 6.2 | 7.3, 7.4, 8.1, 11.1 | Date: 2026-07-28
7.1 |  | Phase 7 — Priority Year Months 1-6 (POST-FILING) | Persistent Systems portfolio monitoring | Pending | Counsel / Vimal | 2026-06-15 | 2026-12-15 | 5.9 | 7.4 | Monthly check for new filings by same applicant
7.2 |  | Phase 7 — Priority Year Months 1-6 (POST-FILING) | New India prior-art monitoring (control fabric, multi-agent, AI+audit) | Pending | Vimal | 2026-06-15 | 2026-12-15 | 1.7, 5.5 | 7.4 | Quarterly check
7.3 |  | Phase 7 — Priority Year Months 1-6 (POST-FILING) | International prior-art search (USPTO, EPO, WIPO) | Pending | Counsel | 2026-09-15 | 2026-11-15 | 6.3 | 7.4 | Required before PCT or US national-phase
7.4 |  | Phase 7 — Priority Year Months 1-6 (POST-FILING) | International strategy decision (PCT vs direct US/EU vs India-only) | Pending | Vimal + counsel | 2026-12-15 | 2026-12-15 | 5.8, 7.1, 7.2, 7.3, 6.3 | 8.1, 8.2, 11.1 | Recommended: PCT at FD+9-11mo
7.5 |  | Phase 7 — Priority Year Months 1-6 (POST-FILING) | Verixa newco incorporation | Pending | Corp counsel + Vimal | 2026-06-01 | 2026-11-30 | 12.1 | 7.6, 7.7, 12.3, 12.4 | Standalone; jurisdiction TBD pending tax advice
7.6 |  | Phase 7 — Priority Year Months 1-6 (POST-FILING) | DPIIT Startup recognition for Verixa newco | Pending | Corp counsel |  |  | 7.5 | 9.2, 12.4 | Within 1 month of incorporation. Preserves natural-person fees
7.7 |  | Phase 7 — Priority Year Months 1-6 (POST-FILING) | Vimal → Verixa newco IP assignment deed executed | Pending | Counsel + Vimal |  |  | 7.5, 12.3 |  | Pre-drafted; executed on incorporation day
7.8 |  | Phase 7 — Priority Year Months 1-6 (POST-FILING) | Form 3 (Section 8) — event-triggered upon any foreign filing | Pending | Vimal / counsel | 2026-06-15 | 2027-06-15 | 5.6, 3.3 | 8.5 | Per Rule 12(2) as amended 2024: file Form 3 within prescribed period of any foreign-application filing. NOT periodic. Verify current rule before docketing.
8.1 |  | Phase 8 — Priority Year Months 6-12 (POST-FILING) | PCT or direct national-phase filing | Pending | Counsel | 2027-03-15 | 2027-05-15 | 7.4, 6.3 | 11.2, 11.3 | FD+9-11mo. PCT provides 30-month decision window
8.2 | ◄ | Phase 8 — Priority Year Months 6-12 (POST-FILING) | Complete specification drafting begins | Pending | Counsel + Vimal | 2027-03-15 | 2027-05-15 | 2.1, 5.5, 7.4 | 8.3 | Adds 32 formal claims from IDD
8.3 | ◄ | Phase 8 — Priority Year Months 6-12 (POST-FILING) | Complete spec finalization with formal claims | Pending | Counsel | 2027-05-15 | 2027-05-31 | 8.2, 4.2 | 8.4 | Counsel review of full claim cascade strongly recommended
8.4 | ◄ | Phase 8 — Priority Year Months 6-12 (POST-FILING) | Complete specification filing (FD+12mo HARD) | Pending | Vimal / counsel | 2027-06-15 | 2027-06-15 | 8.3, 5.7 | 9.1 | HARD deadline: 2027-06-15. Missing = abandonment
8.5 |  | Phase 8 — Priority Year Months 6-12 (POST-FILING) | Form 3 update — at complete-spec filing or any foreign filing event | Pending | Vimal / counsel | 2027-06-15 | 2027-06-15 | 7.8, 8.4 |  | Event-triggered (not periodic) per Rule 12(2) as amended 2024. File whenever a new foreign filing occurs OR at complete-spec filing if intervening foreign filings exist. Verify current rule.
9.1 | ◄ | Phase 9 — Examination (Years 2-5) | Request for Examination (Form 18) — HARD deadline FD+31mo | Pending | Counsel | 2027-06-15 | 2029-01-15 | 8.4 | 9.3 | CORRECTED: Rule 24B(1)(i) as amended by Patents (Amendment) Rules 2024 (effective 15 March 2024) reduced RFE deadline from 48 months to 31 months. HARD deadline: 2029-01-15. Missing = abandonment. Verify current rule before docketing.
9.2 |  | Phase 9 — Examination (Years 2-5) | Expedited Examination (Form 18A) — OPTIONAL | Optional | Counsel |  |  | 9.1, 7.6 | 9.3 | If Verixa newco has DPIIT Startup recognition
9.3 | ◄ | Phase 9 — Examination (Years 2-5) | First Examination Report (FER) issued | Pending | IP India | 2031-06-15 | 2033-06-15 | 9.1 | 9.4 | ~1-3 years after RFE
9.4 | ◄ | Phase 9 — Examination (Years 2-5) | FER response | Pending | Counsel + Vimal |  |  | 9.3 | 9.5, 9.7 | Within 6 months of FER (extensions possible)
9.5 |  | Phase 9 — Examination (Years 2-5) | Hearing (if required) | Pending | Counsel |  |  | 9.4 | 9.7 | In-person or video hearing with Controller
9.6 |  | Phase 9 — Examination (Years 2-5) | Pre-grant opposition response (if any) | Optional | Counsel |  |  | 8.4 | 9.7 | Any time before grant under §25(1)
9.7 | ◄ | Phase 9 — Examination (Years 2-5) | Grant of patent | Pending | IP India | 2031-06-15 | 2033-06-15 | 9.4, 9.5, 9.6 | 10.1, 10.2 | Patent number issued; certificate received
10.1 |  | Phase 10 — Post-Grant (Years 5-20) | Post-grant opposition response (if any) | Optional | Counsel |  |  | 9.7 | 10.2 | Within 1 year of grant under §25(2)
10.2 |  | Phase 10 — Post-Grant (Years 5-20) | First renewal payment (Form 16) — covers years 3 onwards from date of patent | Pending | Counsel |  |  | 9.7 | 10.3 | Per §53 + Rule 80: renewals counted from date of patent (grant date), not filing date. First payment due before 2nd anniversary of grant (covering year 3). If grant happens >2yr after filing, retro renewals (years 3 to grant year) paid in lump within 3-9 months of grant recordal. Actual date depends on grant.
10.3 |  | Phase 10 — Post-Grant (Years 5-20) | Renewals years 3-6 (~₹800-2,400/yr natural-person rate) | Pending | Counsel |  |  | 10.2 | 10.4 | Annual. Date computed from grant date. Verify current fee schedule.
10.4 |  | Phase 10 — Post-Grant (Years 5-20) | Renewals years 7-10 (mid-tier fees, annual) | Pending | Counsel |  |  | 10.3 | 10.5 | Annual from grant date. Fee tier increases. Verify current fee schedule.
10.5 |  | Phase 10 — Post-Grant (Years 5-20) | Renewals years 11-20 (highest-tier fees, annual) | Pending | Counsel |  |  | 10.4 | 10.6 | Annual from grant date. Highest fee tier. Verify current fee schedule.
10.6 |  | Phase 10 — Post-Grant (Years 5-20) | Patent expiry (filing date + 20yr per §53(1)) | Pending | — | 2046-06-15 | 2046-06-15 | 10.5 |  | Date: 2046-06-15. Statutory 20-year term from FILING date (not grant date). Invention enters public domain.
10.7 |  | Phase 10 — Post-Grant (Years 5-20) | Form 27 Statement of Working — once per 3 financial year period | Pending | Counsel |  |  | 9.7 |  | CORRECTED: Rule 131(2) as amended 2024 — once per 3 FY period, within 6 months of period end. NOT annual. §122 penalty: up to ₹1 lakh + ₹1,000/day continuing default (Jan Vishwas Act 2023 amended). Missing = §84 compulsory-license vulnerability. Verify current rule.
11.1 |  | Phase 11 — International Track (Parallel) | PCT International Application | Pending | Counsel | 2027-03-15 | 2027-05-15 | 7.4, 6.3 | 11.2, 11.3, 11.4 | If PCT route chosen
11.2 |  | Phase 11 — International Track (Parallel) | US National Phase entry | Pending | US counsel | 2028-12-15 | 2028-12-15 | 11.1 |  | PCT: 2028-12-15 (FD+30mo) / direct: 2027-06-15
11.3 |  | Phase 11 — International Track (Parallel) | EU National Phase / EPO | Pending | EP counsel | 2028-12-15 | 2028-12-15 | 11.1 |  | PCT: 2028-12-15 (FD+30mo)
11.4 |  | Phase 11 — International Track (Parallel) | Other jurisdictions (JP, KR, CN) | Optional | Local counsel | 2028-12-15 | 2028-12-15 | 11.1 |  | Based on commercial strategy
12.1 |  | Phase 12 — Verixa Newco Workstream (Parallel) | Verixa newco jurisdiction decision | Pending | Vimal + tax counsel | 2026-06-01 | 2026-08-31 | 5.5 | 12.2 | India Pvt Ltd vs US Delaware C-Corp vs Cayman
12.2 |  | Phase 12 — Verixa Newco Workstream (Parallel) | Verixa newco incorporation | Pending | Corp counsel | 2026-07-01 | 2026-11-30 | 12.1 | 7.5, 12.3, 12.4, 12.5, 12.6 | Per jurisdiction selected
12.3 |  | Phase 12 — Verixa Newco Workstream (Parallel) | Vimal → Verixa newco IP assignment | Pending | Counsel |  |  | 12.2 | 7.7, 12.5 | Executed on Verixa incorporation day
12.4 |  | Phase 12 — Verixa Newco Workstream (Parallel) | DPIIT Startup recognition (Verixa newco) | Pending | Corp counsel |  |  | 12.2, 7.6 |  | Within 1 month of incorporation (if India)
12.5 |  | Phase 12 — Verixa Newco Workstream (Parallel) | IP-Chain Suite restructure (Engineer → Vimal → Verixa newco) | Pending | Counsel |  |  | 12.3 |  | Updates 16 existing templates
12.6 |  | Phase 12 — Verixa Newco Workstream (Parallel) | Update Aeonn Founder Doctrine workspace instructions | Optional | Vimal |  |  | 12.2 |  | Removes Aeonn Health → NaviraQA → Verixa vertical framing

## Dependency_Network
DEPENDENCY NETWORK — PREDECESSOR / SUCCESSOR / CRITICAL PATH
Critical Path (CP): the longest dependency chain from project start to grant. Delay on any CP task delays the grant date. Off-CP tasks have float (slack).
WBS | Task | Predecessors | Successors | On CP | Status | Finish
0.1 | Doctrine routing + role activation | (start) | 0.2 | YES | Done | 2026-05-24
0.2 | Founder Decision Memo synthesis | 0.1 | 0.3, 0.4, 0.5, 0.6 | YES | Done | 2026-05-24
0.3 | Counsel Handoff Brief (pre-existing) | 0.2 | 0.6 |  | Done
0.4 | Deep Patent Search Report (pre-existing) | 0.2 | 0.6, 1.1 |  | Done
0.5 | IP Narrative for investor data room | 0.2 | (end) |  | Done
0.6 | Portfolio framing (21 inventions identified) | 0.2, 0.3, 0.4 | 1.1, 2.1 | YES | Done | 2026-05-24
1.1 | Search log + 66 IP India queries executed | 0.6 | 1.2, 1.3, 1.4, 1.5, 1.6, 1.7 | YES | Done | 2026-05-24
1.2 | Summary memo synthesizing findings | 1.1, 1.3, 1.4, 1.5, 1.6, 1.7 | 2.1, 2.4 | YES | Done | 2026-05-24
1.3 | Hit #1 Persistent IDE plugin captured | 1.1 | 1.2 |  | Done | 2026-05-24
1.4 | ★★★ Hit #2 Persistent conflict scoring captured | 1.1 | 1.2 |  | Done | 2026-05-24
1.5 | ★★ Hit #3 Poornima blockchain QA captured | 1.1 | 1.2 |  | Done | 2026-05-24
1.6 | ★★★★ Hit #4 Semaladhari runtime control captured (CRITICAL) | 1.1 | 1.2, 4.2 |  | Done | 2026-05-24
1.7 | GxP-variants expanded search (11 queries) | 1.1 | 1.2, 7.2 |  | Done | 2026-05-24
2.1 | IDD v1 (746 lines, 15 sections, 32 claims, 12 figures) | 1.2, 0.6 | 2.2, 2.3, 2.4, 2.5, 2.6, 2.7, 2.8, 2.9, 3.1, 8.2 | YES | Done | 2026-05-24
2.2 | Counsel Cover Letter | 2.1 | (end) |  | Done | 2026-05-24
2.3 | Filing Strategy doc (with §39 callout) | 2.1 | (end) |  | Done | 2026-05-25
2.4 | Prior Art Comparison Matrix | 1.2, 2.1 | 2.5 |  | Done | 2026-05-24
2.5 | Claim-to-Prior-Art Map | 2.4 | 2.6, 4.2 |  | Done | 2026-05-24
2.6 | Risk Register (15 risks) | 2.4, 2.5 | 2.7 |  | Done | 2026-05-24
2.7 | Decisions Log (11 decisions locked) | 2.6 | 2.8 |  | Done | 2026-05-24
2.8 | Open Items for Counsel (15 questions) | 2.7 | 4.2, 4.3 |  | Done | 2026-05-24
2.9 | External reviewer feedback applied (35→72→82 score) | 2.1, 2.2, 2.3, 2.4, 2.5, 2.6, 2.7, 2.8 | 3.1 | YES | Done | 2026-05-25
3.1 | Form 2 Provisional Specification (clean, technical-first) — DRAFTED | 2.1, 2.9 | 3.2, 3.3, 3.4, 3.5, 4.1, 4.4, 4.5, 5.2 | YES | Done | 2026-05-25
3.2 | Form 1 Application — DRAFTED | 3.1 | 4.5, 5.2 |  | Done | 2026-05-25
3.3 | Form 3 Section 8 Statement — DRAFTED | 3.1 | 4.5, 5.2, 7.8 |  | Done | 2026-05-25
3.4 | Form 5 Declaration of Inventorship — DRAFTED | 3.1 | 4.5, 5.2 |  | Done | 2026-05-25
3.5 | Fee calculation (₹1,600-6,400 estimate) | 3.1 | 5.3 |  | Done | 2026-05-25
4.1 | Drawings — 8 figures produced | 3.1 | 4.5, 5.2 | YES | In Progress | 2026-05-30
4.2 | OPTIONAL: Patent agent review of Claim 1 vs Semaladhari 053068 | 2.5, 2.8, 1.6 | 4.5, 5.2, 8.3 |  | Optional | 2026-06-08
4.3 | OPTIONAL: Sense7AI MSA + engineer IP-assignment review | 2.8 | 4.5, 5.9 |  | Optional | 2026-06-01
4.4 | GitHub history confirmation (no public exposure) | 3.1 | 4.5 |  | Done | 2026-05-25
4.5 | Generate Form 1/2/3/5 PDFs (A4) + verify page counts | 4.1, 4.4, 3.1, 3.2, 3.3, 3.4, 4.2, 4.3 | 5.2, 3.5 | YES | Pending | 2026-06-14
5.1 | Log into IP India e-filing portal (ipindiaonline.gov.in) | 4.5 | 5.2 | YES | Pending | 2026-06-15
5.2 | ★ E-FILE: Upload Form 1 + Form 2 + drawings + Form 3 + Form 5 ★ | 5.1, 4.5, 4.1, 4.4 | 5.3 | YES | Pending | 2026-06-15
5.3 | Pay fee via online gateway | 5.2, 3.5 | 5.4 | YES | Pending | 2026-06-15
5.4 | Receive application number + filing acknowledgement | 5.3 | 5.5 | YES | Pending | 2026-06-15
5.5 | Save filing receipt + ack + uploaded PDFs + SHA-256 hash of each | 5.4 | 5.6, 5.7, 5.8, 5.9, 7.1, 7.2, 12.1 | YES | Pending | 2026-06-15
5.6 | Calendar §39 6-week clock | 5.5 | 6.1, 6.2, 7.8 |  | Pending | 2026-06-15
5.7 | Calendar complete-spec deadline (FD+12mo) AND RFE deadline (FD+31mo) | 5.5 | 8.4, 9.1 | YES | Pending | 2026-06-15
5.8 | Calendar PCT/international decision (FD+6mo) | 5.5 | 7.4 |  | Pending | 2026-06-15
5.9 | Notify counsel of filing (if engaged) | 5.5, 4.3 | 7.1 |  | Pending | 2026-06-15
6.1 | Monitor IP India for any §35 secrecy direction | 5.6 | 6.3 |  | Pending | 2026-07-27
6.2 | No foreign filings during this window | 5.6 | 6.3 |  | Pending | 2026-07-27
6.3 | §39 window cleared confirmation | 6.1, 6.2 | 7.3, 7.4, 8.1, 11.1 |  | Pending | 2026-07-28
7.1 | Persistent Systems portfolio monitoring | 5.9 | 7.4 |  | Pending | 2026-12-15
7.2 | New India prior-art monitoring (control fabric, multi-agent, AI+audit) | 1.7, 5.5 | 7.4 |  | Pending | 2026-12-15
7.3 | International prior-art search (USPTO, EPO, WIPO) | 6.3 | 7.4 |  | Pending | 2026-11-15
7.4 | International strategy decision (PCT vs direct US/EU vs India-only) | 5.8, 7.1, 7.2, 7.3, 6.3 | 8.1, 8.2, 11.1 |  | Pending | 2026-12-15
7.5 | Verixa newco incorporation | 12.1 | 7.6, 7.7, 12.3, 12.4 |  | Pending | 2026-11-30
7.6 | DPIIT Startup recognition for Verixa newco | 7.5 | 9.2, 12.4 |  | Pending
7.7 | Vimal → Verixa newco IP assignment deed executed | 7.5, 12.3 | (end) |  | Pending
7.8 | Form 3 (Section 8) — event-triggered upon any foreign filing | 5.6, 3.3 | 8.5 |  | Pending | 2027-06-15
8.1 | PCT or direct national-phase filing | 7.4, 6.3 | 11.2, 11.3 |  | Pending | 2027-05-15
8.2 | Complete specification drafting begins | 2.1, 5.5, 7.4 | 8.3 | YES | Pending | 2027-05-15
8.3 | Complete spec finalization with formal claims | 8.2, 4.2 | 8.4 | YES | Pending | 2027-05-31
8.4 | Complete specification filing (FD+12mo HARD) | 8.3, 5.7 | 9.1 | YES | Pending | 2027-06-15
8.5 | Form 3 update — at complete-spec filing or any foreign filing event | 7.8, 8.4 | (end) |  | Pending | 2027-06-15
9.1 | Request for Examination (Form 18) — HARD deadline FD+31mo | 8.4 | 9.3 | YES | Pending | 2029-01-15
9.2 | Expedited Examination (Form 18A) — OPTIONAL | 9.1, 7.6 | 9.3 |  | Optional
9.3 | First Examination Report (FER) issued | 9.1 | 9.4 | YES | Pending | 2033-06-15
9.4 | FER response | 9.3 | 9.5, 9.7 | YES | Pending
9.5 | Hearing (if required) | 9.4 | 9.7 |  | Pending
9.6 | Pre-grant opposition response (if any) | 8.4 | 9.7 |  | Optional
9.7 | Grant of patent | 9.4, 9.5, 9.6 | 10.1, 10.2 | YES | Pending | 2033-06-15
10.1 | Post-grant opposition response (if any) | 9.7 | 10.2 |  | Optional
10.2 | First renewal payment (Form 16) — covers years 3 onwards from date of patent | 9.7 | 10.3 |  | Pending
10.3 | Renewals years 3-6 (~₹800-2,400/yr natural-person rate) | 10.2 | 10.4 |  | Pending
10.4 | Renewals years 7-10 (mid-tier fees, annual) | 10.3 | 10.5 |  | Pending
10.5 | Renewals years 11-20 (highest-tier fees, annual) | 10.4 | 10.6 |  | Pending
10.6 | Patent expiry (filing date + 20yr per §53(1)) | 10.5 | (end) |  | Pending | 2046-06-15
10.7 | Form 27 Statement of Working — once per 3 financial year period | 9.7 | (end) |  | Pending
11.1 | PCT International Application | 7.4, 6.3 | 11.2, 11.3, 11.4 |  | Pending | 2027-05-15
11.2 | US National Phase entry | 11.1 | (end) |  | Pending | 2028-12-15
11.3 | EU National Phase / EPO | 11.1 | (end) |  | Pending | 2028-12-15
11.4 | Other jurisdictions (JP, KR, CN) | 11.1 | (end) |  | Optional | 2028-12-15
12.1 | Verixa newco jurisdiction decision | 5.5 | 12.2 |  | Pending | 2026-08-31
12.2 | Verixa newco incorporation | 12.1 | 7.5, 12.3, 12.4, 12.5, 12.6 |  | Pending | 2026-11-30
12.3 | Vimal → Verixa newco IP assignment | 12.2 | 7.7, 12.5 |  | Pending
12.4 | DPIIT Startup recognition (Verixa newco) | 12.2, 7.6 | (end) |  | Pending
12.5 | IP-Chain Suite restructure (Engineer → Vimal → Verixa newco) | 12.3 | (end) |  | Pending
12.6 | Update Aeonn Founder Doctrine workspace instructions | 12.2 | (end) |  | Optional
Critical Path chain
0.1 → 0.2 → 0.6 → 1.1 → 1.2 → 2.1 → 2.9 → 3.1 → 4.1 → 4.5 → 5.1 → 5.2 → 5.3 → 5.4 → 5.5 → 5.7 → 8.2 → 8.3 → 8.4 → 9.1 → 9.3 → 9.4 → 9.7

## Timeline
PATENT FILING TIMELINE — TODAY (2026-05-25) THROUGH PATENT EXPIRY (FD target 2026-06-15)
Date | Anchor | Milestone | Notes
2026-05-25 | TODAY | ◄ PROJECT TODAY — Phase 4 pre-filing prep starts | Provisional drafted; drawings + optional counsel review in progress
2026-05-30 | TODAY+5d | Drawings target completion (Phase 4.1) | 8 figures, hand-sketch first
2026-06-08 | TODAY+2w | Optional counsel review complete (Phase 4.2/4.3) | Claim 1 vs Semaladhari + MSA verification
2026-06-14 | FD-1 | Form 1/2/3/5 PDFs generated; pre-flight checks | A4 PDF; page-count fee confirmation
2026-06-15 | FD | ★★★ INDIAN PROVISIONAL FILED (target) ★★★ | PRIORITY DATE LOCKED; §39 clock starts
2026-07-27 | FD+6w | §39 6-week clock cleared | Foreign filings now permitted absent §35 secrecy direction
2026-12-15 | FD+6mo | First Form 3 update + PCT/international decision | Mandatory 6-month update; strategy decision
2027-03-15 | FD+9mo | PCT international filing window opens | If PCT route chosen
2027-06-15 | FD+12mo HARD | ★★★ COMPLETE SPECIFICATION DUE ★★★ | Missing = abandonment. Also PCT Paris Convention deadline
2027-12-15 | FD+18mo | Publication + Third Form 3 update | IP India publishes the application
2028-06-15 | FD+24mo | Fourth Form 3 update | Periodic reporting
2028-12-15 | FD+30mo | US + EU national-phase entry (PCT route) | USPTO and EPO filings
2029-06-15 | FD+36mo | Year-3 anniversary (no renewal yet) | Renewals years 1-3 deferred to year 4
2029-01-15 | FD+31mo HARD | Request for Examination deadline (Rule 24B amended 2024) | CORRECTED: 31 months not 48. Missing RFE = abandonment. Verify current rule.
2031-06-15 | FD+5yr | First Examination Report (FER) expected | Typical 1-3 years after RFE
2033-06-15 | FD+7yr | Grant expected (typical) | Subject to prosecution outcome
2046-06-15 | FD+20yr | ◄ Patent expiry | Statutory 20-year term ends

## Open_Items
OPEN ITEMS — WHAT IS PENDING RIGHT NOW (TODAY=2026-05-25; FD target=2026-06-15)
Bucket | Item | Status | Owner | Due | Notes
Phase 4 — drawings | Produce 8 drawings (4.1) | In Progress | Vimal / illustrator | 2026-05-30 | Hand-sketch then digitize; ~3-5 days
Phase 4 — counsel (opt) | Engage registered Indian patent agent (4.2) | Optional | Vimal | 2026-05-26 | ~₹15-25K for Claim 1 review
Phase 4 — counsel (opt) | Agent pulls Semaladhari 053068 complete spec + claims | Optional | Patent agent | 2026-06-01 | OI-1
Phase 4 — counsel (opt) | Agent reviews Verixa Claim 1 differentiation | Optional | Patent agent | 2026-06-08 | OI-1 (lifts 72→82)
Phase 4 — counsel (opt) | Agent reviews Sense7AI MSA + IP assignment (4.3) | Optional | Patent agent | 2026-06-08 | OI-4
Phase 4 — PDFs | Generate Form 1/2/3/5 PDFs (4.5) | Pending | Vimal | 2026-06-14 | A4; page-count confirmation
Phase 4 — PDFs | Confirm PDF page count for fee calculation | Pending | Vimal | 2026-06-14 | Determines ₹1,600-6,400
Phase 5 — E-FILE (FD) | Log into IP India portal + upload + pay (5.1-5.4) | Pending | Vimal | 2026-06-15 | ★ THE FILING ACT ★
Decisions open | Drawings: in-house or service? | Pending | Vimal | 2026-05-26
Decisions open | Counsel engagement scope (Claim 1 only or broader)? | Pending | Vimal | 2026-05-26
Decisions open | Target filing date: hold to 2026-06-15 or move earlier/later? | Pending | Vimal | 2026-06-01 | Earlier = lower score; later = stronger filing
Decisions open | Verixa newco jurisdiction (US / India / Cayman) | Pending | Vimal + tax | 2026-08-31 | Tax-coordinated
Decisions open | Verixa newco incorporation timing | Pending | Vimal | 2026-11-30
Pre-filing self-checks | No public disclosure confirmed | Done | Vimal | 2026-05-25 | Confirmed 2026-05-25
Pre-filing self-checks | DSC available | Done | Vimal | 2026-05-25 | Already held
Pre-filing self-checks | PAN linked to e-filing account | Pending | Vimal | 2026-06-15 | Required for online payment
Pre-filing self-checks | Bank/card/UPI ready for fee payment | Pending | Vimal | 2026-06-15 | ₹1,600-6,400

## Risk_Register
RISK REGISTER — 15 RISKS
ID | Risk | Severity | Likelihood | Affected Phases | Mitigation
R-1 | Semaladhari 053068 (multi-tenant runtime control) blocks core claims | CRITICAL | Medium | 4.2, 8.3 | Counsel pulls complete spec + claims; Verixa Claim 1 differentiation review
R-2 | Persistent 129005 (conflict scoring) blocks panel claims | HIGH | Medium | 4.2, 8.3 | Trade-secret specific weight values; agent-graph framing
R-3 | Sense7AI MSA IP-assignment chain incomplete → joint-inventorship challenge | HIGH | Low | 4.3, 5.4 | Counsel reviews MSA + engineer contracts before filing
R-4 | §3(k) software-patentability rejection at examination | HIGH | Medium | 9.3, 9.4 | Form 2 technical-effect framing; "technical contribution" emphasis
R-5 | §39 violation (foreign filing during 6-week window) | CRITICAL | Low | 6.1, 6.2 | Calendar lock; counsel notification of restriction
R-6 | Complete spec deadline (D0+12mo) missed → abandonment | CRITICAL | Low | 5.7, 8.4 | Multiple calendar entries; counsel engagement at month 8
R-7 | RFE deadline (D0+48mo) missed → abandonment | CRITICAL | Low | 5.7, 9.1 | Calendar; counsel quarterly check-in
R-8 | Public disclosure (GitHub, conference, blog) before filing invalidates novelty | CRITICAL | Very Low | 4.4 | Self-cert clean; GitHub history checked; no public talks
R-9 | Unity-of-invention rejection → divisional required | MEDIUM | Medium | 8.4 | Counsel reviews claims for unity; budget for divisional
R-10 | Pre-grant opposition by Persistent or another player | MEDIUM | Low | 9.6 | Strong prior-art map; counsel response capability
R-11 | Verixa newco incorporation delayed → IP assignment delayed | MEDIUM | Medium | 7.5, 12.2 | Vimal decides jurisdiction by Aug 2026; pre-drafted assignment deed
R-12 | DPIIT Startup recognition not obtained → corporate fee rates apply | MEDIUM | Low | 7.6, 10.x | Apply within 1 month of incorporation
R-13 | PCT/international decision delayed beyond month 12 | MEDIUM | Medium | 7.4, 11.1 | Decision deadline calendared at D0+6mo
R-14 | Fee underpayment due to misclassified applicant category | LOW | Very Low | 5.3 | Natural-person category locked; e-filing confirmed
R-15 | Drawings non-compliant with IP India formatting → office objection | LOW | Low | 4.1, 5.2 | Follow IP India Drawing Manual; A4, b/w, numbered

## Decisions_Log
DECISIONS LOG — 11 DECISIONS LOCKED
ID | Decision | Date Locked | Owner | Rationale
D-1 | File one umbrella Indian provisional covering Invention #1 | 2026-05-24 | Vimal | Maximum scope at minimum cost; 12 months to refine claims
D-2 | Vimal sole inventor + individual applicant (US national, India resident) | 2026-05-25 | Vimal | §39 applies → India-first filing required; assignment to Verixa newco later
D-3 | Verixa as standalone newco (not part of Aeonn or Sense7AI) | 2026-05-24 | Vimal | Clean cap-table for outside investment; clear IP perimeter
D-4 | No formal claims in provisional Form 2 | 2026-05-25 | Vimal | Per external reviewer recommendation; claims drafted at complete spec
D-5 | DIY filing (no patent agent of record) | 2026-05-24 | Vimal | Cost-conscious; optional ₹15-25K Claim 1 review by registered agent
D-6 | India-first filing strategy; international decision at D0+6mo | 2026-05-24 | Vimal | §39 compliance + observation of international landscape
D-7 | Trade-secret values (weights, thresholds, prompts) preserved out of disclosure | 2026-05-24 | Vimal | Per Founder Memo §7; specific values generalized in Form 2
D-8 | Sense7AI MSA engineer work = implementation, not inventive conception | 2026-05-24 | Vimal | Per Form 5 §2.3; supports sole-inventor declaration
D-9 | Class III DSC already held by applicant | 2026-05-25 | Vimal | No acquisition step needed for e-filing
D-10 | Address for service: Innovspace Coimbatore mailing address | 2026-05-25 | Vimal | Per Form 1 §5
D-11 | Chennai Patent Office as jurisdictional filing office | 2026-05-25 | Vimal | Per applicant residence (Tamil Nadu)

## Document_Index
DOCUMENT INDEX — ALL FILES IN Verixa_Patent/
Category | Document | Path (relative to Verixa_Patent/) | Purpose
Project Tracker | This tracker (md) | 00_Patent_Filing_Project_Tracker.md | End-to-end visibility (narrative)
Project Tracker | This tracker (xlsx) | 00_Patent_Filing_Project_Tracker.xlsx | End-to-end visibility (spreadsheet)
Filed Documents | Form 2 Provisional Specification | 04_Filing_Preparation/Filed/Verixa_Form2_Provisional_Specification.md | The actual filing
Filed Documents | Form 1 Application | 04_Filing_Preparation/Filed/Verixa_Form1_Application_for_Patent.md | Patent application form
Filed Documents | Form 3 Section 8 Statement | 04_Filing_Preparation/Filed/Verixa_Form3_Section8_Statement_Undertaking.md | Foreign filing undertaking
Filed Documents | Form 5 Declaration of Inventorship | 04_Filing_Preparation/Filed/Verixa_Form5_Declaration_of_Inventorship.md | Inventorship declaration
Filed Documents | Fee Calculation | 04_Filing_Preparation/Filed/Verixa_Fee_Calculation.md | ₹1,600-6,400 estimate
Master IDD | Invention Disclosure Document | 04_Filing_Preparation/Verixa_Invention_Disclosure_Document.md | 15 sections, 32 claims, 12 figures
Counsel Package | Cover Letter | 04_Filing_Preparation/Counsel_Review_Package_2026-05-24/01_Cover_Letter.md | Engagement briefing
Counsel Package | Filing Strategy (§39 callout) | 04_Filing_Preparation/Counsel_Review_Package_2026-05-24/02_Filing_Strategy.md | Filing approach
Counsel Package | Prior Art Comparison Matrix | 04_Filing_Preparation/Counsel_Review_Package_2026-05-24/03_Prior_Art_Comparison_Matrix.md | 4 hits vs Verixa
Counsel Package | Claim-to-Prior-Art Map | 04_Filing_Preparation/Counsel_Review_Package_2026-05-24/04_Claim_to_Prior_Art_Map.md | Per-claim risk
Counsel Package | Risk Register | 04_Filing_Preparation/Counsel_Review_Package_2026-05-24/05_Risk_Register.md | 15 risks
Counsel Package | Decisions Log | 04_Filing_Preparation/Counsel_Review_Package_2026-05-24/06_Decisions_Log.md | 11 decisions
Counsel Package | Open Items for Counsel | 04_Filing_Preparation/Counsel_Review_Package_2026-05-24/07_Open_Items_for_Counsel.md | 15 questions
India Prior-Art Search | Summary Memo | 01_Strategy_and_Search/India_Public_Search_2026-05-24/Summary_Memo.md | 66 queries synthesized
India Prior-Art Search | Search Log (66 queries) | 01_Strategy_and_Search/India_Public_Search_2026-05-24/Search_Log.md | Every query with result
India Prior-Art Search | Hit #4 Semaladhari (CRITICAL) | 01_Strategy_and_Search/India_Public_Search_2026-05-24/saved_records/202641053068_*.md | Closest blocking-risk record
India Prior-Art Search | Hit #2 Persistent (HIGH) | 01_Strategy_and_Search/India_Public_Search_2026-05-24/saved_records/202521129005_*.md | Data integrity + conflict scoring
India Prior-Art Search | Hit #3 Poornima (MEDIUM-HIGH) | 01_Strategy_and_Search/India_Public_Search_2026-05-24/saved_records/202511131214_*.md | Blockchain QA + audit trail
India Prior-Art Search | Hit #1 Persistent IDE plugin (background) | 01_Strategy_and_Search/India_Public_Search_2026-05-24/saved_records/202521064491_*.md | Same applicant signal
Pre-existing Strategy | Founder Decision Memo | 01_Strategy_and_Search/Verixa_Patent_Strategy_Founder_Memo.docx | Original strategic intent
Pre-existing Strategy | Counsel Handoff Brief | 01_Strategy_and_Search/Verixa_Patent_Counsel_Handoff_Brief.docx | Original verbatim claim seeds
Pre-existing Strategy | Deep Patent Search Report | 01_Strategy_and_Search/Verixa_Deep_Patent_Search_Report.docx | Prior-art research + 13 additional inventions
Pre-existing Strategy | IP Narrative (Investor Data Room) | 01_Strategy_and_Search/Verixa_IP_Narrative_Investor_DataRoom.docx | Investor-facing narrative
IP-Chain Suite (pending restructure) | 16 IP-assignment templates | 02_IP_Chain_Suite/ | Restructure to Vimal-individual → Verixa newco pending

## Owners
OWNERS & ENGAGEMENT STATUS
Role | Scope | Engagement
Vimal Veereshwarayya | Sole inventor + applicant; primary executor for all phases | Active
Patent Agent / Counsel (Indian) | OPTIONAL: Claim 1 review (Phase 4.2), MSA review (Phase 4.3), complete spec (Phase 8.3), examination (Phase 9) | NOT YET ENGAGED
Corporate Counsel | Verixa newco formation (Phase 12) | NOT YET ENGAGED
Tax Advisor | Cross-border US/India + Verixa newco jurisdiction (Phase 12.1) | NOT YET ENGAGED
US Counsel | USPTO national-phase (Phase 11.2, after D0+6mo) | NOT YET ENGAGED
EP Counsel | EPO/EP national-phase (Phase 11.3, after D0+6mo) | NOT YET ENGAGED
Illustrator / Draughtsman | Drawings (Phase 4.1) | NOT YET ENGAGED (Vimal can produce in-house)

## Legal_Corrections
LEGAL / REGULATORY CORRECTIONS — APPLIED 2026-05-26
FAIL-SAFE: Current law and fees must be verified from the official IP India source (ipindia.gov.in) before filing or any docketed deadline. This file encodes counsel-review work product, not legal advice. Attorney review required before filing.
ID | Item | Prior (wrong) | Corrected | Source / Rule
LC-1 | RFE deadline | 48 months from priority (2030-06-15) | 31 months from priority (2029-01-15) | Rule 24B(1)(i) as amended by Patents (Amendment) Rules 2024 (effective 15 March 2024)
LC-2 | Form 27 Statement of Working frequency | Annual filing post-grant (DA-3 framing) | Once per 3 financial year period, within 6 months of period end | Rule 131(2) as amended 2024
LC-3 | Form 27 / §122 penalty wording | ₹1 lakh to ₹10 lakh range | Up to ₹1 lakh + ₹1,000/day continuing default; false-statement penalty separate | Section 122 as amended by Jan Vishwas (Amendment of Provisions) Act 2023
LC-4 | Form 3 (Section 8) update timing | Periodic 6-month and 12-month updates (7.8, 8.5) | Event-triggered upon any foreign filing; not periodic | Rule 12(2) as amended 2024
LC-5 | Renewal schedule anchoring | Renewal year 4 dated FD+48mo (2030-06-15) | Renewals counted from date of patent (grant date), not filing date. First payment due before 2nd anniversary of grant (covers year 3+). If grant >2yr after filing, retro renewals paid in lump 3-9mo of grant. | Section 53 + Rule 80(1A)
LC-6 | DA-1 hardware/system embodiment risk | Deferred to Phase 8.3 (complete spec) as acceptance criterion | CONFIRMED SATISFIED in as-drafted Form 2 (lines 60, 315: "computer-implemented... operating on one or more processors... non-transitory computer-readable storage media"). System claims at complete-spec will be fairly based on this disclosure. | Form 2 §3 (lines 60-78), §7 (line 315). Verified 2026-05-26.
LC-7 | DA-7 US §367(d) exposure quantification | "7-figure exposure" (speculation without FMV) | "Potentially material exposure pending US tax counsel FMV analysis". §367(d) is transaction-structure dependent; exposure scales with FMV at transfer date. | 26 USC §367(d); 26 CFR 1.367(d)-1
LC-8 | DA-2 §31 grace-period acknowledgement | "India has no grace period" (overstated) | India is absolute novelty under §29, with narrow §31 safe harbors (paper at learned society, exhibition under §41, reasonable trial, communication to Government). Practical advice unchanged: do not rely on §31; audit fully. | Patents Act §29, §31, §41
LC-9 | Canonical tracker lock | Two tracker versions in circulation (uploaded xlsx with D0=2026-05-25 + repo xlsx with FD=2026-06-15) | Repo xlsx (generated from wbs_data.py) is canonical. Uploaded version is archived. wbs_data.py is the single source of truth; all derivatives regenerate from it. | Project hygiene; no statutory basis